|  |  |  | Proposal |
| --- | --- | --- | --- |
| Customer: Attention: Subject: | Falcon Power P.O. Box 2700 Big Spring, TX 79721 Mr. Allen Franco Maintenance Inspections of one (1) MS7001EA | Date: Proposal: | January 9, 2003 2002.47.28.4208 |
| 1. Description |  |  |  |
| Sermatech Power Solutions (Turbine Technology Service division) is pleased to provide the following proposal to Falcon Power for a turnkey Maintenance Inspections of one (1) MS7001EA heavy-duty gas turbine located at the Big Spring Facility in Big Spring, Texas. |  |  |  |
| 2. Workscope – Combustion Inspection |  |  |  |
| The following workscope is for the completion of a Combustion Inspection of one (1) MS7001EA heavy-duty gas turbine. Sermatech Power Solutions (SPS) shall supply two (2) Technical Directors, two (2) Millwright Supervisors, ten (10) Millwrights and all Tooling necessary to perform the inspection in three (3) days. Each day will consist of two (2) twelve (12) hour shifts. SPS assumes that all work will begin on a Monday. SPS will provide four (4) hours of support for start-up activities. Any additional start-up time will be provided on a Time and Materials basis. SPS has provided for one (1) pre-outage meeting and one (1) post-outage meeting at the Big Spring Facility. Two (2) SPS representatives have been designated to attend the pre outage meeting and one (1) SPS representative shall attend the post-outage meeting. Additional individuals requested by Falcon Power for either meeting shall be provided on a Time and Materials basis. |  |  |  |
| 2.1. | Disassembly |  |  |
|  | 2.1.1. Prepare turbine compartment roof for removal 2.1.2. Remove turbine compartment roof and side panels 2.1.3. Remove liquid fuel lines 2.1.4. Remove atomizing air lines 2.1.5. Remove gas fuel lines 2.1.6. Remove liquid fuel check valves 2.1.7. Remove steam or water injection lines 2.1.8. Remove fuel nozzle end cover assemblies |  |  |
| Sermatech Power Solutions |  | Proposal to Falcon Power |  |
| Proposal Number 2002.47.28.4208 |  | Page 1 of 19 |  |

| SERMATECH® |  |  |  |
| --- | --- | --- | --- |
|  |  | Proposal |  |
|  | 2.1.9. | Remove flame detectors and spark plugs |  |
|  | 2.1.10. Remove combustion liners and crossfire tubes 2.1.11. Remove flow sleeves 2.1.12. Remove combustion casings number 2, 4, 7 and 9 to facilitate transition removal 2.1.13. Remove transition pieces 2.2. Inspection Procedure |  |  |
|  | 2.2.1. 2.2.2. 2.2.3. 2.2.4. 2.2.5. 2.2.6. 2.2.7. 2.2.8. 2.2.9. | Pressure test fuel oil check valves (by customer or outside services) Fuel nozzle inspection Inspect crossfire tubes and retainers Inspect transition pieces Inspect combustion chamber flow sleeves Inspect combustion chambers Inspect 1st stage nozzle Inspect and test spark plugs (by customer or outside services) Inspect and test flame detectors (by customer or outside services) |  |
|  | 2.3. Reassembly |  |  |
| 3. | 2.3.1. 2.3.2. 2.3.3. 2.3.4. 2.3.5. 2.3.6. 2.3.7. 2.3.8. 2.3.9. | Install transition pieces Install combustion chambers number 2, 4, 7 and 9 Install flow sleeves and combustion liners Install combustion casing covers and fuel nozzles Install flame detectors and spark plugs Install fuel oil check valves Install liquid fuel tubing Install atomizing air piping Install fuel gas piping |  |
|  | 2.3.10. Set and bolt turbine compartment roof and side panels 2.3.11. Leak check liquid fuel connections 2.3.12. Clean-Up / Visual Inspection / Start-Up |  |  |
|  | Workscope – Hot Gas Path Inspection |  |  |
|  | The following workscope is for the completion of a Hot Gas Path Inspection of one (1) MS7001EA heavy-duty gas turbine. Sermatech Power Solutions (SPS) shall supply two (2) Technical Directors, two (2) Millwright Supervisors, ten (10) Millwrights and all Tooling necessary to perform the inspection in ten (10) days. Each day will consist of two (2) twelve (12) hour shifts. SPS assumes that all work will begin on a Monday. SPS will provide four (4) hours of support for start-up activities. Any additional start-up time will be provided on a Time and Materials basis. |  |  |
| Sermatech Power Solutions |  |  | Proposal to Falcon Power |
| Proposal Number 2002.47.28.4208 |  |  | Page 2 of 19 |

|  | Proposal |
| --- | --- |
| SPS has provided for one (1) pre-outage meeting and one (1) post-outage meeting at the Big Spring Facility. Two (2) SPS representatives have been designated to attend the pre outage meeting and one (1) SPS representative shall attend the post-outage meeting. Additional individuals requested by Falcon Power for either meeting shall be provided on a Time and Materials basis. |  |
| 3.1. | Disassembly 3.1.1. Prepare turbine compartment roof for removal 3.1.2. Remove turbine compartment roof and side panels 3.1.3. Remove exhaust and inlet duct access panels 3.1.4. Remove liquid fuel lines 3.1.5. Remove atomizing air lines 3.1.6. Remove fuel gas lines 3.1.7. Remove liquid fuel check valves 3.1.8. Remove steam or water injection lines 3.1.9. Remove fuel nozzles and end cover assemblies |
| 3.2. | 3.1.10. Remove flame detectors and spark plugs 3.1.11. Removed combustion liners and crossfire tubes 3.1.12. Removed flow sleeves 3.1.13. Remove upper half cooling and sealing air piping 3.1.14. Remove combustion casings number 2, 4, 7 and 9 to facilitate rotor positioning check 3.1.15. Take opening compressor and turbine rotor positioning checks 3.1.16. Remove wheelspace thermocouples 3.1.17. Install mechanical jacks under turbine casings 3.1.18. Remove turbine casing bolts 3.1.19. Remove upper half turbine casing 3.1.20. Remove transition pieces 3.1.21. Check and record 1st stage radial concentricity 3.1.22. Remove upper half 1st stage nozzle segment 3.1.23. Remove upper half 1st stage support ring 3.1.24. Check and record rotor thrust 3.1.25. Check and record turbine section opening clearances 3.1.26. Remove lower half 1st stage nozzle segment 3.1.27. Remove 2nd and 3rd stage nozzle segments (lower and upper) Inspection Procedure |
|  | 3.2.1. Pressure test fuel oil check valves (by customer or outside services) 3.2.2. Inspect fuel nozzles 3.2.3. Inspect combustion liners 3.2.4. Inspect crossfire tubes and retainers |

|  |  | Proposal |
| --- | --- | --- |
|  | 3.2.5. 3.2.6. 3.2.7. 3.2.8. 3.2.9. | Inspect combustion chamber flow sleeves Inspect combustion chambers Inspect and test spark plugs (by customer or outside services) Inspect and test flame detectors (by customer or outside services) Inspect 1st, 2nd and 3rd stage nozzles |
| 3.3. | 3.2.10. Inspect 1st, 2nd and 3rd stage buckets 3.2.11. Inspect 1st, 2nd and 3rd stage shroud blocks 3.2.12. Inspect 2nd and 3rd stage diaphragm segments 3.2.13. Check and record 1st stage nozzle ellipticity Reassembly |  |
|  | 3.3.1. 3.3.2. 3.3.3. 3.3.4. 3.3.5. 3.3.6. 3.3.7. 3.3.8. 3.3.9. | Install lower half 1st stage nozzle segment and eccentric pin Install lower half 2nd and 3rd stage nozzle segments Check and record turbine section closing clearances Install 1st stage upper half support ring Install upper half 1st stage nozzle segment Check and record 1st stage nozzle concentricity Install upper half 2nd and 3rd stage nozzle segments Install transition pieces Set and bolt upper half turbine casing |
|  | 3.3.10. Install wheelspace thermocouples 3.3.11. Install upper half cooling and sealing air piping 3.3.12. Remove turbine support jacks from under turbine casing 3.3.13. Check and record final rotor positioning checks 3.3.14. Install combustion chambers number 2, 4, 7 and 9 3.3.15. Install flow sleeves and combustion liners 3.3.16. Install combustion chamber end covers and fuel nozzle assemblies 3.3.17. Install flame detectors and spark plugs 3.3.18. Install liquid fuel check valves 3.3.19. Install liquid fuel tubing 3.3.20. Install atomizing air piping 3.3.21. Install fuel gas piping 3.3.22. Set and bolt turbine compartment roof and side panels 3.3.23. Bolt exhaust and inlet access covers in place 3.3.24. Clean-Up / Leak Check / Start-Up |  |

| SERMATECH® |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Proposal |  |  |  |
| 4. | Workscope – Major Inspection |  |  |  |
| The following workscope is for the completion of a Major Inspection of one (1) |  |  |  |  |
| MS7001EA heavy-duty gas turbine. Sermatech Power Solutions (SPS) shall supply two |  |  |  |  |
| (2) Technical Directors, two (2) Millwright Supervisors, twelve (12) Millwrights and all |  |  |  |  |
| Tooling necessary to perform the inspection in twenty-four (24) days. Each day will |  |  |  |  |
| consist of two (2) twelve (12) hour shifts. SPS assumes that all work will begin on a |  |  |  |  |
| Monday. SPS will provide four (4) hours of support for start-up activities. Any |  |  |  |  |
| additional start-up time will be provided on a Time and Materials basis. |  |  |  |  |
| SPS has provided for one (1) pre-outage meeting and one (1) post-outage meeting at the |  |  |  |  |
| Big Spring Facility. Two (2) SPS representatives have been designated to attend the pre |  |  |  |  |
| outage meeting and one (1) SPS representative shall attend the post-outage meeting. |  |  |  |  |
| Additional individuals requested by Falcon Power for either meeting shall be provided |  |  |  |  |
| on a Time and Materials basis. |  |  |  |  |
| 4.1. |  | Disassebmly |  |  |
|  |  | 4.1.1. | Visually Inspect all Compartments |  |
|  |  | 4.1.2. | Remove all Accessory Shaft Bolts & Remove Shaft |  |
|  |  | 4.1.3. | Remove Load Coupling Bolts ( Turbine End ) & Split Shaft |  |
|  |  | 4.1.4. | Check Unit Alignment |  |
|  |  | 4.1.5. | Remove Air Inlet Elbow Lifting Hatch |  |
|  |  | 4.1.6. | Remove Fwd upper half Air Inlet Plenum Chamber Wall |  |
|  |  | 4.1.7. | Remove all Lube Oil Vent Pipework |  |
| Remove Turbine Roof & side panels |  |  |  |  |
| Remove Exhaust Plenum Top Hat4.1.8. |  |  |  |  |
| 4.1.9. |  | 4.1.10. Remove Exhaust Plenum Side Panel 4.1.11. Remove Exhaust Frame / Exhaust Plenum Flexi Seals 4.1.12. Remove Exhaust Diffuser / Exhaust Plenum Flexi Seals 4.1.13. Remove Exhaust Plenum Fwd Wall 4.1.14. Remove Exhaust Plenum Chamber Insulation Panels 4.1.15. Remove Cooling & Sealing Air Piping 4.1.16. Remove Compressor Bleed Valves 4.1.17. Remove all Fuel Gas / Oil / Water Pigtail Pipes 4.1.18. Remove all Upper Half Gas / Oil / Air Manifolds |  |  |
|  |  | 4.1.19. Remove Spark Plugs & Flame Detectors 4.1.20. Remove all Fuel Nozzles 4.1.21. Remove all Combustion Covers 4.1.22. Remove all Combustion Liners, Cross Fire Tubes 4.1.23. Remove all Combustion Chambers 4.1.24. Carry Out Clearance'o'meter Checks |  | & Retainers |
| Sermatech Power |  | Solutions |  | Proposal to Falcon Power |
| Page 5 of 19Proposal Number |  |  |  |  |

2002.47.28.4208

| 4.2.Proposal |  |
| --- | --- |
| 4.1.25. Fit Casing Support Jacks 4.1.26. Remove all Combustion Wrapper Bolting 4.1.27. Remove Upper Half Combustion Wrapper 4.1.28. Measure Transition Piece Throat Clearances 4.1.29. Remove all Transition Pieces 4.1.30. Remove All Inlet Casing Bolts 4.1.31. Remove Upper Half Inlet Casing 4.1.32. Remove all Fwd & Aft Compressor Casing Bolting 4.1.33. Remove Upper Halves Fwd & Aft Compressor Casings 4.1.34. Remove all Turbine Shell Bolting 4.1.35. Remove Upper Half Turbine Shell 4.1.36. Remove all Compressor Discharge Casing Bolts 4.1.37. Remove Upper Half Compressor Discharge Casing 4.1.38. Remove all Inner Barrel Bolts 4.1.39. Remove Upper Half Inner Barrel 4.1.40. Remove Upper Half 1st Stage Nozzle 4.1.41. Remove Upper Half 1st Stage Nozzle Support Ring 4.1.42. Remove Aft Exhaust Diffuser Insulation Panels (For Bolt Removal) 4.1.43. Remove all Exhaust Frame / Diffuser Bolts 4.1.44. Remove Upper Half Exhaust Frame / Diffuser 4.1.45. Check Axial Float Of GT Rotor 4.1.46. Remove all Upper Halves of Bearing Housings 4.1.47. Record all Bearing / Seal Clearances 4.1.48. Remove All Rotor Coupling Bolts 4.1.49. Install Compressor Rotor Support & Split Coupling 4.1.50. Remove Turbine Rotor 4.1.51. Remove Compressor Rotor 4.1.52. Remove Lower Half 1st Stage Nozzle 4.1.53. Remove Upper Half 2nd Stage Nozzle Segments 4.1.54. Remove Lower Half 2nd Stage Nozzle Segments 4.1.55. Remove Upper Half 3rd Stage Nozzle Segments 4.1.56. Remove Lower half 3rd Stage Nozzle Segments Inspection/Disassembly | 4.2.1. Take & Record a Full Set of Turbine Clearances 4.2.2. Carry Out TIL 1151-3 Nozzle Creep Deflection 4.2.3. Carry Out TIL's 1132-2, 1068-2 & 517 - IGV's |
|  | 4.2.4. Take & Record a Full Set of Compressor Clearances 4.2.5. Inspect all Turbine / Compressor Components 4.2.6. Record All Damage to Compressor / Turbine Components 4.2.7. Measure / Inspect Turbine Bearings |
| Sermatech Power |  |
| Proposal NumberSolutions Proposal to Falcon Power |  |

2002.47.28.4208	Page 6 of 19

|  |  | Proposal |
| --- | --- | --- |
| 4.3. | Unit Preassembly |  |
|  | 4.3.1. 4.3.2. 4.3.3. 4.3.4. 4.3.5. | Clean out lower half turbine / compressor casings Re-assemble lower half 1st stage nozzle Re-assemble lower half 2nd Stage Nozzle Segments Re-assemble lower half 3rd Stage Nozzle Segments Carry out final inspection of lower half turbine / compressor casings |
| 4.4. 4.5. | Inspection/Reassembly |  |
|  | 4.4.1. 4.4.2. 4.4.3. | Take & Record a Full Set of Turbine Clearances Carry Out TIL 1151-3 Nozzle Creep Deflection Take & Record a Full Set of Compressor Clearances |
|  | Unit Reassembly |  |
| Sermatech Power Proposal Number | 4.5.1. 4.5.2. 4.5.3. 4.5.4. 4.5.5. 4.5.6. 4.5.7. 4.5.8. 4.5.9. | Re-install Compressor Rotor Re-install Turbine Rotor Marry Turbine Rotor to Compressor Rotor Install all Bearing Oil Seals & Liners Record all Bearing / Seal Clearances Re-assemble all Upper Halves of Bearing Housings Check Axial Float Of GT Rotor Re-assemble Upper Half 1st Stage Nozzle Support Ring Re-assemble Upper Half 1st Stage Nozzle |
|  | 4.5.10. Align 1st stage nozzle ( Grind Shims ) 4.5.11. Re-assemble Upper half 2nd Stage Nozzle Segments 4.5.12. Re-assemble Upper half 3rd Stage Nozzle Segments 4.5.13. Re-assemble Upper Half Inner Barrel 4.5.14. Secure all Inner Barrel Bolts 4.5.15. Re-assemble Upper Half Compressor Discharge Casing 4.5.16. Secure all Compressor Discharge Casing Bolts 4.5.17. Re-assemble Upper Halves Fwd & Aft Compressor Casings 4.5.18. Secure Fwd / Aft Compressor Casings with all Bolting 4.5.19. Re-assemble Upper Half Inlet Casing 4.5.20. Secure All Inlet Casing Bolts 4.5.21. Re-assemble all Transition Pieces 4.5.22. Measure T/P Throat Clearances 4.5.23. Re-assemble Upper Half Turbine Shell 4.5.24. Secure Turbine Shell with New Bolting 4.5.25. Re-assemble upper half Combustion Wrapper 4.5.26. Secure Combustion Wrapper with new Bolting |  |
|  | Solutions | 2002.47.28.4208 Proposal to Falcon Power Page 7 of 19 |

| SERMATECH® |  |  |
| --- | --- | --- |
|  | Proposal |  |
| 5. | 4.5.27. Re-assemble Upper Half Exhaust Frame / Diffuser 4.5.28. Secure all Exhaust Frame / Diffuser Bolts 4.5.29. Remove Casing Support Jacks 4.5.30. Re-assemble all Combustion Chambers 4.5.31. Re-assemble all Combustion Liners, Cross Fire Tubes & Retainers 4.5.32. Re-assemble all Combustion Covers 4.5.33. Re-assemble all Secondary Fuel Nozzles 4.5.34. Re-assemble Spark Plugs & Flame Detectors 4.5.35. Re-assemble all Upper Half Gas / Oil / Air Manifolds 4.5.36. Re-assemble all Fuel Gas / Oil / Air Pigtail Pipes 4.5.37. Re-assemble Cooling & Sealing Air Piping 4.5.38. Re-assemble Upper Half Air Inlet Plenum Chamber 4.5.39. Re-assemble Air Inlet Transition Piece 4.5.40. Re-assemble Air Inlet Elbow 4.5.41. Re-assemble Turbine Roof & side panels 4.5.42. Re-assemble New Lube Oil Vent Pipework 4.5.43. Re-assemble Aft Exhaust Diffuser Insulation Panels 4.5.44. Re-assemble Exhaust Plenum Chamber Insulation Panels 4.5.45. Re-assemble Exhaust Plenum Side Panel 4.5.46. Re-assemble Exhaust Plenum Top Hat 4.5.47. Re-assemble new Exhaust Frame / Exhaust Diffuser Flexi Seals 4.5.48. Re-assemble new Exhaust Diffuser / Exhaust Plenum Flexi Seals 4.5.49. Check / Adjust Unit Alignment 4.5.50. Re-install Load Coupling Bolts ( Turbine End ) & Secure Shaft 4.5.51. Re-assemble Accessory Shaft & Secure With all Bolting 4.5.52. Final Inspection of Air Inlet Filter House, Trash Screen & Plenum Chamber 4.5.53. Final Inspection of Exhaust Plenum Chamber & Ducting Steam Turbine – Minor Inspection The following workscope is for the completion of a Minor Inspection of one (1) Steam Turbine. Sermatech Power Solutions (SPS) shall supply one (1) Technical Director, one (1) Millwright Supervisor, four (4) Millwrights and all Tooling necessary to perform the inspection in seven (7) days. Each day will consist of one (1) ten (10) hour shift. SPS assumes that all work will begin on a Monday. SPS will provide four (4) hours of support for start-up activities. Any additional start-up time will be provided on a Time and Materials basis. Please note: Falcon Power will be responsible for any overhauls associated with the Steam Turbine valves. SPS has provided for one (1) pre-outage meeting and one (1) post-outage meeting at the Big Spring Facility. Two (2) SPS representatives have been designated to attend the pre |  |
| Sermatech Power Solutions |  |  |
| Proposal Number 2002.47.28.4208Proposal to Falcon Power |  | Page 8 of 19 |

| SERMATECH® |  |  |  |
| --- | --- | --- | --- |
| 110w i' SciIutir ns |  |  |  |
| Proposal |  |  |  |
|  | outage meeting and one (1) SPS representative shall attend the post-outage meeting. Additional individuals requested by Falcon Power for either meeting shall be provided on a Time and Materials basis. |  |  |
|  | • |  | Inspect bearings and valves with turbine case in place |
| Inspect exhaust valve |  |  |  |
| Inspect high pressure control valve• |  |  |  |
| Inspect four (4) return valves• |  |  |  |
| • | • |  | Inspect LP buckets |
|  | • |  | Inspect number 3 bearing |
| 6. |  |  |  |
| 6.5.Notes |  | Falcon Power Responsibilities |  |
| 6.5.1. |  |  |  |
| 6.5.2.Falcon Power shall provide normal operational activities. |  |  |  |
| 6.5.3.Falcon Power to provide I & C personnel to perform instrument and |  |  | electrical disconnections. Falcon Power will check and calibrate gauges, instrumentation and |
| 6.5.4. |  |  |  |
| 6.5.5.thermocouples associated with the turbine generator (if required). Falcon Power will arrange for any required disassembly of fuel nozzles |  |  | and/or flow testing. Falcon Power will be responsible for any overhauls associated with the |
| 6.5.6. |  |  |  |
| 6.5.7.Steam Turbine valves. Electrical power (120/208, single phase and 208/480, three phase), |  |  |  |
| 6.5.8.necessary water, compressed air (120 psi) and lubricants as necessary shall be provided by Falcon Power. Falcon Power will make available to SPS all special tooling required to |  |  |  |
| 6.5.9.work on the unit or to facilitate disassembly or reassembly of the unit (if required). In the event that any asbestos materials or lead paint are encountered, |  |  | Falcon Power will be notified and it shall be Falcon Power’s responsibility for all asbestos abatement. Falcon Power will supply any necessary cranes or forklifts. |
| Sermatech Power Solutions |  |  |  |
| Proposal Number 2002.47.28.4208Proposal to Falcon Power |  |  |  |

Page 9 of 19

|  |  | Proposal |
| --- | --- | --- |
|  | 6.5.10. Falcon Power is responsible for the provision of oxy-acetylene and/or transport of same. 6.5.11. Falcon Power shall provide containers for rags and solvent disposal and shall provide disposal of same. 6.5.12. Timber, skids, rotor stands, pallets etc. needed for the disassembled parts shall be supplied by Falcon Power. 6.5.13. Falcon Power will provide renewal parts, including normal manufacturer supplied pre-cut gaskets and gasket materials. 6.5.14. Falcon Power to supply all in–house manuals, Technical Information Letters/Service Bulletins and drawings pertaining to the work. |  |
| 6.6. |  |  |
| 6.6.1.6.5.15. Fire protection equipment must be available from Falcon Power. 6.6.2. 6.6.3. 6.6.4. 6.6.5. 6.6.6. 6.6.7. 6.6.8. Sermatech Power Solutions Proposal Number 2002.47.28.4208 6.5.16. Falcon Power shall supply one (1) analog phone line and 220 VAC power. 6.5.17. Falcon Power shall supply toilet and wash facilities. Technical Clarifications |  | SPS shall provide non-union labor for the inspections. SPS reserves the right to adjust staffing levels in order to maintain inspection schedule. No site-specific training has been provided. Any necessary training will be the responsibility of Falcon Power. Falcon Power will be billed on a Time and Materials basis (see attached rate sheet) for any time spent for training. Additional component removal outside of those described in Sections 2-4 will be provided on a Time and Materials basis (see attached). Any requested component repair(s) outside of those described in Sections 2-5 will be provided on a Time and Materials basis. No requested component repair(s) shall be performed without prior written approval from Falcon Power. One (1) mobilization and one (1) demobilization has been provided within the scope of supply. Additional costs may be incurred for any delays. Additional demobilization and remobilization fees will apply on a per man, per occurrence basis according to their classification. Start-up shall immediately follow mechanical completion of the unit. All materials brought on site shall have a MSDS sheet. Proposal to Falcon Power Page 10 of 19 |

| SERMATECH® |  |  |  |
| --- | --- | --- | --- |
| Proposal6.6.9. SPS will hold daily meetings with the designated Falcon Power |  |  |  |
| 6.6.10. SPS will perform dial indicator alignment checks.6.6.11. Any internal alignment shall be performed on a Time and Materials basis. 6.6.12. Two (2) copies of the final outage report will be provided by SPS. These will be supplied on Compact Disks (CD) unless otherwise requested. |  | personnel. |  |
| $45,5008.Extra Work and Delays$329,5007.8.Steam Turbine (minor), as described inSection 5. SPS will provide all Technical$135,3007.7.Major Inspection, as described in Section 4.SPS will provide all Technical Direction,$69,9007.6.Hot Gas Path Inspection, as described inSection 3. SPS will provide all Technical7.5.Combustion Inspection, as described inSection 2. SPS will provide all Technical7. Direction, Supervision, Craft Labor and Tooling required for one turnkey Minor Inspection of one (1) Steam Turbine. Supervision, Craft Labor and Tooling required for one turnkey Major Inspection of one (1) MS7001EA heavy-duty gas turbine. Direction, Supervision, Craft Labor and Tooling required for one turnkey Hot Gas Path Inspection of one (1) MS7001EA heavy-duty gas turbine. Direction, Supervision, Craft Labor and Tooling required for one turnkey Combustion Inspection of one (1) MS7001EA heavy-duty gas turbine. |  |  |  |
| Price | Any extra work performed by SPS that is not included in the scope of this proposal, as outlined in Sections 2-5, or delays not attributable to SPS, shall be billed to Falcon Power at SPS Standard Domestic Rates (see attachment). Extra work performed by SPS subcontractors shall be billed at cost plus 15%. Living expenses, accrued as a result of |  |  |
| Sermatech Power Solutions |  |  | Proposal to Falcon Power |
| Proposal Number 2002.47.28.4208 |  |  |  |

Page 11 of 19

| SERMATECH® |  |
| --- | --- |
| extra work or delays, shall be billed to Falcon Power at cost plus 10% in addition toProposal hourly rates. No extra work shall be performed without prior written approval from Falcon Power. |  |
| 9. Payment Terms |  |
| Payment terms shall be negotiated upon award of contract. Payment terms shall be due upon receipt of invoice, payable to Sermatech Power Solutions. |  |
| 10. Warranty |  |
| Items in this proposal are warranted for a period of one (1) year from the date of installation or eighteen (18) months from the date of shipment, whichever comes first. Full guarantee is outlined in the SPS Standard Terms and Conditions (see attachment). |  |
| 11. Taxes |  |
| Stated prices do not include any taxes. If applicable, please include your tax exemption certificate along with your Purchase Order or signed Authorization to Commence Work form (see attached). |  |
| 12. Terms and Conditions |  |
| Unless otherwise stated, SPS Standard Terms and Conditions shall apply. |  |
| 13. Validity |  |
| This proposal shall be valid for acceptance for 60 days from the issue date on Page 1. |  |
| Sermatech Power Solutions | Proposal to Falcon Power |
| Proposal Number 2002.47.28.4208 | Page 12 of 19 |

| A.Classification Straight TimeSermatech Power Solutions Engineering Services 2002 Domestic Rate Schedule |  |  |  |  |
| --- | --- | --- | --- | --- |
| B. C. D. E. F. | 1. 2. 3. 4. 5. 6. 7. | Technical Director Controls Engineer Project Manager Senior Consultant Controls Technician Design Engineering Office Field After Hours Emergency Service | $ 145.00 $ 160.00 $ 165.00 $ 195.00 $ 115.00 $ 125.00 $ 140.00 $ 175.00 | / Hour / Hour / Hour / Hour / Hour / Hour / Hour / Hour |
|  | Overtime rates shall be billed at one and one-half times the applicable straight time rate for the particular classification. |  |  |  |
|  | Definitions |  |  |  |
|  | 1. 2. 3. 4. 5. | Straight time shall be considered to be eight (8) hours per day, Monday through Friday. Time in excess of eight hours shall be billed as overtime. Rates are shown as hourly and shall apply to day or night shifts. Minimum workday shall be four (4) hours, plus travel time. For work in excess of four (4) hours, a full workday shall be charged. Overtime rates shall apply for all work performed on Saturday, Sunday and U.S. Holidays. Emergency Service shall be any contact by a client, after normal work hours or weekends, requiring technical assistance over the phone or on site for troubleshooting or a forced outage. |  |  |
| Expenses and Travel | 1. 2. | Travel time for all personnel shall be charged at 75% of the applicable straight time per hour rate. Lodging, air and ground transportation, cost based per diem ($40 per day) and miscellaneous expenses shall be charged at cost plus 10%. |  |  |
| Outside Purchases | Requested materials and subcontractors supplied by SPS shall be billed at cost plus 15%. |  |  |  |
|  | Terms and Conditions |  |  |  |
|  | 1. 2. 3. | The rates contained herein are effective April 1, 2001 and shall remain in effect until further notice. All work performed shall be subject to SPS Standard Terms and Conditions attached. This proposal is intended for the sole use of the party named herein and may not be reproduced in whole or in part. |  |  |
|  | Payment Terms Payment terms shall be due upon receipt of invoice, payable to Sermatech Power Solutions. |  |  |  |
| Proposal to Falcon PowerSermatech Power Solutions |  |  |  |  |
| Page 13 of 19Proposal Number 2002.47.28.4208 |  |  |  |  |

|  |  | Sermatech Power Solutions Classifications |
| --- | --- | --- |
|  | 1. 2. 3. 4. 5. | Technical Director. A Mechanical Engineer or equivalent providing onsite advice and recommendations during the inspection and repairs of Power Generation apparatus or associated equipment. The Technical Director will not provide supervision or management of Customer's employees, agents or other Contractors. Controls Engineer. The Controls Engineer provides onsite control system technical support (calibration, modification, startup and commissioning) or telephone advice and recommendations for turbine control equipment. The Controls Engineer will not provide supervision or management of Customer's employees, agents or other Contractors. Project Manager. An onsite engineer dedicated as the Customer Representative who will perform all logistical functions associated with a turnkey project as well as act as the technical liaison between the Customer and the Vendors. Senior Consultant. An engineer providing specialized expertise (Combustion Specialist, Vibration Specialist, Excitation Specialist and Generator Specialist), testing and / or evaluation of turbine equipment and systems. Work may be performed onsite or through telephone consultation. Controls Technician. The Controls Technician provides calibration of on base turbine devices and may assist Controls Engineer in calibration, modification, installation, startup and commissioning of turbine control equipment. |
|  | 6. Design Engineering. An Engineer providing onsite or in-house apparatus design services. |  |

Sermatech Power Solutions Proposal Number 2002.47.28.4208

Proposal to Falcon Power Page 15 of 19

| A.Classification Straight TimeOvertime |  |  |  | Sermatech Power Solutions Craft Labor 2002 Domestic Rate Schedule |
| --- | --- | --- | --- | --- |
|  | 1. | Millwright Supervisor | $ 49.00 / Hour | $ 71.00 / Hour |
| Millwright$ 35.00 / Hour$ 50.00 / Hour |  |  |  |  |
| B.2. C. D. E. | Definitions |  |  |  |
|  | 1. Straight time shall be considered to be eight (8) hours per day, Monday through Friday. 2. Overtime shall be considered any hours worked over eight (8) and all hours worked Saturday, Sunday and U.S. Holidays. 3. Rates are shown as hourly and shall apply to day or night shifts. |  |  |  |
|  | Expenses and Travel |  |  |  |
|  | 1. Mobilization / Demobilization for all personnel shall be charged at the straight time hourly rate, roundtrip. 2. Public Transportation shall be charged at cost plus 20%. 3. Per Diem (Food and Lodging) shall be billed at $ 75 per day per man. 4. Air travel if required shall be billed at cost plus 10%. |  |  |  |
|  | Outside Purchases |  |  |  |
|  | Requested materials and subcontractors supplied by TTS shall be billed at cost plus 15%. |  |  |  |
|  | Tool Rental |  |  |  |
|  | • | Turbine Tools and Portable Container shall be billed at $ 250 per day for Combustion |  |  |
| Inspection or Hot Gas Path Inspection. Turbine Tools and Portable Container shall be billed at $ 500 per day for Major |  |  |  |  |
| Inspection.• |  |  |  |  |
| F. Vehicles |  |  |  |  |
| G. Payment Terms1. Onsite Vehicles shall be billed at $ 81 per day. 2. Mileage for Company Vehicles shall be billed roundtrip from the base office at $ 0.81 per mile. |  |  |  |  |
| Payment terms shall be due upon receipt of invoice, payable to Sermatech Power |  |  |  |  |
| Solutions. |  |  |  |  |

| SERMATECH POWER SOLUTIONS STANDARD TERMS AND CONDITIONS |  |
| --- | --- |
| 1. Scope | Permission, Operating License, or any other |
| Technical Direction is consulting with and advising |  |
| others in the performance of their jobs regarding thegovernmental authorization, even though any such | authorization may be applied for by Company. |
| technical interpretation of drawing and equipment condition. Project Management can include planning, |  |
| scheduling and reporting on the conduct and progressCompany shall not be liable in any authorization is | delayed, denied, revoked, restricted or not renewed |
| of the job. Neither work scope will include direct | and Purchaser shall not be relieved thereby of its |
| supervision or responsibility for the acts and | obligations to pay Company for its work. |
| omissions of others unless otherwise specified herein. |  |
| 2. Payment TermsAll sales hereunder shall at all times be subject to the |  |
| Unless specified otherwise in this contract, paymentexport control laws and regulations of the US | Government and any amendments thereof. Purchaser |
| terms are 30 day net from the issue date of the invoice. | agrees that it shall not make any disposition, by way |
| For accounts 30 days past due, an annual rate of 18% | of transshipment, re-export, diversion or otherwise, |
| interest charge will be levied and billed on a monthly | except as said laws and regulations may expressly |
| basis. |  |
| 3. Title and Risk of Losspermit, of US origin goods purchased from Company, |  |
| The title and right of possession of equipment and/orother than in and to the ultimate country of destination specified on Purchaser's order and/or declared as the | country of ultimate destination on Company's |
| materials shall pass to the Customer once the | invoices. |
| equipment and/or materials have been shipped to by the Company and for which payment has been |  |
| received. Risk of loss shall pass to Purchaser F.O.B.6. Warranty | Sermatech Power Solutions (Company) warrants that |
| Point of Shipment. |  |
| 4. Taxes and Dutiesfield services will be performed in a competent |  |
| Company's prices do not include sales, use, excise,manner. If the purchaser notifies Company in writing of dissatisfaction, Company will replace the assigned | specialist or manager in a timely manner. In the event |
| value added or similar taxes. Consequently, in | it is determined that the services were improperly |
| addition to the price specified herein, the amount of | performed, Company will re-perform that portion of |
| any present or future sales, use, excise, value added or | services at no charge. |
| other tax applicable to the sale or use of the equipment hereunder shall be paid by Purchaser, or in lieu |  |
| thereofPurchaser shall provide Company with a taxCompany warrants to Purchaser that equipment to be | delivered and work to be performed will be free from |
| exemption certificate acceptable to the taxing | defects in material or workmanship. If the equipment |
| authorities. |  |
| Any taxes (including income, stamp and turnoverdelivered hereunder or the work carried out does not |  |
| taxes), duties, fees, charges or assessments of anymeet the above warranties, Purchaser shall promptly notify Company and make the equipment available | promptly for correction. Company shall thereupon |
| nature levied by any governmental authority other | correct any nonconformance or defect in materials or |
| than of the U.S. in connection with this transaction, | workmanship by, at its option, either repairing any |
| whether levied against Purchaser, against Company or | defective parts of the equipment, or by making |
| its employees, or against any of Company's | available at Company's plant necessary repaired or |
| subcontractors or their employees, or otherwise, at any | replacement parts. Where a failure cannot be |
| tier, shall be for Purchaser's account and shall be paid | corrected by Company's reasonable efforts, the parties |
| directly by Purchaser to the governmental authority | will negotiate an equitable agreement. |
| concerned. If Company is required by law or otherwise to pay any such levy and/or fines, penalties, |  |
| or assessments in the first insurance or as a result ofCompany does not warrant the equipment or work | against normal wear and tear due to operation or |
| Purchaser's failure to comply with any applicable laws | environment. Factors such as excessive operation at |
| or regulations governing the payment of such levies by | peak capacity, frequent starting, type of fuel or |
| Purchaser, the amount of any payments so made by | detrimental air inlet conditions can create the need for |
| Company shall be reimbursed by Purchaser to | repair or replacement as part of normal wear and tear |
| Company upon submission of Company's invoices. |  |
| All rights to drawback of customs duties for theduring the warranty period. Further, Company does | not warrant any equipment of others design where such equipment is not normally supplied by Company. |
| equipment (or material therein) belong to and shall | The foregoing warranties (except as to title) for each |
| remain in Company. Purchaser agrees to cooperate | unit shall apply for a period of twelve (12) months |
| with Company and to furnish such documents to | from the date of shipment of the equipment or from |
| Company as may be necessary to obtain drawback. | the date of completion of the works. In no event shall |
| 5. Governmental Authorizations |  |
| Purchaser shall be responsible for the timely obtainingthe warranty for equipment extend more than eighteen | (18) months from the date of shipment by Company. |
| of any required authorization, such as an Export | On expiration of the warranty period, all such liability |
| License, Import License, Exchange Permit or Planning | shall terminate. |

| The foregoing warranties as exclusive and in lieu of all other warranties, whether written, oral, implied or statutory (except as to title). NO IMPLIED STATUTORY WARRANTY OR MERCHANTABILITY OR FITNESS FOR |  |  |
| --- | --- | --- |
| PARTICULAR PURPOSE SHALL APPLY.INCIDENTAL, PUNITIVE OR CONSEQUENTIAL DAMAGES, WHETHER FORESEEABLE OR NOT, OCCASIONED BY COMPANY'S FAILURE TO PERFORM HEREUNDER, DELAY IN ITS PERFORMANCE, FAILURE OF THE PURCHASER |  | TO PERFORM OR ANY OTHER CAUSE |
| 7. Force Majeure |  | WHATSOEVER. COMPANY MAKES NO |
|  |  | WARRANTY, EXPRESS OR IMPLIED, TO ANY |
| No failure or omission to carry out or observe any of |  |  |
| the terms, provisions or conditions of this Contract |  | OTHER PERSON OR ENTITY CONCERNING THE |
| shall give rise to any claim by Purchaser against the |  | SERVICES PERFORMED HEREUNDER, AND |
| Company or be deemed to be breach of this Contract if |  | PURCHASER SHALL DEFEND AND INDEMNIFY |
| the same shall be caused by or arise out of: |  | COMPANY FROM ANY CLAIMS MADE UNDER |
| 8.ANY WARRANTY OR REPRESENTATION BY PURCHASER TO ANY THIRD PARTY. This Limitation of Liability prevails over any conflicting provisions of this contract. (a) Liability and Indemnity Company shall not be liable for injuries suffered by Purchaser, its employees, agents, representatives or assigns incurred while performing work, delivering equipment, material or supplies, or performing or carrying out any other work or services in connection with this contract. Purchaser shall hold Company harmless from any and all claims, causes or action, injuries or damages incurred by or to its employees, agents, representatives or other individuals not employees of the Company arising from the performance of this contract, unless the claims, causes or actions injuries or damages are caused by the sole negligence of, or gross misconduct of Company, its agents, representatives or assigns. 9. Price Adjustments In case a change in the contract specification results in a change in price, all installments shall be adjusted accordingly. However, if the change results in a decrease in price, then the payments previously made shall be retained by Company and applied to subsequent payments as they become due. In the event of a cancellation or termination of this contract, if the amount theretofore paid exceed the cancellation charges, the excess shall be refunded to the Purchaser. If deliveries are delayed by Purchaser and Company agrees to a revised delivery schedule, due dates of payments shall be based on the revised delivery schedule. Payments already made shall be retained by | (a) any war, declared or not or hostilities, or of belligerence, blockades, revolution, insurrection, riot, public disorder, expropriation, requisition, confiscation or nationalization, export or import restrictions by any governmental authorities, closing of harbors, docks, canals, or other assistance's to or adjuncts of the shipping or navigation's of or within any place, rationing or allocation, whether imposed by law, decree or regulation by, or by compliance of industry at the insistence of any governmental authority, or fire, unusual flood, earthquake, storm, lightning, tide (other than normal tides), tidal wave, perils of the sea, accidents of navigation or breakdown or injury of vessels, accidents to harbors, docks, canals, or other assistance's to or adjuncts of the shipping or navigation, epidemic, quarantine, strikes or combination or workmen, lookouts or other labor disturbances, or any other event, matter or thing, wherever occurring, which shall not be within the reasonable control of Company. (b) In the event of such a delay, the dates for delivery and completion shall be extended for a period equal to the time lost by reason of delay. (c) If the company is delayed by the actions or failure to act of the Purchaser, its subcontractors or assigns, then the dates of shipment and completion shall be extended by a period equal to the time lost by reason of delay. Furthermore, the Purchaser shall reimburse the Company for all extra costs incurred by Company as a result of that delay. Limitation of Liability |  |
|  |  | Company and applied to payments as they become |
| ANY AND ALL EXPRESS AND IMPLIED |  |  |
| WARRANTIES ARE EXPRESSLY EXCLUDED |  | due. Suspension If either party to this contract decides |
| AND DISCLAIMED EXCEPT TO THE EXTENT |  | to suspend work under this contract, that party shall |
| SPECIFICALLY AND EXPRESSLY PROVIDED |  | give the other one week advanced, written notice of |
| FOR IN THIS CONTRACT. IT IS EXPRESSLY |  | the suspension date. Purchaser will be responsible for |
| AGREED THAT COMPANY’S SOLE |  | any and all costs incurred prior to the suspension date. |
| OBLIGATIONS AND LIABILITIES RESULTING |  | 10. Cancellation |
| FROM A BREACH OF THIS CONTRACT, AND |  | Shipping dates are approximate and are based upon |
| PURCHASER'S EXCLUSIVE REMEDIES FOR |  | prompt receipt of the equipment and/or materials and |
| ANY CAUSE WHATSOEVER (INCLUDING, |  | all necessary information. The Purchaser may cancel |
| WITHOUT LIMITATION, LIABILITY ARISING |  | this contract only upon written notice and upon |
| FROM NEGLIGENCE) ARISING OUT OF OR |  | payment to the Company of reasonable and proper |
| RELATING TO THIS CONTRACT AND/OR THE |  | cancellation charges. |
| TRANSACTIONS CONTEMPLATED HEREBY, ARE LIMITED TO THOSE SET FORTH HEREIN, |  |  |
| AND ALL OTHER REMEDIES OF ANY KIND11. Nonfulfillment |  | The due fulfillment by Purchaser of all the conditions |
| ARE EXPRESSLY EXCLUDED. IN NO EVENT |  | set forth above, including the issuance of acceptable, |
| SHALL COMPANY BE LIABLE FOR ANY |  | irrevocable letters of credit and the making of |

| payments thereunder as prescribed within the times |  |
| --- | --- |
| specified hereunder are the essence of this contractif sent by facsimile, or upon the expiration of the third |  |
| and the failure to fulfill any such conditions shallbusiness day after being deposited in the United States | mails, postage prepaid, certified or registered, |
| constitute a breach of contract by Purchaser. |  |
| Should Purchaser fail to fulfill any of the conditions ofaddressed to the other party. this clause, Company may suspend work or | 17. Severability |
| performance under the contract and any cost incurred | Nothing contained in this Contract shall be construed |
| by Company is accordance with such suspension shall | so as to require the commission of any act contrary to |
| be added to the contract price. In the event that | any law, and wherever there is any conflict between |
| Purchaser does not correct such failure in the manner | any provision of this Contract and any law, such law |
| and time satisfactory to Company, then Company | shall prevail; provided, however, that in such event the |
| may, at its option, terminate the contract with respect | provisions of this Contract so affected shall be |
| to the portion of equipment not delivered and work not | curtailed and limited only to the extent necessary to |
| yet performed and Company's termination charges | permit compliance with the minimum legal |
| shall be paid by Purchaser to Company upon | requirement, and no other provisions of this Contract |
| presentation by Company of its invoices under the | shall be affected thereby, and all such other provisions |
| letter of credit to the extent funds are available. |  |
| Performance of Company's obligations shall beshall continue in full force and effect. |  |
| extended for a period equaling the period of18. Successors | This Contract shall be binding on and shall inure to the |
| Purchaser's non-fulfillment of any portion of the | benefit of any and all successors of the parties. |
| payment terms, whether or not Company suspends performance. |  |
| 12. Straight Time/Overtime19. Rules of Construction and Headings |  |
| The standard work week (straight time) shall consistAny ambiguities shall be resolved without reference to which party may have drafted this Contract. The | description headings of the several sections and |
| of five (5) eight (8) hour days, exclusive of weekends, | paragraphs of this Contract are inserted for |
| USA national holidays or local holidays, as agreed. | convenience only and do not constitute a part of this |
| The standard work hours and days are to be agreed | Contract. |
| upon among the parties of this contract. Time worked over and above the agreed upon work week shall be |  |
| charged at the agreed overtime rate.20. Entire Agreement and Amendment |  |
| 13. Travel and Living ExpensesThis Contract constitutes the entire agreement between |  |
| Company shall bill Purchaser all travel and living andthe parties, and supersedes all previous understandings, commitments or representations | concerning the subject matter. This Contract may not |
| other related expenses at cost plus ten (10) percent, |  |
| unless included in the price. Accommodations shallbe amended or modified in any way, and none of its | provisions may be waived, except by a writing signed |
| be arranged by the Company. If they are arranged by | by an authorized officer of the party against whom the |
| others, they will be subject to Company approval. | amendment, modification or waiver is sought to be |
| 14. Technical Reports | enforced. The parties each acknowledge that the other |
| Company shall submit a full report on work performed | party has not made any representations other than |
| to Purchaser. |  |
| 15. Non-Waiver of Breachthose which are contained herein. Either party hereto may specifically waive any breach of this Contract by the other party, provided that no such waiver shall be binding or effective unless in writing and no such waiver shall constitute a continuing waiver of similar or other breaches. A waiving party, at any time and upon notice given in writing to the breaching party, may direct future compliance with the waived term or terms of this Contract, in which event the breaching party shall comply as directed from such time forward. 16. Notices Each party shall provide the other party with a telephone number to be used for routine and emergency operational notifications. For routine notifications, any such telephonic notification shall be followed up with written notification as outlined below. All notices and other communications from either party to the other hereunder shall be in writing and shall be deemed received when actually received if personally delivered, upon acknowledgment of receipt |  |

By:

By:

|  |  | AUTHORIZATION TO COMMENCE WORK Proposal Number: 2002.47.28.4208 |  |
| --- | --- | --- | --- |
| THIS AGREEMENT at P.O. Box 2700, Power Solutions Technology Parkway, WHEREAS, WHEREAS, undertake WHEREAS, |  | made and entered into by and between Falcon Power with general offices Big Spring, TX 79721 (hereinafter referred to as "Company") and Sermatech (Turbine Technology Service division) with general offices at 3050 Suite 100, Orlando, Florida 32826 (hereinafter referred to as "SPS") WITNESSETH THAT: Company has need for certain services to be performed by SPS; and Company desires to engage SPS to perform the services and SPS desires to such performance; Company intends to issue to SPS a purchase order encompassing all the |  |
| terms and conditions of the engagement, but, desires SPS to undertake such performance prior to issuance of the purchase order. |  |  |  |
| NOW, THEREFORE, monies to be paid WHICH INCLUDE SURRENDER THE PARTIES, OWN NEGLIGENCE, |  | in consideration of the respective undertakings of the parties, and the hereunder, and of the terms, conditions, and provisions hereinafter set forth, TERMS, CONDITIONS, AND PROVISIONS THAT OPERATE TO OR OTHERWISE MODIFY THE LEGAL RIGHTS AND OBLIGATIONS OF INCLUDING RELIEVING A PARTY FOR THE CONSEQUENCES OF ITS the parties hereto have agreed and do hereby agree as follows: |  |
|  | 1. | Prior to issuance of the purchase order or the execution of the contract for the |  |
|  | 2. | services to be provided by SPS, Company authorizes SPS to commence the contemplated work. Company shall be liable to SPS for the amounts due with respect to SPS' work pursuant to this authorization. Prior to the acceptance of the terms of the purchase order or the execution of a |  |
|  | 3. | contract for the performance of the work by SPS, SPS’ standard terms and conditions for the providing of services shall apply. If Company does not issue a purchase order or the parties are unable to agree as |  |
| Sermatech |  | to the terms of the engagement and Company notifies SPS to stop work, Company shall pay SPS the amount due with respect to SPS' work pursuant to this authorization within thirty (30) days of receipt of an invoice for the same. |  |
|  | IN WITNESS WHEREOF, the parties hereto have executed this Agreement by their |  |  |
|  | authorized representatives as of the |  | day of , 2003. |
|  |  | Power Solutions (SPS) | Falcon Power |