Proposal FS05-0109

LG&E Energy

Gordonsville Power Station

Technical Proposal For

GE Frame 7EA

Combustion Inspection

805 Thompson Boulevard		1395 S. Marietta Pkwy SE Bldg 300-216

Sedalia, Missouri 65301		Marietta, Georgia 30067-2896

(660) 829-5100		(678) 594-0991

ProEnergy Services is an integrated service company. We provide a wide range of services to power plant owners ranging from temporary specialized personnel to execution of turnkey projects on turbine generators and balance of plant equipment. Our four business groups include Technical Services, Professional Services, Field Services, and Operations and Maintenance Services.

Contents

of

Proposal

- Introduction……………………………………………………………………….Page 3

- Strategy……………………………………………………………………………Page 3

- Proposal Summary……………………………………………………………….Page 4

- Typical Inspection Work Scope………………………………………………….Page 4

- Combustion Inspection Procedure……………………………………………....Page 4

- Assumptions……………………………………………………………………….Page 6

- Supplied By ProEnergy Services………………………………………………...Page 6

- Supplied By Others……………………………………………………………….Page 6

- Pricing……………………………………………………………………………..Page 7

- Terms & Conditions………………………………………………………………Page 8

1.0  Introduction

- ProEnergy Services (“ProEnergy”) is pleased to provide this proposal to LG&E Energy, (“LG&E”)Gordonsville Power Station for the supply of Craft Labor, Tools and Supervisory Services to execute a Planned Combustion Inspection.  This proposal includes a fixed price to perform a combustion inspection of a GE 7EA gas turbine. Also included in this proposal is extra work rates that will apply to any unplanned work or work scopes not defined.

- ProEnergy will supply sufficient resources to perform the inspection of the gas turbine and any extra work incurred. ProEnergy can also provide specialty personnel and services to support maintenance on the gas turbine auxiliaries and the balance of plant equipment.

2.0  Strategy

The ProEnergy team that will perform the maintenance at the LG&E facilities will be knowledgeable and experienced in performing major maintenance on GE gas turbine generators. The ProEnergy team will consist of multiple non-union craftsmen and led by a seasoned foreman. The foreman will be responsible for the quality of work and the production of the craftsmen. The foreman will work with the ProEnergy technical advisors to plan the daily work tasks and ensure all the data is being taken properly to ensure the inspection is properly documented.

The ProEnergy team will be properly safety trained and briefed on the site specific requirements and procedures. The ProEnergy foreman has the authority and responsibility to uphold the safety procedures and regulations. ProEnergy also incorporates drug testing into our safety program.

ProEnergy expect to be an active participant in outage planning to ensure that they are aware of the complete work scope and timing of the outage. This will help to ensure sufficient manpower is planned to support any non-typical work scopes or schedule constraints.

Extra work occurs on most maintenance projects. However, after the project is complete there is usually confusion and disagreement to which activities were considered extra work. ProEnergy requests that any extra work that is performed during an outage be signed off by a LG&E representative prior to the commencement of the work. Also any time sheets associated with any extra work should be signed off each day by a LG&E Representative. Hopefully these measures will eliminate any related problems.

3.0  Proposal Summary

PROENERGY SERVICES has attempted to provide a comprehensive description of the technical direction or consultation available from PROENERGY SERVICES to execute an inspection.

Inspection parameters may vary depending on fuel, duty cycle, and the maintenance philosophy of the owner. Where information is not provided, or where the requirements are unclear, PROENERGY SERVICES has attempted to make reasonable assumptions based on its experience of similar inspections. In the event that information is missing, or unclear, PROENERGY SERVICES is willing to work with the owner to develop a site specific scope of work to meet the Owners requirements.

4.0  Typical Inspection Work scope

General:

Inspection Work-Scope Description:

The scope of work includes tools, direct supervision and craft labor for this inspection process.

The Inspection Team shall prepare an inspection plan which will include but not be limited to the following:

                - Inspection Schedule from mobilization through turnover to Owner.

                - Manpower Resource Plan.

                - Document Control Plan including, but not limited to operating data, inspection forms and data,  and maintenance performed

5.0  Combustion Inspection Procedures

A combustion inspection scope of work will focus on the combustion hardware. A typical combustion inspection will remove all the combustion hardware including fuel nozzles, combustion liners, cross fire tubes and transition pieces. A visual inspection of the first stage nozzle partitions is performed to determine the condition of the component.

Any incidental hardware such as unit piping, lagging, or enclosure will be removed as required to perform the inspection

The ProEnergy Services typical scope: (Gas Only)

Disassemble:

                - Removal of Flame Detectors

                - Removal of Spark Plugs.

                - Removal of Gas Fuel and Purge Flex Hoses

                - Removal of Fuel Nozzle Assembly

                - Removal of cross fire tubes

                - Removal of Cap and liner Assembly

                - Removal of Flow Sleeves

                - Removal of Outer Crossfire Tubes

                - Removal of Outer Combustion Casings

                - Removal of Transition Pieces

Inspect:

                - Fuel Nozzle tips

                - Spark Plug

                - Flame Detectors

                - Combustion Cap and Liner

                - Crossfire Tube and Retainer

                - Combustion Chamber Flow Sleeve

                - Forward Combustion casings

                - Outer Casing

                - Transition Pieces

                - First Stage Nozzle

Reinstall:

                - Transition Pieces

                - Combustion Casings and outer Crossfire Tubes

                - Flow Sleeves and Combustion Liner Assemblies

                - Spark Plugs

                - Fuel Nozzle Assembly

                - Gas Fuel Lines

                - Flame Detectors

                - Piping

Start Up (For all Inspections):

                - Minimal start-up support

6.0  Assumptions

The following assumptions have been made in the preparation of this proposal:

                - Standard services include disassembly, clean, inspect, and reassemble with new/refurbished components.

                - Repair services not included in this scope.

                - Turbine inspection only, generator and gear box work not included.

                - OEM provided special tools are available for use.

                - Lay-down area in close proximity to inspection site is available.

                - Technical Direction will be provided by ProEnergy Services.

                - Units are gas only fuel.

                - Start-up support includes two craftsmen and a supervisor for one shift.

7.0  Supplied by PROENERGY SERVICES

The following equipment, material and services are supplied by PROENERGY SERVICES:

                - Technical Direction and Project Management

                - All craft labor, supervision, and tools.

                - Personal protection equipment (PROENERGY SERVICES personnel)

                - Lap-top computers for PROENERGY SERVICES personnel

                - Manpower loading and outage schedule

                - Mobilization costs of PROENERGY SERVICES personnel

                - Per diem expenses of PROENERGY SERVICES personnel

                - Local travel and lodgings of PROENERGY SERVICES personnel

                - Portable cranes to support inspection

                - General Liability and Workman’s compensation Insurance

                - Workmanship warranty

8.0  Supplied by Others

The following equipment, material and services are not supplied by PROENERGY SERVICES:

                - NDT services

                - Instrument calibration services

                - Electricians to disconnect electrical devices

                - Component repair

                - Site Facilities for PROENERGY SERVICES

                - Site offices

                - Telephone for business use

                - Use of printers, copiers and other business equipment

                - Temporary material storage

                - Service manuals

                - Individual equipment and system operating manuals and instructions

                - Site Security

                - Temporary power and water

                - Lubricating oil, greases, glycol and other chemical / fluids

                - Hazardous and non hazardous waste disposal

                - Compressed air and electrical power at unit.

9.0  Pricing

Fixed Price

Table one below outlines the fixed price amount for a Combustion Inspection for a 7EA gas turbine generator. This table also includes the expected duration for these inspections.

Table two in section 5.0 outlines the payment schedule for these fixed price amounts.

Table 1:  Fixed Price Table

| Inspection | Fixed Price | Expected Duration |
| --- | --- | --- |
| Combustion Inspections | $63,775.00 USD | 5 days |

Note 1) Expected duration for planned workscope does not include any extra work.

Time and Material (extra work)

Any re-work required due to an error or mistake made by parties other than ProEnergy will be treated as extra work. Also, any delays that impact the critical path activities (extend outage) that are caused by parties other than ProEnergy will be treated as extra work. These two items will be implemented with tolerance and reason.

Table 2:  Time and Material Table

| Position | Hourly Rate (3) |
| --- | --- |
| Foreman & Specialty Craft | $54.00 |
| Craftsmen | $48.00 |

Note 1) Hourly rate for all hours worked.

Note 2) Craftsmen include Millwrights, Electricians, Pipe Fitters, Electricians and Carpenters.

Note 3) Specialty craftsmen include I&E Technicians, Tube Welders and Valve Technicians.

Note 4) Combustion Dynamics Tuning will be performed on Time & Material. (see attached rates)

Note 5) Combustion Inspection price above does not include cranes. Cranes to be supplied by customer.

10.0 Terms & Conditions

The fixed price amounts will be invoiced upon completion of the inspection. These invoices will be due within ten (10) calendar days of receipt.

All time and material charges for extra work will be invoiced weekly and will be due within ten (10) calendar days of receipt. The invoices for extra work will include authorization for the work and signed timesheets that reflect the billing on the invoice.

This proposal shall be subject to the terms and conditions of the Master Service Contract 
No. 2005-0109, dated January 28, 2005 between ProEnergy Services and LG&E and shall be deemed incorporated in this proposal by this reference.

Other Items

Any scheduled outage that is cancelled or delayed with less than 48 hours notice, LG&E will be invoiced $5,000.00 to cover overhead costs to reschedule manpower. Any scheduled outage that is cancelled or delayed with less than 12 hours notice, LG&E will be invoiced $10,000.00 to cover overhead costs plus any mobilization expenses incurred. These invoices will be due within ten (10) calendar days of receipt.

ProEnergy will request compensation for any significant delay in work activities that is not caused by ProEnergy. ProEnergy will be reasonable with such a request and expect that LG&E will not unreasonably with hold.

| ProEnergy Services By: ________________________________________ Printed Name: ________________________________________ Title: ________________________________________ | LG&E – Gordonsville Power Stations By: ________________________________________ Printed Name: ________________________________________ Title: ________________________________________ |
| --- | --- |