## Cost Sheet
Projects Name | Project Number | Work Schedule | Shifts per day
Major Inspection | 0 | 2005-07-12 | 2
Mobilization / Demobilization
Travel In / Out | Number | Cost per |  | Total Cost
Craftsmen | 18
Mobilization | 18 | 500 |  | 9000
Time |  | 0 |  | 0
Per Diem |  | 65 |  | 0
Local Transport |  | 0 |  | 0
Job Set Up Hours | 32 | 902.176 |  | 902.176
9902.176
Foreman | 2
Mobilization | 2 | 500 |  | 1000
Time |  | 0 |  | 0
Per Diem |  | 65 |  | 0
Local Transport |  | 0 |  | 0
Job Set Up | 16 | 512.6 |  | 512.6
1512.6
TA's/Supervision/Gen. Spe | 2
Air fare | 2 | 750 |  | 1500
Time | 36 | 3960 |  | 3960
Per Diem | 2 | 100 |  | 200
Local Transport | 2 | 600 |  | 1200
6860
Project Manager | 1
Air fare | 1 | 750 |  | 750
Time | 16 | 1760 |  | 1760
Per Diem | 2 | 100 |  | 200
Local Transport | 4 | 500 |  | 2000
4710
Inspection | [5 empty] | Direct Labor |  | Outage Duration Direct Labor | Outage Duration Indirect Labor
| Number | ST. | O.T | Per Diem Days | Per Diem | Straight time Days | Hours Per Day | Number of Work Days For Per Diem | Number of Work Days Per Diem
Craftsmen | 18 | 2160 | 2160 | 20 | 23400 | 15 | 8 | 20 | 21
Straight time Days with OT
Foreman | 2 | 240 | 240 | 20 | 2600 | 15 | 4
Overtime Days
TA's/Supervision | 2 | 240 | 240 | 21 | 4200 | 5 | 12
Project Manager | 1 | 120 | 120 | 0 | 0
Indirect Labor
Generator Specialist | 0 | 0 | 0 |  |  | Straight time Days | Hours Per Day
[6 empty] | 15 | 8
Rates: | ST | OT |  |  |  | Straight time Days with OT
Craftsmen | 28.193 | 42.2895 |  |  |  | 15 | 4
Foreman | 32.0375 | 48.0562 |  |  |  | Overtime Days
T/A's/Supervision | 110 | 110 |  |  |  | 5 | 12
Project Manager | 110 | 110
Project Summary
| ST.Hours | ST Price | OT Hours | OT Price | Per Diem | Travel in / Out
Craftsmen | 2160 | 60896.88 | 2160 | 91345.32 | 23400 | 9902.176
Foreman | 240 | 7689 | 240 | 11533.5 | 2600 | 1512.6
TA's/Supervision | 240 | 26400 | 240 | 26400 | 4200 | 6860
Project Manager | 120 | 13200 | 120 | 13200 | 0 | 4710
Totals | 2760 | 108185.88 | 2760 | 142478.82 | 30200 | 22984.776
Total Direct Hours | 4800
Total Indirect Hours | 480 | 516
Total Direcr Labor Cost | 208879.476
Total Indirect Labor Cost | 63860
Subtotal | 303849.476
Other Cost
Non Part Consumables | 1000
Tools / Shipping | 4000
Report | 2500
Project Coordination
Office Trail/Phone
Safety
Air Compressor
Subtotal | 7500
Grand Total | 311349.476
Warranty cost (3%) | 9340.4843
Total Cost on Labor | 320689.9603
Sub Contracts
Hi-Torque | 10000
Total Cost on Sub Contracts | 10000
Mark Up of Sub's 5% | 500
Sales Price on Subs | 10500
Commission on Labor
Direct Labor 3% | 6266.3843
InDirect labor 4% | 2554.4
Total Commission | 8820.7843

## Sales Sheet
Pricing Sheet
Major Inspection
|  | Margin in $ | Margin
Direct Labor Cost | 247489.476
Margin (%) | 20%
Direct Labor Sales Price | 309361.845 | 61872.369
Indirect Labor Sales Price | 63860 | 12900
Sub Contracts | 10500 | 500
Commission on Labor | 8820.7843
Sales Price | 392542.6293 | 75272.369 | 19.18%

## Labor Rates
Project: | Major Inspection | Project #: |  | Schedule: | 2005-07-12 | # of Shifts | 2
Proposal Basis (assumptions)
Note:
TRADE OR CLASSIFICATION | BASE RATE – STRAIGHT TIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE S/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 5% | 2% | 10% | 28.15% | 5% | 22% | 55.15%
Foreman | 25 | 1.9125 | 0.2 | 0.675 | 0 | 1.25 | 0.5 | 2.5 | 32.0375 | 1.6019 | 7.4007 | 41.04
Millwright | 22 | 1.683 | 0.176 | 0.594 | 0 | 1.1 | 0.44 | 2.2 | 28.193 | 1.4097 | 6.5126 | 36.1152
TA's | 110
Project Manager | 110
TRADE OR CLASSIFICATION | BASE RATE – OVERTIME | FICA | FUTA | SUTA | FRINGES | SMALL TOOLS / CONSUMABLES | INSURANCE |  | SUBTOTAL | OVERHEAD AND PROFIT |  | ALL-INCLUSIVE O/T RATE
[7 empty] | GL | W Comp |  | OH | Profit
|  | 7.65% | 0.8% | 2.7% | 0% | 5% | 2% | 10% | 28.15% | 0% | 22% | 50.15%
Foreman | 37.5 | 2.8687 | 0.3 | 1.0125 | 0 | 1.875 | 0.75 | 3.75 | 48.0562 | 0 | 10.5724 | 58.6286
Millwright | 33 | 2.5245 | 0.264 | 0.891 | 0 | 1.65 | 0.66 | 3.3 | 42.2895 | 0 | 9.3037 | 51.5932