|  |  |  |
| --- | --- | --- |
| EPC | Weekly Report **17 July 2010** | |
| Date: 17 July 2010 | Project: Sidor Site A, Puerto Ordaz Venezuela | |
| Written By: Patrick Melody | ProEnergy EPC Project Mgr  ProEnergy Site Manager | William Lugo  Patrick Melody |
|  |  |  |

**Table of Contents**

**1. Executive Summary**

**1.1 Safety and Regulatory Compliance**

**1.2 Personnel/Staffing**

**1.3 Weekly Accomplishments**

**1.4 Scheduling Conflicts**

**1.5 Site Manager Commentary and Amplifying Remarks**

**2. Engineering and Design**

**2.1 General Arrangement**

**2.2 Site/Civil/ Structural**

**2.3 Mechanical**

**2.4 Electrical**

**2.5 Instruments & Control**

**2.6 O&M Manuals**

**3. Procurement**

**3.1 Purchase Order Requests**

**3.2 Equipment & Material Quotations**

**3.3 Purchase Order**

**4. Contracts**

**4.1 EPC Contract**

**4.2 Construction Subcontracts**

**4.3 Proposal and Quotes**

**5. Construction**

**5.1 Schedule**

**5.2 Equipment Delivery Status (expediting report)**

**5.3 Civil**

**5.3.1 Site Preparation**

**5.3.2 Centerline Foundation**



**5.3.3 GSU Foundation**

**5.3.4 Auxiliary Foundations**

**5.4.1 Centerline Equipment Installation**

**5.4.2 Centerline Piping Installation**

**5.4.3 Auxiliary Piping Installation**

**5.4.4 Underground Piping Installation**

**5.4.5 Above Ground Piping Installation**

**5.4.6 Balance of Plant (BOP) Piping Installation**

**5.5 Electrical**

**5.5.1 Duct Bank Installation**

**5.5.2 Centerline Electrical Installation**

**5.5.3 Auxiliary Electrical Installation**

**5.5.4 Balance of Plant (BOP) Installation**

**5.6 QA/QC**

**5.6.1 Equipment Testing**

**5.6.2 Nonconformity Report**

**5.6.3 Drawing Revisions**

**5.6.4 CWI Reports**

**5.6.5 As-built Drawings**

**6 Start Up & Commissioning**

**6.1 Schedule**

**6.2 Equipment Status**

**6.3 Punch list**

**6.4 Equipment Checkout**

**6.5 Equipment Functional Test**

**6.6 Equipment Turnover**

**6.7 Performance Testing**

**6.8 Emission Testing**

**7 Mobilization**

**7.1 Schedule**

**7.2 Operating Procedure Development**

**7.3 Operation Staff Training**

**7.4 Spare Parts/Inventory Status**



**1. Executive Summary .**

This report provide an overview of the project activities for the week ending 7

* 1. **Safety & Regulatory Compliance** 
     + Develop Job Safety Analysis as required.
     + Inspection of motorized equipment prior to usage.
     + Inspection of subcontractor power tools.
     + Site orientation for tie in work in existing switchyard
  2. **Personnel/Staffing**

|  |  |  |  |
| --- | --- | --- | --- |
| Lugo, Bill | Project Director |  |  |
|  |  |  |  |
| Melody, Patrick | Site Manager | Daniels, Julio | Tool Room (Local) |
| Siros, James | Mech. Supt. | Izquierdo, Weiser | Mat'l. Handler |
| Bird, Jason | Tech. Advisor | Flores, Herman | Tool Room (Local) |
| Little, John | Material Manager | Newan, Miguel | Mat’l Handler |
| Frawely, Ted | Electrical |  |  |
| Blacke, Edward | Safety Manager | Leccia, Karina | Admin Assist |
|  |  | Rojas, Moises | Logistics |
|  |  | Zambrano, Natalia | Electrical Engineer |
|  |  | Alvarez, Josbett | Translator |
|  |  | Jansen Teodoro | Translator |
|  |  | Monasterios, O | Safety ( Local) |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

* 1. **Weekly Accomplishments** 
     + GT 100 Oily Water Tank Foundation Complete
     + GT 100 Oily Water Separator Foundation Complete
     + GT 100 Site Grading
     + GT 300 Complete Cable Tray Racks
     + GT 300 Set CO2 Skid
     + GT 300 Set Fogging Skid
     + GT 300 Exhaust Stack – Interior welding
     + GT 300 Excavate PEECC
     + GT 300 Install piping in the unit ongoing
     + GT 300 Excavate for water injection skid
     + GT 300 Backfill GT foundation to grade ongoing
     + Duct bank – West side of GT 300
     + BOP – Fabricating pipe to gas compressor
     + BOP – Demin Water Tank – Backfill tank in process
     + BOP – Raw Water Tank – Setting forms and rebar
     + BOP - Switch Yard Foundations Ongoing
     + BOP – Switch Yard Finish grading
     + BOP – Install fire line ongoing
     + BOP - Install process pipe ongoing



**1.4– Scheduling Conflicts**

* CPM schedule was issued 14 June 2010***.*** Impacts resulting from the lack of progress payments is being reviewed for inclusion.
  1. **– Site Managers Commentary and Amplifying Remarks**
* ***Civil Contractor has agreed to resume Saturday work for critical items. Site grading is adversely affected by heavy nightly rains***
* 7EA Dual fuel conversion is being evaluated to determine impact on critical path. ***Dual fuel conversion team is schedule to arrive on site 23 Jul 1.***
* The following components have been sent to Termozulia. Beckwith; Electro Industries volt/amp meter; coupling bolts; purge and vent valves for fuel gas module; and ignition transformer. Lead times are critical for replacement of these items. Control cards for 7EA are also required this week by Termozulia.
* SIDOR has indicated that there is an existing Demin Water Treatment plant on Site with the capacity to deliver 68 GPM. SIDOR wants to minimize the impact of the delay in tank construction due to their failure to remove the power lines. ***Off site fabrication of the water tanks is being discussed with the fabricator.***
* ***Heavy nightly rains and intermittent showers during the day are seriously impacting production.***
* ***DCS design is not complete. DCS has not been released for fabrication.***

**2 Engineering and Design**

**2.1 – General Arrangement-**

**2.2 – Site /Civil /Structural**

**2.3 – Mechanical**

**2.4 – Electrical**

* + - ***DCS Design is not complete.***
    - ***Cathodic protection design is not complete.***

**2.5 – Instrumentation**

* **Ongoing**

**2.6 – O&M Manuals –**

* **Ongoing**

**3 Procurement**

**3.1 – Purchase Order Requests**

**3.2– Equipment & Material Quotations**

**3.3 - Purchase Order –**

* Purchase Orders have been prepared for the following
  + Electrical Subcontractor – Duct bank cleaning / Ground grid
  + Misc. Metal fabrication
  + Pre Engineered Metal Building Erection
* Pending
  + Tank erection

**4 Contracts**

**4.1 – EPC Contract –**

**4.2 – Construction Subcontracts –**

**4.3 – Proposal & Quotes**

**5 Construction**

* **5.1 Schedule**
* CPM schedule was issued 14 June 2010.

**5.2 Equipment Delivery**

* **Boroscope arrived from Tacoa**

**5.3 Mechanical**

* GT 100 – GT Erection is complete
* GT 200 – GT Erection is complete. Awaiting arrival of turbine for installation.
* GT 300 – GT Erection is complete

**5.4 Electrical**

* Installation of Manholes and duct banks is ongoing.

**5.5 QA/QC**

* Inspections of concrete placements, excavation, welding, and backfill activities is ongoing.

**6 Startup & Commissioning**

* Pending.

**7 Startup Mobilization**



GT 200 Heavy Rain Overnight



GT 100



Process Pipe Trench