| EPC | Weekly Report 19 June 2010 |  |
| --- | --- | --- |
| Date: 19 June 2010 | Project: Sidor Site A, Puerto Ordaz Venezuela |  |
| Written By: Patrick Melody | ProEnergy EPC Project Mgr ProEnergy Site Manager | William Lugo Patrick Melody |

Table of Contents

1. Executive Summary

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary .

This report provide an overview of the project activities for the week ending 15 May 2010 for the engineering, procurement, and the construction activities on site.

  - Safety & Regulatory Compliance

    - Develop Job Safety Analysis as required.

    - Inspection of motorized equipment prior to usage.

    - Inspection of subcontractor power tools.

  - Personnel/Staffing

| Lugo, Bill | Project Director |  |  |
| --- | --- | --- | --- |
| Melody, Patrick | Site Manager | Daniels, Julio | Tool Room (Local) |
| Siros, James | Mech. Supt. | Izquierdo, Weiser | Mat'l. Handler |
| Bird, Jason | Tech. Advisor | Flores, Herman | Tool Room (Local) |
| Horn, Ryan | Tool Room Super. |  |  |
|  |  | Leccia, Karina | Admin Assist |
|  |  | Rojas, Moises | Logistics |
|  |  | Zambrano, Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |

  - Weekly Accomplishments

    - GT 100 Install expansion joint

    - GT 100 Install cable tray supports

    - GT 100 Install sprint skid & water injection skid

    - GT 200 Install cable tray supports

    - GT 200 Liquid fuel skid

    - GT 200 Install sprint skid & water injection skid

    - GT 300 Install piping inside the enclosure

    - GT 300 Prep exhaust transition duct

    - GT 300 Exhaust Stack – Interior welding

    - GT 300 – Install GSU transformer

    - GT 300 – Install grating & ladders at filter house

    - GT 300 – Liquid gas fuel module foundation complete

    - GT 300 – Install demister foundation complete

    - GT 300 – Install water wash foundation complete

    - Complete Duct bank – MH 1 to GT 300

    - Complete Duct bank – MH 8 to GT 200

    - Complete Duct bank – MH 9 to gas compressor

    - Utility Bldg. Install anchor bolts for PEB

    - Water Treatment Bldg – Install floor drain

    - POB - Install black start generator

    - BOP - Excavate storm drain on west side of GT300

    - BOP – Demin water tank mud mat

    - BOP – RO Tank foundation complete

    - BOP - Switch Yard foundations ongoing

    - BOP - Switch yard precast manholes complete

    - BOP – Install fire line

    - BOP -  Install process pipe

    - BOP – Oily water separator foundation in process

    - BOP – Fire line Hydro Test East side

1.4– Scheduling Conflicts

- CPM schedule was issued 14 June 2010.  Impacts resulting from lack of progress payments is being reviewed for inclusion

  - – Site Managers Commentary and Amplifying Remarks

- Civil Contractor has reduced manpower this week due to the payment issue. No Saturday work is planned after 12 June 10.  GT 300 duct bank 7 foundations, switch yard and water treatment building will be adversely affected.

- Power line which was restraining excavation of tank foundations was removed on 18 June 2010. Excavation to begin on Monday, 21 June 2010

- GT 300 GSU transformer was damaged in shipment. Repair will be made in field by heat straightening damaged tube.

- 7EA Dual fuel conversion is scheduled to start on 21 June 10 provided commercial issues are resolved. Approximately 6 week duration. Pending receipt of payment.

- The following components have been sent to Termozulia. Beckwith; Electro Industries volt/amp meter; coupling bolts; purge and vent valves for fuel gas module; and ignition transformer. Lead times are critical for replacement of these items. Control cards for 7EA are also required this week by Termozulia

2 Engineering and Design

2.1 – General Arrangement-

2.2 – Site /Civil /Structural

2.3 – Mechanical

2.4 – Electrical

    - Additional detail is required to stub up conduit at the location required. A list of foundation has been provided to the engineer for his action.

    - Grounding grid drawings are required.

2.5 – Instrumentation

- Ongoing

2.6 – O&M Manuals –

- Ongoing

3 Procurement

3.1 – Purchase Order Requests

- A local vendor list is being developed with the assistance of SIDOR.

- The lack of Progress Payments is restricting issuing PO’s to local subcontractors and vendors.

- – Equipment & Material Quotations

- Local procurement is hampered by financial restraints

3.3 - Purchase Order –

4 Contracts

4.1 – EPC Contract –

4.2 – Construction Subcontracts –

4.3 – Proposal & Quotes

5 Construction

- 5.1  Schedule

Impacts resulting from lack of progress payments is being reviewed for inclusion

- CPM schedule was issued 14 June 2010.

5.2  Equipment Delivery

5.3  Mechanical

- GT 100 – GT Erection is complete

- GT 200 – GT Erection is complete. Awaiting arrival of turbine for installation.

- GT 300 – GT Erection is complete

5.4  Electrical

- Installation of Manholes and duct banks is ongoing.

- On site meeting was held to resolve high voltage and switchyard final design.

5.5 QA/QC –

- Inspections of concrete placement, excavation, and backfill activities is ongoing.

6 Startup & Commissioning

- Pending.

7 Startup Mobilization

GT 300 7EA GSU Transformer

Duct Bank MH1 to GT 300 PEECC