| EPC | Weekly Report 8 May 2010 |  |
| --- | --- | --- |
| Date: 8 May 2010 | Project: Sidor Site A, Puerto Ordaz Venezuela |  |
| Written By: Patrick Melody | ProEnergy EPC Project Mgr ProEnergy Site Manager | William Lugo Patrick Melody |

Table of Contents

1. Executive Summary

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary .

This report provide an overview of the project activities for the week of 2 May 2010 for the engineering, procurement, and the construction activities on site.

  - Safety & Regulatory Compliance

    - Develop Job Safety Analysis as required.

    - Inspection of motorized equipment prior to usage.

    - Inspection of subcontractor power tools.

  - Personnel/Staffing

| Lugo Bill | Project Director | Jason Bird | Tech Adviser 7EA |
| --- | --- | --- | --- |
| Melody Patrick | Site Manager | Allan Hill | Tech Adviser LM 600 |
| Sewell David | Const. Manager | Meyer Daniel | Material Support |
| Blacke Edward | Safety Manager | Horn Ryan | Tool Room Super. |
| Urbana Diomarys | Local Safety Mgr. | Little John | Mat’l. Coordinator |
| Bretherick Teresa | Scheduler | Daniels Julio | Tool Room (Local) |
| Cornett Clarence | Civil Supt | Izquierdo Weiser | Mat'l. Handler |
| Kirk Scott | Civil Support | Lopez Juan Carlos | Mat'l. Handler |
| Siros James | Mech. Supt. | Ortega Ramon | Tool Room (Local) |
| Archuleta Pete | Piping Supt. |  |  |
| Riley Jasper | Electrical Supt | Cornett Elizabeth | Document Control |
| Herasimchuk Michael | I & C Supt. | Leccia Karina | Admin Assist |
| Soriano Rafael | QA/QC Manager | Mendez Kenia | Translator |
| Thomas Hankins | QA/QC Manager | Zambrano Natalia | Translator |
| Delgado Daniel | Resident Engineer | Alvarez Josbett | Translator |
| Contreras Wilson | Mechanical Supt | Jansen Teodoro | Translator |

  - Weekly Accomplishments

- GT 100 Install Turbine

    - GT 100 Install Puffer Manifold System

    - GT 100 FRP Pipe Rack Foundation

    - GT 100 Install Baffles in Exhaust Stack

    - GT 100 Excavate 15 kv Switch Foundation

    - GT 100 Excavate Cable Rack Foundation

    - GT 100 GSU FRP Lower Half Blast Wall

    - GT 200 Complete Erection of Air Filter House

    - GT 200 GSU FRP Lower Half Blast Wall

    - GT 200 Erect Turbine Exhaust

    - GT 300 Prepare 7 EA Foundation for Equip. Erection

    - GT 300 Assemble/Align Exhaust Stack Base for Welding

    - GT 300 Exhaust Stack Uppers repairs ongoing.

    - Form/Pour Electrical MH 10

    - Form/Pour Electrical MH 8

    - Install Conduit MH 4 to SWBD 100

    - Install Conduit MH 4 to Utility Bldg.

    - Install Conduit GT200 to MH 4

    - Install conduit MH 6 to SWBD 100

    - Excavate MH 10

    - Backfill Foundations Excavation at Gas Compressor

    - Backfill Duct Bank Excavation MH 4 to MH 9; MH 5 to MH 3

    - Excavate Demin Water Tank for Placement of Select Fill

1.4– Scheduling Conflicts

- Development of CPM schedule is ongoing.

  - – Site Managers Commentary and Amplifying Remarks

- Inventory of GT 200 Generator/Turbine is ongoing. Customs has completed the  release of GT 200.

- The ability of the concrete plant to supply the project continues to be a problem. Concrete was not available for placement on  7th, 8th, & 9th May

- A portion of the Mechanical contractor’s employees were not able to access the site due to a Sidor labor strike/protest.

- Erection of GT 100 and 200 is complete. Erection of GT 300 is pending installation of fixators which is ongoing.

2 Engineering and Design

2.1 – General Arrangement-

2.2 – Site /Civil /Structural

2.3 – Mechanical

- Fire protection drawings are required.

- Fully coordinated underground piping drawings are required.

2.4 – Electrical

    - Additional detail is required to stub up conduit at the location required.

    - Grounding grid drawings are required.

    - Switch yard foundations and related duct bank drawings are required.

2.5 – Instrumentation

- Ongoing

2.6 – O&M Manuals –

- Ongoing

3 Procurement

3.1 – Purchase Order Requests

- A local vendor list is being developed with the assistance of Sedor.

- – Equipment & Material Quotations

- Local procurement is ongoing

3.3 - Purchase Order –

4 Contracts

4.1 – EPC Contract –

4.2 – Construction Subcontracts –

- A Purchase Order has been issued to ISI, Mechanical Subcontractor, pending award of a Subcontract. ISI has mobilized on Thursday, 29 April 2010.

4.3 – Proposal & Quotes

5 Construction

5.1  Schedule

- CPM schedule development is ongoing.

5.2  Equipment Delivery

- Fixators for GT 300 arrive on 7 May 2010

5.3  Mechanical

- GT 100 – GT Erection is complete

- GT 200 – GT Erection is ongoing.complete. Awaiting arrival of turbine for installation.

5.4  Electrical

- Installation of Manholes and duct banks foundation ongoing.

5.5 QA/QC –

- Inspections of concrete placement, excavation, and backfill activities is ongoing. Numerous deficiencies of civil subcontractor QC program have been noted. Awaiting additional information from civil subcontractor. Subcontractor has added addiotnal QC staff.

6 Startup & Commissioning

- Pending.

7 Startup Mobilization

Concrete Placement Duct Bank at MH 4

Erection of GT 200

GT 300 7EA Foundation

GT 100, 200, & 300 and Elect. Manholes

Sidor’s 650 ton Crane for Erection of 7EA