## UNIT 300
UNIT 300
DATE: | 2010-10-18
EQUIPMENT | ACTIVITIES | BEGIN DATE | END DATE | PROGRESS | NOTE
TURBINE | CONDUIT | 2010-09-24 | 2010-10-19
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
ACCESORY BASE | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
GENERATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PDC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PEECC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
STACK | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SWTG | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FIRE PROTECTION | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
COOLING WATER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TURBINE AIR INLET FILTER COMP | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
LIGHTING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FOGGING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SCRUBBER SEPARATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TRANSFORMER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER

## UNIT 200
UNIT 200
DATE: | 2010-10-18
EQUIPMENT | ACTIVITIES | BEGIN DATE | END DATE | PROGRESS | NOTE
TURBINE | CONDUIT | 2010-09-24 | 2010-10-19
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
ACCESORY BASE | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
GENERATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PDC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PEECC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
STACK | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SWTG | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FIRE PROTECTION | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
COOLING WATER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TURBINE AIR INLET FILTER COMP | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
LIGHTING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FOGGING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SCRUBBER SEPARATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TRANSFORMER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER

## UNIT 100
UNIT 100
DATE: | 2010-10-18
EQUIPMENT | ACTIVITIES | BEGIN DATE | END DATE | PROGRESS | NOTE
TURBINE | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
ACCESORY BASE | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
GENERATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PDC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
PEECC BUILDING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
STACK | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SWTG | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FIRE PROTECTION | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
COOLING WATER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TURBINE AIR INLET FILTER COMP | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
LIGHTING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
FOGGING | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
SCRUBBER SEPARATOR | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER
TRANSFORMER | CONDUIT
PULLING CABLE
CONNECTION
COTINUITY TEST
MEGGER

## Hoja2
ITEM | ACTIVITY DESCRIPTION | ESTIMED COMPLETION | TOTAL QUANTITIES | % COMPLETION | % COMPLETION | NOTE/COMMENTS/HOLD UPS
1 | GTG 100 AND AUXILIARIES (INCLUDING INTERFACE WITH GSUT |  |  |  | 2010-10-21
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) |  |  |  | 100% | WAITING FOR INSTALLATION OF DCS CABINET
B | CABLE PULLING - POWER | 2010-11-01 |  |  | 90% | 13,8 KV LINESIDE CUBICULE
C | CABLE PULLING - CONTROL | 2010-11-01 |  |  | 95% | DCS CABLE NOT PULLING (NOT INFORMATION)
D | CABLE TERMINATION - POWER | 2010-11-01 |  |  | 95% | STRESS CONE 750 MCM
E | CABLE TERMINATION - CONTROL | 2010-11-01 |  |  | 90% | ELECTRO VALVULAS & FILTER HOUSE & DCS
F | MEGGER CABLE | 2010-11-01 |  |  | 95% | 750 MCM CABLE
G | COTINUITY TEST | 2010-11-01 |  |  | 90%
2 | GTG 200 (LM6000)AND AUXILARIES (INCLUDING INTERFACE WITH GSUT)
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) |  |  |  | 100%
B | CABLE PULLING - POWER | 2010-11-01 |  |  | 90% | 13,8 KV LINESIDE CUBICULE / STRESS CONE 750 MCM
C | CABLE PULLING - CONTROL | 2010-11-01 |  |  | 99%
D | CABLE TERMINATION - POWER | 2010-11-01 |  |  | 95% | STRESS CONE 750 MCM
E | CABLE TERMINATION - CONTROL | 2010-11-01 |  |  | 99%
F | MEGGER CABLE | 2010-11-01 |  |  | 95% | 750 MCM CABLE
G | COTINUITY TEST | 2010-11-01 |  |  | 90%
3 | GTG 300 (7EA)AND AUXILARIES (INCLUDING INTERFACE WITH GSUT)
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) | 2010-10-27 |  |  | 89%
B | CABLE PULLING - POWER | 2010-10-29 |  |  | 78% | CHANGE IN INFORMATION / REACONDITIONING
C | CABLE PULLING - CONTROL | 2010-10-27 |  |  | 75% | CHANGE IN INFORMATION / REACONDITIONING
D | CABLE TERMINATION - POWER | 2010-11-07 |  |  | 20% | NOT AS MANY PULLED
E | CABLE TERMINATION - CONTROL | 2010-11-07 |  |  | 30%
F | MEGGER CABLE | 2010-11-07 |  |  | 20%
G | COTINUITY TEST |  |  |  | 0%
4 | WATER TREATMENT BUILDING EQUIPMENT
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) | 2010-10-27 |  |  | 98% | 100% CABLE TRAY / 95% CONDUIT
B | CABLE PULLING - POWER | 2010-10-28 |  |  | 50% | EQUIPMENT NOT
C | CABLE PULLING - CONTROL | 2010-10-28 |  |  | 75% | PERMANENTLY MOUNTED
D | CABLE TERMINATION - POWER | 2010-11-01 |  |  | 50% | LACK OF EQUIPMET ANCHORAGE
E | CABLE TERMINATION - CONTROL | 2010-11-01 |  |  | 50% | LACK OF EQUIPMET ANCHORAGE
F | MEGGER CABLE | 2010-10-28 |  |  | 50%
G | COTINUITY TEST |  |  |  | 0%
5 | GAS COMPRESSOR BUILDING EQUIPMENT
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) | 2010-11-01 |  |  | 95% | 100% CABLE TRAY/90% CONDUIT MANUFACTURING; WAITING FOR JB
B | CABLE PULLING - POWER | 2010-11-07 |  |  | 70%
C | CABLE PULLING - CONTROL | 2010-11-07 |  |  | 90% | WAITING FOR MOTORS AND PUMP ASSEMBLY
D | CABLE TERMINATION - POWER | 2010-11-08 |  |  | 80% | WAITING FOR MOTORS AND PUMP ASSEMBLY
E | CABLE TERMINATION - CONTROL | 2010-11-08 |  |  | 0% | Information to be release next week
F | MEGGER CABLE | 2010-11-08 |  |  | 70%
G | COTINUITY TEST | 2010-11-08 |  |  | 0%
6 | MAIN CONTROL ROOM EQUIPMENT
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) | LTR |  |  | 0%
B | CABLE PULLING - POWER | LTR |  |  | 0%
C | CABLE PULLING - CONTROL | LTR |  |  | 0%
D | CABLE TERMINATION - POWER | LTR |  |  | 0%
E | CABLE TERMINATION - CONTROL | LTR |  |  | 0%
F | MEGGER CABLE | LTR |  |  | 0%
G | COTINUITY TEST | LTR |  |  | 0%
7 | UTILITY BUILDING EQUIPMENT
A | RACEWAY (CONDUIT, CABLE TRAY, ETC) | 2010-11-01 |  |  | 100%
B | CABLE PULLING - POWER | 2010-11-01 |  |  | 99% | DCS NOT COMPLETE
C | CABLE PULLING - CONTROL | 2010-11-01 |  |  | 99% | DCS NOT COMPLETE
D | CABLE TERMINATION - POWER | 2010-11-01 |  |  | 99%
E | CABLE TERMINATION - CONTROL | 2010-11-01 |  |  | 99% | BLACK START NOT COMPLETE
F | MEGGER CABLE | 2010-11-01 |  |  | 100%
G | COTINUITY TEST | 2010-11-01 |  |  | 80%