## PL CVG A
Electrical Activities - Punch List
Power Station - CVG A
Item | PO | Activity Description | Priority | Resp | Responsible Contractor | Start Date | Completion Date | Orig Completion | Estimated Completion | Total Quantities | % Completion | % Completion Incremental from Yesterday's | Notes/Comments/Hold ups
1 | Follow | Power cable is scheduled to arrive at CVG A site Oct 9th, 2010. Follow up with SIDOR and Customs needed to improve dates | 2 | Bill Lugo/ Pat Melody |  |  |  |  | 2010-10-09 | NA | 2% | NA
2 |  | Control cable is scheduled to arrive at CVG A site Oct 4th, 2010. Follow up with SIDOR and Customs needed to improve dates |  | Bill Lugo/ Pat Melody |  |  |  |  | 2010-10-04 | NA |  | NA
3 | 441 | DCS equipment cabinets are scheduled to arrive Guanta Port Oct 8th and CVG A site by Oct 12th, 2010. Follow up with SIDOR and Customs needed to improve dates |  | Bill Lugo/ Pat Melody |  |  |  |  | 2010-10-12 | NA |  | NA
4 | 441 | MCC parts for GTG 100 & 200 are scheduled to arrive CVG A site Oct 4th, 2010. Follow up with SIDOR and Customs needed to improve dates |  | Bill Lugo/ Pat Melody |  |  |  |  | 2010-10-12 | NA |  | NA
5 | 441 | Rest of skids and pumps (with exception of P- 500A and 500B) are scheduled to arrive CVG A site Oct 9th, 2010. Follow up with SIDOR and Customs needed to improve dates |  | Bill Lugo/ Pat Melody |  |  |  |  | 2010-10-05 | NA |  | NA
6 | Follow | CTG # 100 (LM6000) and Auxilaries (including interface with GSUT)
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | 100 | 97% | 2% | Cabling for DCS is remaining
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | 53 | 80% |  | 13.8 KV line side cubicle in process. Gedney hubs have arrived,
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | 206 | 85% |  | Cabling for DCS is remaining
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | 550 | 90%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | 1200 | 90%
7 | Follow | CTG # 200 (LM6000) and Auxilaries (including interface with GSUT)
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | 100 | 99% |  | Cabling for DCS is remaining
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | 53 | 90% |  | 13.8 KV line side cubicle in process. Gedney hubs have arrived,
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | 206 | 97% |  | Cabling for DCS is remaining
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | 550 | 90%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | 1200 | 90%
8 | Follow | CTG # 300 (7EA) and Auxilaries (including interface with GSUT)
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | 100 | 80%
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | 70 | 50%
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | 860 | 50%
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | 500 | 10%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | 3800 | 40%
9 | Follow | Water Treatment Building Equipment
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | 100 | 70% |  | Cable tray 90% Conduit 40%
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | 55 | 40%
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | 18 | 0%
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | 330 | 30%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | 36 | 0%
10 | Follow | Gas Compressor Building Equipment
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | 100 | 90% |  | Cable Tray 100% Conduit 80%
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | 19 | 75%
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | 10 | 75%
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | 76 | 40%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | 40 | 0% |  | Termination Information requried for gas compressor.
11 | Follow | Main Control Room Equipment
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [5 empty] | TBD | 0%
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [5 empty] | TBD | 0%
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [5 empty] | TBD | 0%
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [5 empty] | TBD | 0%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [5 empty] | TBD | 0%
12 | Follow | Utility Building Equipment
A |  | Raceway (conduit, cable tray, etc.) Installation |  | J Riley | [6 empty] | 99% |  | Cabling for DCS is remaining
B | 441 | Cable Pulling - Power - (qtty: number of pulls) |  | J Riley | [6 empty] | 99% |  | Cabling for DCS is remaining
C | 441 | Cable Pulling - Control - (qtty: number of pulls) |  | J Riley | [6 empty] | 99% |  | Cabling for DCS is remaining
D | 441 | Cable Termination - Power - (qtty: number of terminations) |  | J Riley | [6 empty] | 99%
E | 441 | Cable Termination - Control (qtty: number of terminations) |  | J Riley | [6 empty] | 99% |  | Blck Start Gen. Additional Design Information Required.
NOTES
1 |  | Yellow (Qtts) - By by Svetlana
2 |  | Green (target dates) - By J Riley
3 |  | Blue (Total % Completion) - By J Riley
4 |  | Gray (% Completion increment from Yesterday) - By J Riley