# CVG SIDOR POWER PROJECT SITE “B”

# DATE: 6 September, 2010, Monday # PROJECT #: 410-3203 # SITE MANAGER: Cole Franklin

TEMPERATURE:  90 F

RANGE: 76 to 96

SITE CONDITIONS: sunny, hot, and humid, poor air quality

PERSONNEL ON SITE:

CONSTRUCTION SUPPORT:

Williams Lugo - Project Manager (A&B)

Cole Franklin - Site Manager

Ysrin Gomez – Local Safety (Local)

Keith McMurray - Scheduler (A&B)

Unfilled Mechanical/Piping (local ASAP)

Mark Hanks - Electrical Supt

Jose Garcia - Elect. Field Eng. (local)

Kyle Roskam - Civil Supt

Howard Velasquez-Civil Field Eng (local)

Felix Martinez-QA/QC

Jason Bird - 7EA TA (A&B)R&R

Paul Olivo – Material

Mike Montgomery-QA/QC

MATERIAL SUPPORT:

José Ángel Gonzales – Material (Local)

Julio Daniels 	– tool room (Local)

ADMIN SUPPORT:

Daniel Febres – Logísticas (Local)

Paola Gómez – Administración (Local)

Patricia Muños – Administración (Local)

Skeila García – Translator / Doc Control (Local)

SUBCONTRACTOR PERSONNEL: Concorcio Megavatio

General Superintendant		1

Safety					1

Foremen				1

Electricians				0

Operators				0                     Surveyor				0

Carpenters				5

Surveyor Helper			0

Oiler Helper				0

Crane Operator			0                           Laborers				3

Truck Drivers				0

Concrete Finishers			0

Oilers					0

Plumbers				0

Iron Workers				5

Helpers

Welders				0

Total:					16

SUBCONTRACTOR PERSONNEL: ISI

General Superintendant		0

Safety					1

Foremen				1

Operators				1

Oiler Helper				0

Welders                                         5

Millwrights

Crane Operator			1                           Laborers				0

Truck Drivers				1

Mechanic	      			4

Helpers				6

Pipe fitter                                       0

Total                                             22

SUBCONTRACTOR PERSONNEL:  Coinserma

Foreman                                       2		Laborers				6

Safety                                            1		Skilled					6

Operators                                      2

Welders				2		total 19

- GENERAL ITEMS

  - Received valuation #2 from Concorcio Megavatio and returned same today, not corrected.  Need new copy of valuation corrected to prepare a PO for last month.

  - Directed surveyors (Concorcio) to layout storm drains where possible.  PO pending

  - Crane erection for 7FA equipment. No work today

  - Consorcio Megavatio offsite today

- CLIENT ISSUES/CONCERN:

2.1   Drainage for RO Water System, study underway to see if it can be rerouted North to miss duct banks.

2.2   Access to GSU for service (grating over containment area) Check Chem Grate, cost will be prohibitive.  Will prepare quote for Sidor.

- CIVIL:

  - Ready to proceed with de min and raw Water Tanks after backfill of DB

  - Received drawings to prepare liquid Fuel De Scope documents.

  - Received unit pricing  from Coinserma to excavate for piping.  Will review and issue PO if acceptable.

  - Poured duct bank near GSU 100.

  - Working DB West side of MH 5 Concrete placement Monday Sept. 6, 2010

  - Anchor bolts checked and grouted, finishing grouting fixators, plan to set turbine 9 Sept.

- CONCRETE FOUNDATIONS:

4.1 Poured 7FA diffuser foundation base

- MECHANICAL:

  - ISI with 22 people, installing Turbine and Accessory piping and enclosures

  - Continue with 7EA stack weld, sent paint spec. to Sedalia for review to prepare scope and RFQ.

  - Installing platforms for doors for the enclosures, need modifications, will get sketches this week.

  - Installing bolts on Filter House Structure, awaiting delivery of correct bolts.

- PIPING:

  - Plan to start piping installation this week if we can get PO issue resolved.

  - Need a film viewer.  Will purchase locally.

  - ISI continues piping installation on 7EA

  - ISI continues exhaust joint installation

  - ISI will start underground piping this week.

- ELECTRICAL:

  - Cathodic protection contractor, received quote for Tanks Monday, Sept. 6 and piping is scheduled for Friday, Sept. 10

  - Continue preparing Cable schedule and audit of electrical drawing against equipment nomenclature tags

  - Meggering of electrical motors near complete

  - Inventorying electrical materials that do not match packing list to prepare a delta between what is on site and what needs to be ordered immediately.

- INSTRUMENTATION AND CONTROLS:

9.    SCHEDULED ITEMS:

9.1 General Schedule issues

The schedule is predicated by the following:

- Contractor increases manpower to work in all areas

- Contractor works two shifts or a 12 hours shift (were notified both the main civil and the mechanical contractors plan to reduce overtime for commercial issues.  Will work a 48 hour week, 4 each 9 hrs days and 1 each 8 hr days.

- Sedalia material delivers are forthcoming to meet demand

9.2 Milestone Payment Estimated Delivery

- Completed Milestone Payments (50%)

Complete

- Gas Turbines on Foundation (10%)

Sep 9, 2010 4 day delay Awaiting crane installation for turbine lift.  Met with Sidor to prompt them to start crane set-up.  Walked the haul road and showed where additional fill is necessary to augment the portion completed by contractor.  Probable date to set turbine is 9 Sept

- Civil Foundations Complete (25%)

Sep 15, 2010 (*) do not have all drawings for foundations.  We expect at least 5 weeks delay, schedule review continues.

- Electrical/Mechanical Complete (10%)

Dec 3, 2010 (*) expect at least 5 weeks due to lack of drawings and lack of electrical contractor, electrical field engineer reviewing existing drawings to prioritize drawings delivery and cable routing..

- Start- up Complete and Ready to Export Power (5%)

Dec 11, 2010 (*) see above expect a revised schedule week end

The dates (*) will be revised as soon as the schedule review is complete and a history is trend is available.

9.3 Ready for Start-up Dates

- Unit 100 – 7EA

Nov 29, 2010* expect slippage

- Unit 200 – 7FA

Dec 11, 2010

- CRITICAL AREAS OF CONCERN:

  - Commercial issues with Contractors.

  - Shortage of cement is affecting the scheduling of foundations.  I am not entertaining accelerated schedule at this time without assurance of commercial restitution.

  - .Install Site construction power, contractor received payment for other PO, have asked they use a portion to install site power. Contractor informed us he is ordering material, at least 5 days before starting installation.

  - Need to assure the 7FA has all materials, contractor support, and resources from PES to meet or shorten the schedule.  Cost for GE TA is 25K per week.

  - Crane installation and acceleration of set up schedule between turbine and generator lifts for the 7FA.  Sidor advised they would have crane ready for Wed lift of turbine.

  - SAFETY:

    - Inclement weather, open excavations, night work with lights

    - Spotters for equipment operators

  - OUTSTANDING DRAWINGS:

| Drawings Issue | Forecast date | New F/C date | Closed |
| --- | --- | --- | --- |
| Substation Foundations 7FA ISO phase bus(GA#22) 7FA Generator Breaker(GA#31 7FA FG Heater(GA#TBD) | TBD |  |  |
| 7FA CWM(GA#11) 7FA Fin Fan | 3 August, 10 5 August, 10 |  |  |
| U/G piping | 5May10 | 28May10 | Comments pending |
| Design essentially complete | 31 May | No forecast date | No forecast date |

11. PICTURES:

Photo 1: concrete between #100 & GSU

Photo 2: Crane for 7FA turbine

Photo 3: Crane for 7FA erection

Photo 4: 7FA Fixator grout and crane in background