# CVG SIDOR POWER PROJECT SITE “B”

# DATE: 30 September, 2010, Thursday # PROJECT #: 410-3203 # SITE MANAGER: Cole Franklin

TEMPERATURE:  82 F

RANGE: 76 to 95

SITE CONDITIONS: overcast, hot, humid

PERSONNEL ON SITE:

CONSTRUCTION SUPPORT:

Williams Lugo - Project Manager (A&B)

Cole Franklin - Site Manager

Ysrin Gomez – Local Safety (Local)

Keith McMurray - Scheduler (A&B)

Unfilled Mechanical/Piping (local ASAP)

Unfilled mechanical / piping expat ASAP

Mark Hanks - Electrical Supt

Jose Garcia - Elect. Field Eng.

Kyle Roskam - Civil Supt

Howard Velasquez-Civil Field Eng

Felix Martinez-QA/QC

Jason Bird - 7EA TA

Paul Olivo – Material

Unfilled T/O coordinator

MATERIAL SUPPORT:

José Ángel Gonzales – Material (Local)

Julio Daniels 	– tool room (Local)

ADMIN SUPPORT:

Daniel Febres – Logísticas (Local)

Paola Gómez – Administración (Local)

Patricia Muños – Administración (Local)

Skeila García – Translator / Doc Control

SUBCONTRACTOR PERSONNEL: Concorcio Megavatio

General Superintendant		1

Safety					1

Foremen				2

Electricians				2

Operators				1                    Surveyor				1

Carpenters				5

Surveyor Helper			2

Oiler Helper				0

Crane Operator			0                           Laborers				6

Truck Drivers				2

Concrete Finishers			0

Oilers					0

Plumbers				0

Iron Workers				5

Helpers

Welders				1

Total:					29

SUBCONTRACTOR PERSONNEL: ISI

General Superintendant		0

Safety					1

Foremen				1

Operators				1

Oiler Helper				0

Welders                                         6

Millwrights

Crane Operator			1                           Laborers				0

Truck Drivers				1

Mechanic	      			4

Helpers				6

Pipe fitter                                       6

Total                                             32

- GENERAL ITEMS

  - 7FA generator set on foundation, crane disassembly not started after setting.  Critical lift plan attached.

  - Dual fuel team working on 7EA.  Pipe repairs to pre fabbed spools, need QA/QC for work performed in Sedalia, no NDE reports.

  - Need to review model contract and get contractors to table to formalize contracts.  Concorcio seems agreeable to meet about contract but no date for meeting.  We are preparing a line item scope of work.

  - Need status of delivery for de min and raw water tank materials

  - Crane assembled for 7FA Generator placement, reviewed lift plan with Sidor and GE this morning, plan to lift tomorrow morning.

  - Had teleconference for 7FA with GE today.

- CLIENT ISSUES/CONCERN:

  - Access to GSU for service (grating over containment area) Chem. grate manufacturer came to site to view GSU at Site A and prepare a quote and design. Ongoing

  - Building design for office maintenance building, PSC, and MCC attached to compressor building.

- CIVIL:

  - Spoke with David Miner (Maracaibo), will prepare a quote and can start with approved materials immediately after receipt of PO for compressor bldg anchor bolts.

  - Removing excess spoils from High Yard area to offsite location

- CONCRETE FOUNDATIONS:

  - Backfill ongoing compressor bldg, anchor bolt RFQ prepared.

  - Ongoing forms and rebar for Raw Water Tank Foundation

  - Stopped forms and rebar for Demin Water Tank, requires cutting forms that will be first utilized for raw water tank.

  - Extending spare conduits on 7FA placed lean concrete for Accessory Module Foundation

  - Laid out excavation boundaries for Unit #100 GSU today, started excavation.

- MECHANICAL:

  - Started LO prep for flush, necessary to move disassembled materials from Site A to Site B

  - Paint spec. to Sedalia for review to prepare scope and RFQ.  Received a material spec, but this requires purchase of material in US and then testing to see if it is acceptable. Unresolved

  - Prepare a QA plan for tanks.  Issued scope of work for Tank PO. QA/QC plan received first draft, returned with comments.

  - GE Rep left site after 7FA generator setting.  Need forecast for when Sidor will remove the crane and the temporary fill used to set crane.

- PIPING:

  - Piping installation is started, but NCR issued for materials.  Received PES QA Plan and find MTR required per plan.

  - Need a film viewer.  Will purchase US not available here, they read film with flashlight.  Have doubts to the veracity of the x-ray readings.

  - ISI continued underground piping this week.  Fabbing spools for tie points.  Preparing ISO’s from drawings produced at site.

- ELECTRICAL:

  - Cathodic protection contractor, received quote for Tanks Monday, Sept. 6 and piping is scheduled for today, received quotation cathodic people will come to site tomorrow and discuss the planned installation after testing conductivity in A. Unresolved

  - Cable schedule for hi and med voltage cables completed.  Will send list ot EDGI for review.

  - Review and audit of electrical drawing against equipment nomenclature tags ongoing, all transformers checked will check motors and additional materials as received. Ongoing

  - Prepared a scope of work for electrical contract with local contractor, about 80% complete.

  - Need to prepare a CO for delays in energizing temp const power to site.  De mob of equipment to Site A, shut down const power at site.  Met with Sidor late afternoon to jointly conduct punch list for energizing. Ongoing

  - Daniel Gonzalez informed us he had a building we could check the electrical equipment in, Mark Hanks will follow up.

- INSTRUMENTATION AND CONTROLS:

9.    SCHEDULED ITEMS:

9.1 General Schedule issues

The schedule is predicated by the following:

- Contractor increases manpower to work in all areas

- Contractor works two shifts or a 12 hours shift.  Need authorization to work more hours.

- Sedalia material delivers are forthcoming to meet demand

9.2 Milestone Payment Estimated Delivery

- Completed Milestone Payments (60%)

Complete

- Civil Foundations Complete (25%)

Sep 15, 2010 (*) do not have all drawings for foundations.  We expect at least 7 weeks delay, schedule review continues.

- Electrical/Mechanical Complete (10%)

Dec 3, 2010 (*) expect at least 5 weeks due to lack of drawings and lack of electrical contractor, electrical field engineer reviewing existing drawings to prioritize drawings delivery and cable routing..

- Start- up Complete and Ready to Export Power (5%)

Dec 11, 2010 (*) see above expect a revised schedule week end

The dates (*) will be revised as soon as the schedule review is complete and a history is trend is available.

9.3 Ready for Start-up Dates

- Unit 100 – 7EA

Early  2011* expect slippage

- Unit 200 – 7FA

Early  2011

- CRITICAL AREAS OF CONCERN:

  - Commercial issues with Contractors.

  - Crane set up for 7FA generator will plan to de-mob GE TA after setting gen.  This will be a total of three week delay with associated cost exceeding $50K

  - Building design.

  - Installed Site construction power, must check secondary side after stabbing fuses.  Will test tomorrow after installing another ground rod.  Prepared punch list for works with Sidor.  Lack of generators and light plants are now a cost to Sidor, they are not accepting temp power even though they inspected prior to shut down to connect. Ongoing

  - Need to assure the 7FA has all materials, contractor support, and resources from PES to meet or shorten the schedule.  Cost for GE TA is 25K per week.  Plan to de-mob GE after setting Generator.  Earliest is now Tuesday but Wednesday is more realistic if crane erection completed Tuesday

  - SAFETY:

    - Inclement weather, open excavations, night work with lights

    - Spotters for equipment operators

  - OUTSTANDING DRAWINGS:

| Drawings Issue | Forecast date | New F/C date | Closed |
| --- | --- | --- | --- |
| Substation Foundations 7FA ISO phase 7FA Generator Breaker(GA#31 7FA FG Heater | TBD |  |  |
| 7FA Fin Fan Fdn | 5 August, 10 |  |  |
| U/G piping | 5May10 | 28May10 | Prepared dwgs in field |
| Design essentially complete | 31 May | No forecast date | No forecast date |

11; Pictures

Photo 1: U/G pipe fab

Photo 2: Compressor foundation backfill

Photo 3: Liquid fuel and accy module exc

Photo 4: 7FA gen on the move

Photo 5: Crane ready for 7FA gen

Photo 6: 7FA gen under crane

Photo 7: 7FA gen coming up

Photo 8: 7FA gen up

Photo 9: Level

Photo 10: 7FA gen down