Table of Contents

1. Executive Summary

EPC

Weekly Report 18 to 24 Sep 2010Date: 25-Sep-10Project: Sidor Site B, Puerto Ordaz Venezuela Written By: Cole Franklin ProEnergy EPC Project Mgr

ProEnergy Site Manager

William Lugo

Cole Franklin

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start-Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary.

This review is for the week from 18 to 24 September 2010.  The safety is relatively good, minor issues with contractors and PPE.

The Sidor backfill for the crane pad for the 7FA Generator is not completed will probably go through Monday 20 Sep.  The crane will be assembled after backfill is completed possibly will be ready for lift Thursday 23 Sep.

Contractor quality is good, contractor commercial issues and lack of contract are causing planning nightmares.  We advised the contractor to start staffing up, met with Concorcio to discuss this.  We are now preparing PO for specific work and delivering to Concorcio, see a potential for incurred cost not defined by PO (ie overhead cost for offices, back fill of existing works not covered by new PO, site trash and water truck, safety personnel, ect)..

We met with Coinserma, the are continuously slipping schedule.  I asked for a schedule, told them it was very aggressive and they still indicated they would perform.  Their schedule slipped again for the second week.  I am planning to release them, but keep them interested until we can negotiate with Concorcio Megavatio for this work.   Demobilized Coinserma, they prepared and we reviewed their units to finalize cost to date.

Planning a two week slow down for site b.  We need materials and this will allow deliveries and progress the site.

1.1 Safety & Regulatory Compliance –

- General Safety will be maintained at all times on site, Concorcio is slow to respond and we will request a new site safety supervisor.  Overhead work started, and night work around open excavations for 7FA repairs.

- Daily safety audits are now in place, weekly recap to office.

- Contractor will be directed to install permanent Bulletin board will be installed.

- The safety people and contractor prepared a recap of all man-hours worked, this figure will be incorporated into the sign.

  - Personnel/Staffing –

Cole Franklin (Site Manager)

Keith McMurray (scheduler shared A&B)

Skeila Garcia (doc control and translator)

Paola Gomez (administrative assist. Local hire)

Patricia Munoz (logistics assist. Local hire)

Daniel Febres (logistics support local hire)

Ysren Gomez (safety supervisor Local hire)

Kyle Rosken (Civil Superintendant)

Mark Hawks (Electrical supervisor)

Felix Martinez (QA/QC supervisor)

Paulo Olivio (Material coordinador)

Jose Martinez (material management local hire)

Jason Byrd (TA 7EA 7FA)

Julio Daniels tool room attendant

Jose Garcia Electrical field engineer

Howard Velasquez Civil field engineer

Agustin Navarro GE on site this week

1.3 Weekly Accomplishments

- Ready for 100 GSU

- Fixators set for 7FA Generator

- Waste tank excavation and backfill completed

- Poured top for MH 2

  - Scheduling Conflicts –

- Duct banks still issue, the foundation for the compressors will start next week if the final portion of the duct bank adjacent is completed, no work Weekends, contractor has money issues.  Need anchor bolts, last vendor advises they also want to substitute non spec bolts that are not an equal or better than spec.

- U/G piping contractor is not working long shifts, they worked this week, but indicate this is the last.  We will send the surplus people to site A to finish 7EA.

- Must move on the office and maintenance bldg.  Review of the building design after questions by Sidor.  Howard has determined that we have a problem with the foundation based on crane loads.  Bill asked we develop a solution, but it is near impossible without overhead crane loads.

1.5– Site Managers Commentary and Amplifying Remarks

The remaining duct bank adjacent to the 7EA is partially excavated; we stopped the contractor from further excavation until finished with section open.  The contractor started excavation without finishing, demanded they finish this section this week, but they did not.

We need additional Concorcio people and machinery, they started here Tuesday and are moving quickly to finish the work previously POed.  Concorcio advised they will be fully mobilized next week after finishing site A

Mark and Jose (field engineer) have prepared a take off of electrical drawings and inventoried the materials in laydown yard.  We will send the results to Sedalia next week to order the Delta for the wiring.  Plan to try to get a electrical contractor quoting on a contract so we can start when the cable is returned.

Engineering and Design

2.1.1 Received the following drawings this week;

2.1.2 Grounding

- The grounding shown on grounding drawings is not in accordance with the discussion with Sidor regarding grounding of equipment.  This will become a major issue.  Need to put it to bed!

2.1.3 Geo tech membrane treated fuel oil tank

- The geo tech fabric for oil tank arrived damaged.  Supplier assured they would repair the material when they installed.  We requested they assure their guarantee to be passed over to Sidor when we turned over the material to Sdior.  They refused and we returned the material for material undamaged.

  - – Site /Civil /Structural

    - Waste tank base poured.

    - 7FA generator grouted fixators.

    - Poured several parts of duct bank.

  - – Mechanical –

    - The 7EA stack weld out near complete

    - 7EA piping ongoing

2.4 – Electrical –

2.4.1    Duct bank contractor on site, ongoing.

2.4.2    Take off completed for all identified Hi Voltage and Medium Voltage cable

2.4.3    Completed review of transformers against drawings, required we open the crates.

2.4.4    Verified the motor and finished meggering all on site.

2.5 – Instrumentation - To Be Completed

2.5.1 EDGI tells us the missing information is due from PES

2.5.2 Prepared a list of all electrical electronic parts removed and sent to Termozuila

2.6 – O&M Manuals –

2.6.1 Need to transmit officially one copy 7FA manual.

3. Procurement

3.1 – Purchase Order Requests

- Construction power transformer installation started, awaiting outage to connect.

- Anchor bolts for hi voltage yard and buildings

- Compressor bldg and compressor bolts, last quoting vendor advises they will not offer the proper bolts.

3.2 – Equipment & Material Quotations –

1.

3.3 - Purchase Order

Demin and Raw tank PO issued to same contractor as A

4. Contract

4.1 – EPC Contract –

- CO 001 sent of Poor Soils Site B

- CO002 sent for Backfill under crane due to CO001

- CO 003 construction power distribution to site materials

- CO 004 core drilling to Derwick for Sidor provided concrete

- CO 005 issued for core drilling

- CO 006 issued for moving diesel tank

- CO 008 prepared for back fill under crane at 7FA

- CO010 for repairs to lay down road

- CO for Paint

4.2 – Construction Subcontracts –

1. Contract negotiations with Concorcio on hold, will attempt to get them back to table.

4.3 – Proposal & Quotes

1. Received quote from Ceimusa for Office and maintenance building.	Completed the work

5. Construction

5.1 – Schedule

  - Schedule two week look ahead will not be issued to Sidor next week.

  - 19 day delay for the setting of Generator for 7FA

5.2 – Equipment Delivery – in progress

5.2.1 Material issues, early delivery of packing list before receipt of material, and P.O.s are a major problem

5.3 – Mechanical –

5.3.1 7EA build continues need to pour additional foundations

5.4 – Electrical –

5.4.1 duct bank and manholes ongoing

Preparing scope for electrical contractor

5.5 QA/QC –

- Ongoing inspections concrete, formworks and anchor bolts.

- Started collecting documents for inclusion in T/O manuals

- Weld map prepared 2 production x-rays taken, need film reader to review the x-ray film.

6 Startup & Commissioning –

7 Startup Mobilization - None

Picture 1: 7FA Gen lift crane status over Accy module fdn

Picture 2: De min tank mud mat

Picture 3: Waste tank fdn second pour