Table of Contents

1. Executive Summary

EPC

Weekly Report 23 Sep to 29 Oct 2010Date: 1-Nov-10Project: Sidor Site B, Puerto Ordaz Venezuela Written By: Cole Franklin ProEnergy EPC Project Mgr

ProEnergy Site Manager

William Lugo

Cole Franklin

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start-Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary.

This review is for the week from 23 to 29 October 2010.  The safety is relatively good, minor issues with contractors and PPE.

The 7FA generator damaged by Sidor remains a large issue with no final response from GE.

The two week slow down for site b has been ineffective, the staff took two weeks without pay, but no payments have been forthcoming.  We have ROFed the crew except the material manager, 7EA TA, and me.

There is no resolution to the building design ongoing saga.  If we plan to place the concrete before the next rainy season we should be working on the building fdns now.

We are spending a large portion of the site staff time doing engineering reviews and corrective actions that are not normally in Site team scope.  It is very frustrating to all.  It feels like Site B staff has been punished for something beyond their control.

1.1 Safety & Regulatory Compliance –

- General Safety will be maintained at all times on site, Concorcio has provided a new site safety supervisor.

- Daily safety audits are now in place, weekly recap to office.

- The safety people and contractor prepared a recap of all man-hours worked, this figure will be incorporated into the sign.

  - Personnel/Staffing –

Cole Franklin (Site Manager)

Skeila Garcia (doc control and translator)

Paola Gomez (administrative assist. Local hire)

Patricia Munoz (logistics assist. Local hire)

Ysren Gomez (safety supervisor Local hire)

Paulo Olivio (Material coordinador)

Jose Martinez (material management local hire)

Jason Byrd (TA 7EA 7FA)

Julio Daniels tool room attendant

Jose Garcia Electrical field engineer

Howard Velasquez Civil field engineer

Agustin Navarro GE demobilized until cash flow is assured.

1.3 Weekly Accomplishments

- 7FA diffuser set

- Demin tank, raw water tank, and compressor fdn poured.  Waiting for Cathodic material for tanks.  Tank sheets deliveries are imminent for raw water tank.

- 7EA lube oil flush concluded, quality excellent.  Clean up and restore of piping ongoing.

  - Scheduling Conflicts –

- Need info on buildings

- Materials for tanks

- Cathodic materials

- Wire deliveries

1.5– Site Managers Commentary and Amplifying Remarks

The Concorcio has delivered a quote to complete the civil work and have expressed an interest in also undertaking the duct banks adjacent to foundations.  This is a win – win situation.  Their cost is slightly higher, but they are then accountable for schedule and overall cost will probably be reduced accordingly.  The last two weeks with a larger crew have shown remarkable progress.  If they continue we will have a significant cost reduction.  This is predicated by receipt of sufficient cash flow to maintain the momentum.

Mark and Jose (field engineer) have prepared a Cable schedule from electrical drawings and inventoried the materials in lay down yard.  We prepared a line item scope of work as a precursor to a contract negotiation.

The MCCs are in a enclosed storage in preparation for opening and confirming internal wiring and all components are installed.

Engineering and Design

2.1.1 Have no resolution on building design problems from Septagon Mesco

2.1.2 Grounding

- The grounding shown on grounding drawings is not in accordance with the discussion with Sidor, we are proceeding to ground in accordance with Sidor requirement and red line drawings for future correction.  Need to put it to bed!

2.1.3 Geo tech membrane treated fuel oil tank

- The geo tech fabric for fuel oil tank arrived.   Supplier assured they will pass their guarantee to Sidor when we turn over the material to SIDOR.

  - – Site /Civil /Structural

    - Raw water and de-min tanks are poured and backfilled.

    - Poured mud mat for last Man Hole.

    - Poured first compressor pour

    - Poured 7FA accy module and fuel floors

  - – Mechanical –

    - The 7EA L.O. flush is completed

2.4 – Electrical –

2.4.1   Line list for cables prepared

Line Item scope of work prepared

2.4.3    Move MCC to secure area next week and open and compare to drawings.

2.5 – Instrumentation - To Be Completed

2.5.1 EDGI tells us the missing information is due from PES

2.6 – O&M Manuals –

2.6.1 Started preparing to turn over the L.O. system to Sidor had Dennis work a day and a half, but the books are a disaster.  Site will prepare a new evolution based on latest drawings, when time and manpower permits.

3. Procurement

3.1 – Purchase Order Requests

- Anchor bolts for hi voltage yard and buildings hold

- Compressor bldg and compressor bolts arrived

3.2 – Equipment & Material Quotations –

1.

3.3 - Purchase Order

Demin and Raw tank PO issued to same contractor as A

Awaiting more info for Cathodic protection installation services PO

4. Contract

4.1 – EPC Contract –

- CO 001 sent of Poor Soils Site B

- CO002 sent for Backfill under crane due to CO001

- CO 003 construction power distribution to site materials

- CO 004 core drilling to Derwick for Sidor provided concrete

- CO 005 issued for core drilling

- CO 006 issued for moving diesel tank

- CO 008 prepared for back fill under crane at 7FA

- CO010 for repairs to lay down road

- CO for Paint

- CO for Inspection services Damaged Generator

  - – Construction Subcontracts –

1.   Contract negotiations with Concorcio not complete, have quotation for remaining work.

4.3 – Proposal & Quotes

1.   Need quote for GE site office

3.   Need quote to make the internet access work, GE requires access to drawings and we cannot currently provide adequate bandwidth to enter “PNet”.

5. Construction

5.1 – Schedule

  - Schedule two week look ahead will be issued to Sidor next week.

  - Received three week look ahead from Concorcio

  - – Equipment Delivery – in progress

- Material issues, early delivery of packing list before receipt of material, and P.O.s are a major problem

- Need tank materials

- Need Cathodic protection for tank materials

- Need cables

5.3 – Mechanical –

1.  7EA build continues need to pour additional foundations

5.4 – Electrical –

1.   duct bank and manholes stopped except where necessary to complete the foundations

5.5 QA/QC –

- Ongoing inspections concrete, formworks and anchor bolts.

- Started collecting documents for inclusion in T/O manuals

- Weld map prepared 2 production x-rays taken, need film reader to review the x-ray film.

6 Startup & Commissioning –

7 Startup Mobilization - None

Picture 1: ACCY and liquid fuel 7FA

Picture 2: MH 6 mud mat

Picture 3: compressor second pour formwork