# CVG SIDOR POWER PROJECT SITE “B”

# DATE: 15 July 2010, Thursday # PROJECT #: 410-3203 # SITE MANAGER: Cole Franklin

TEMPERATURE:  81 F

RANGE: 78 to 90

SITE CONDITIONS: mostly showers

PERSONNEL ON SITE:

CONSTRUCTION SUPPORT:

William Lugo - Project Mgr (A&B)

Cole Franklin - Site Manager

Ysrin Gomez – Local Safety (Local)

Keith McMurray - Scheduler (A&B)

Unfilled mechanical/piping (local ASAP)

Mark Hanks - Electrical Supt (A&B)

Unfilled - elect. field engineer (local ASAP)

Kyle Roskam - Civil Supt (A&B)

Unfilled -turnover engineer (need 15Jul)

Felix Martinez-QA/QC (A&B)

Unfilled QA/QC supervisor (local ASAP)

Melinda Siros for unfilled – Document control  (asap)

MATERIAL SUPPORT:

José Ángel Gonzales – Material (Local)

Paul Olivo – Materials

– tool room (Local)

ADMIN SUPPORT:

Daniel Febres – Logísticas (Local)

Paola Gómez – Administración (Local)

Patricia Muños – Administración (Local)

Skeila Garcia – Translator & Doc Control (Local)

Richard Gaines – EDGI electrical (A&B)

SUBCONTRACTOR PERSONNEL:

General Superintendant		1

Safety					1

Foremen				3

Electricians				0

Operators				0                      Surveyor				1

Carpenters				7    Surveyor Helper			2

Oiler Helper				0

Crane Operator			0                           Laborers				4

Truck Drivers				0

Concrete Finishers			0

Oilers					0

Plumbers				0                        Iron Workers				10

Helpers				4

Welders				2

Total:					35

- GENERAL ITEMS:

  - Did not receive the graphic for the crane from Sidor today, they did not attend contractor’s meeting.  Prepared a time line showing anchor bolts arrival, installation of bolts, pour, stripping of forms, backfill, crane assy, disassy, setting of generator, and same for turbine.  Today Sidor’s crane supt. advises again he will try to get the super lift kit delivered.

  - Contacted a pressure grouting company to come to site to prepare a quote and advise what is necessary to start this work as soon as possible.

  - Little work on 7FA foundation, the anchor bolts and Unisorb pre pour package are not on site.  Hope for delivery next week.  Received PO for anchor bolts has three (3) typos, called and e-mailed to assure these are only typos and this can be corrected before bolts arrive, bolts are delayed 4 more days according to latest information received at site.  Lack of anchor bolts is a day per day delay to schedule.

  - We prepared the PO for signature and hopefully will start excavation for duct bank this week.  Received a drawing from Sidor for the pull boxes (manholes).  Richard G will plot full size for the contractor.  PO signed

  - Need to order Geo Tech Membrane for Treated fuel oil tank.  PO prepared, and signed

  - Proposal for modifying sea containers for lay down area office, temperature controlled storage and running power to area offer is on hold pending resolution of commercial issues.  Will issue after confirm quote is still good

  - RFP for trash containers and disposal of trash is prepared pending new quotes.  Will renew contact

  - The dismounting of crane is not completed.  Sidor asked us to accelerate the anchor bolts for the 7FA, and assure we can install the 7FA before 15 Aug.  We asked for a sketch showing their proposals for setting the crane not received today.  Had a meeting with Sidor regarding the crane they will provide a graphic showing the crane setting where I proposed.  If it is as I envision it we do not need the super lift kit.  Will require a significant amount of fill under the crane, but this is back chargeable.  Prepare a quote for a change order, but cannot issue without reviewing the certified rigging plan from Sidor.

  - We will need duct bank details for the area immediately adjacent to GSU 100 when we start excavation for the GSU after crane moves, must pour duct bank area before GSU.

  - GSU embeds PO on hold commercial, mechanical contractor prepared a quote for fabricating them at site.  Will turn on PO after the base PO is prepared for ISI tomorrow

- CLIENT ISSUES/CONCERN:

  - The client was made aware that type II concrete is necessary for 7FA foundation, and adequate equipment plus adequate delivery rate is essential.  Client has made no promises regarding availability of type II cement.

  - Client advised they do not accept the response from EDGI regarding location of Treated Fuel tank.  Meeting held at site with Sidor engineering, and PEC.  We prepared a CO for this to submit to Derwick.

  - Request for purchase for trash bins for site lay down area and construction site released RFP for delivery dates. Sidor has provided one container for wood and trash; still require one more for steel scrap and regular emptying of the both.

  - Prepared a list of all needed from Sidor to accelerate the project.

- CIVIL:

  - PEECC, ISI manufacturing embeds.  Hilti RE500 is ordered for embedding the plates.

  - Oily water separator wall forming continues.  Rebar is finished.

  - Lack of resolution for Treated Fuel Oil Tank location, awaiting CO.

  - Contractor has prepared the 7FA silencer base fill and 7FA stack base fill and poured the mud mats.  Forms ongoing, plan to pour 30 M3 Tuesday below anchor bolt level.

  - Signed PO for local purchase for Geotech membrane.

- CONCRETE FOUNDATIONS:

  - Work on the 7FA main slab halted, working on silencer and stack foundations.  Halted for rain yesterday.

  - 7FA Unisorb and anchor bolts, released for shipment yesterday, expected available to ship on or before 17 July, need at site 20 July to meet present schedule.  This will slip at least 4 days

  - PEECC embeds to be built by ISI (mechanical contractor) delayed by rain yesterday

  - Crane de mob ongoing, delaying GSU excavation.

- MECHANICAL:

  - Will issue PO for start of 7EA stack repairs and erection.

  - Will start set first piece of stack on foundation possible tomorrow.

  - Will start ISI with 12 people on Monday 19  July, for stack after first section is set on foundation.

- PIPING:

  - Issued PO for piping to ISI

  - Will start ISI on prefab of U/G piping.  Will double joint 10” RW piping

- ELECTRICAL:

  - Loaned 5100 linear feet of conduit to Site A.  They will order to replace it, will need it within 1 week.

7.2 Coinserma prepared a new bid.  The execution of this scope will require a large amount of PES time to supervise this work, need to have an electrical local field engineer full time for this.

7.5 The underground piping and duct bank is now critical path and is driving the schedule, can afford no more delays.

7.6 Need to review cathodic protection general specifications; I sent Luis Acevedo a request for advance copy, he advises it is not available.

- INSTRUMENTATION AND CONTROLS:

8.1 Call Mike Horn to determine who is doing DCS and get some details

- SCHEDULED ITEMS:

9.1 General Schedule issues

The schedule is predicated by the following:

- Commercial issues are resolved to local purchase materials

- Contractor increases manpower to work in all areas

- Contractor works two shifts

- The Underground and duct bank is started week of 7 June and does not slip more

- Sedalia material delivers are forthcoming to meet demand

9.2 Milestone Payment Estimated Delivery

- Completed Milestone Payments (50%)

Complete

- Gas Turbines on Foundation (10%)

July 19, 2010 this has slipped for 7FA due to shortage of anchors, we must come up with an incentive to contractor to accelerate the schedule and we must receive the materials for the foundations.  We think the extension as of now is 3 weeks or Sep 5, 2010 for 7FA

- Civil Foundations Complete (25%)

Sep 15, 2010 (*) do not have all drawings for remaining foundations.  Need a forecast date for foundation drawings.  Expect at least 3 weeks delay

- Electrical/Mechanical Complete (10%)

Dec 3, 2010 (*) expect at least 3 weeks due to lack of drawings and lack of electrical contractor

- Start- up Complete and Ready to Export Power (5%)

Dec 11, 2010 (*) see above  expect a revised schedule week end

* Note (*): These dates are estimated based on current uncertain conditions (lack of payment, cash issues, material/equipment deliveries on hold, contractors working at very slow pace, etc).. They will be revised as soon as the schedule review is complete and a clearer path forward is known.

9.3 Payment milestones

- Unit 100 – 7EA

Nov 29, 2010 (*)

- Unit 200 – 7FA

Dec 11, 2010 (*)

- CRITICAL AREAS OF CONCERN:

  - Sidor provided crane now being disassembled, expect 4 days to finish (not finished today 9th day). Sidor explained they have a union problem with the crane sub contractor, but expect to be started again Fri 16 July

  - Lack of materials (anchor bolts 7FA, embed plates PEECC 7EA

  - Changes in designs are impacting project progress/completion.   Need drawings for all foundation and updated GA to meet progress milestone.

  - Need finalized design or if that cannot be completed, need to include all equipment on GA and freeze the design with Sidor approval.

  - Shortage of cement is affecting the scheduling of foundations.  Sidor indicated the lack of concrete is due to site B being second priority.  PES needs to schedule a meeting with Sidor to assure type II Portland cement is available for the 7FA foundation.

  - Duct Bank drawings new forecast 28 June, for issued for construction drawings

  - Need to Issue RFI for Building drawings series 30.

  - Material deliveries and the trickle down caused by commercial issues seriously retard our ability to execute schedule

  - SAFETY:

    - Concorcio Megavatio reported job site information board was assembled and ready to bring to site for installation.   Pending resolution of commercial issues.

  - OUTSTANDING DRAWINGS:

| Drawings Issue | Forecast date | New F/C date | Closed |
| --- | --- | --- | --- |
| GSU 7EA | 15May10 | 25May10 | Will pour when crane moves after setting unit 100 turbine generator |
| Balance of FDN drawings | 25May10 | 3Jun10 | No date, delivery impacts payment milestones |
| Treated Fuel Tank updated drawings | 29May10 | 1Jun10 | To prepare quote for moving |
| U/G piping | 5May10 | 28May10 | comments |
| GSU 7FA | 21May10 | 2 Jun10 | Not critical |
| Duct Bank | 17May | 28 June 10 |  |
| Design essentially complete | 31 May | No forecast date | No forecast date |

    - A spread sheet of all the pending drawing issues noted here is being consolidated; these issues will be captured for both sites.

  - ISSUED DRAWINGS:

Red lined light foundation drawings and sent an e-mail to Luis

11. PICTURES:

Photo 1: 7EA (unit 100) anchor bolt issue, must cut bolt to allow nut to be installed

Photo 2: 7EA (unit 100) GSU core drilling for gen enclosure

Photo 3: Site of HV excavation.  Excavation spoils to be removed approximately 1500 M3 no change need approval of CO to Derwick

Photo 5: Oily water separator rebar finished, lack of material for bracing

Photo 6: 7FA Stack and Silencer foundation and rebar