CVG SIDOR POWER PROJECT SITE “B”

DATE: 08 May 2010, Saturday PROJECT #: 410-3203 SITE MANAGER: Cole Franklin

- TEMPERATURE:  84 F

- RANGE: 75 to 92

- SITE CONDITIONS: Partly Cloudy and a Light Breeze

- PERSONNEL ON SITE:

- CONSTRUCTION SUPPORT:

William Lugo - Projectl Manager (A&B)

Cole Franklin - Site Manager

Ted York - Const Manager

Melinda Siros - Doc Control

Dennis Maloney - T/O Coord (Safety)

Ysrin Gomez – Local Safety

Jason Bird - TA/7EA (A&B)

Hal Schulmeyer - Civil Supv

Edward Dubois – QA/QC (A&B)

MATERIAL SUPPORT

Paul Oliva – Materials (R&R)                                  Jose Angel – Materials

Herman Floras – Materials (“A” Training)

- ADMIN SUPPORT:

- Daniel Febres – Logistics

Paulo Gomez - Admin

Patricia Munos - Admin

Skeila Garcia - Translator

Mark Hanks - Electrical Supv

Rafael Soriano - QA/QC (A&B)

Kyle Roskan - Civil Supt

Keith McMurray - Scheduler

Felix Martinez - QA/QC (A&B)

- SUBCONTRACTOR PERSONNEL:

General Superintendant        1

Foremen			   1

Electricians                            0

Operators                              0                         Surveyor                                1

Carpenters                           10                          Surveyor Helper                    2

Oiler Helper                           0

Crane Operator                     0                           Laborers                                7

Truck Drivers                         0

Concrete Finishers		   0

Oilers                                     0

Plumbers                               0                        Iron Workers			  10

Helpers                                  2

Welders                                 1			Total:				  35

- Note: Contractor ended shift at 1500 hours.

- GENERAL ITEMS:

  - Luis Acevedo from IDG stated in the meeting, 5-3-10, that he is unable to provide any forecast dates at this time do to a redesign of the site which is in process. We are getting close to a work stoppage due to the lack of IFC design drawings. We are in discussions with EDG on this issue.

  - Safety issues are also covered with the contractor in the bi-weekly meeting.

  - GE TA is scheduled to arrive at site on 5-17-10 to perform inventory on 7FA. Currently no bill of material exists on site.

- CLIENT ISSUES/CONCERN:

  - Progress on Foundation 7EA and 7FA.

  - Underground piping and duct bank drawings scheduled for review 31 Mar 10.

  - Waiting on trash bins from Sidor for site lay down area. We are going to discuss this with Sidor.

  - Christoph is preparing a drawing showing locations for potable water and fire water tie-in points.

- CIVIL:

  - Coinserman, Ca subcontractor has trailers set on location. Trailers are ready for A/C, furniture, internet and cleaning.

- CONCRETE FOUNDATIONS:

  - Continued installation of rebar and forms for 7EA foundation.

  - Continued installation of embedded conduits for 7EA foundation.

  - Continued installation of anchor bolts for 7EA foundation.

  - Completed installing drain lines for 7EA foundation. Provided copies of welding information in bi-weekly meeting, 5-06-10. Pro Energy requested weld numbers to be added to the weld map and to x-ray a weld to provide qualification for the welder.

  - Contractor will begin to remobilize personnel and equipment on Monday.

  - Concrete pour for 7FA mud mat scheduled for Monday.

  - Received 7EA blower anchor bolts.

  - Replacement 7EA Unisorb base plates did not arrive with pre-pour items that were received on 5-7-10.

  - Installed center pedestal concrete forms for Treated Fuel Tank per revision 1 of drawing 10-021. Received Foundation Plan for Treated Fuel Tank Rev 2 reducing the center pedestal size, rebar required and depth of fill is deeper than Revision 1. Tank rebar is fabricated and forms installed with fill per revision 1. EDC was informed, performed immediate review and fix the drawing.

- MECHANICAL:

  - Completed sketch for the 7EA generator replacement jib base plate. Emailed sketch to Tom Koontz to have a replacement plate fabricated and shipped to site.

  - Making arrangements to adjust 7EA generator to allow removal of damaged jib plate.

- PIPING:

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS: - Waiting on welding procedures from Consorcio Megavatio for 7EA stack repairs. Provided company name that can help them assemble a QA plan and welding procedures. They stated in the biweekly meeting yesterday that they would put them together. Forecast 5-14-2010 for submittal. - Waiting on estimates from Consorcio Megavatio for balance of foundation installations. Forecast 5-8-2010 - The internet provider is scheduled to begin installation on 5-11-10 for site trailers.

- CRITICAL AREAS OF CONCERN: Consorcio Megavatio will begin remobilizing personnel and equipment on Monday. Changes in designs are impacting project progress/completion.

  - SAFETY:

    - Consorcio Megavatio will install a bulletin board on site. Forecast 5-14-2010.

    - Weekly safety meetings with Sidor, Concorcio and Pro Energy are scheduled for every Tuesday at 1000 hours at the Plant “A” contractor’s office.

    - Site safety meetings are scheduled for every Monday at 0700 hours at the Plant “A” contractor’s office.

  - OUTSTANDING DRAWINGS:

    - GA, plot plans and foundation drawings all need to be on the same foot print.

    - Duct Bank. Forecast 5-11-2010

    - Underground piping. Forecast 5-5-2010

    - Storm Drain. Forecast 5-12-10

    - 7FA foundations Forecast. 5-11-2010

    - 7FA GSU foundation detailed drawings.

    - Gas Compressor detailed drawings.

    - Balance of foundation details. 5-25 -2010

    - Informed EDG that the water seal shown on the foundation drawings is not available here in country. They are reviewing this issue.

    - Grounding Plan ( Drawings are under review and PES has some issues and concerns with the designs).

Note: Email sent by Cole Franklin to Mike Holland on 4-30-10 regarding priorities and needs. Luis Acevedo forwarded email from Mike Holland with forecast dates and items requiring equipment information. Pro Energy is reviewing the EDG drawing log with what has been issued to the site. Results will be issued upon completion.

  - ISSUED DRAWINGS:

    - Foundation Plan for Treated Fuel Tank Rev 2 reducing the center pedestal size, rebar required and depth of fill is deeper than Revision 1. Tank rebar is fabricated and forms installed with fill per revision 1. EDG immediately reviewed and said we are fine. They will fix the drawing.

- PICTURES:

- Picture 1: Continuing on 7EA Foundation.

- Picture 2: Fabricating Embed Supports for 7EA Foundation.

- Picture 3: Forms Installed and Ready for Mud Mat for 7FA Foundation.

- Picture 4: Forms Set for Center Pedestal of Treated Fuel Tank.

- Picture 5: Received 7EA Blower Anchor Bolts.