CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 1 May 2010 Saturday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

Elizabeth Cornett – Doc.Cont            Clarence Cornett – Civil Supt.

Kyle Roskan – Civil Supt                    David Sewell -  Const. Mgr                Felix Martenz – QA/QC

John Little – Mat’l Control

Jay Riley – Elect. Supt.

William Lugo – Project Manager

Scott Kirk – Civil Supt.                       Edward Blacke - Safety Mgr 	                       James Siros – Mech. Supt 		    Catherine Cameron – Inventory        	    Daniel Meyer – Mat’l Control             Mark Hanks – Electrical                    Teresa Bretherick - Scheduler

Patrick Melody – Site Manager

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                   4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                    1

Master Operator                    4                               Master Mechanic                   1

Survey Assistant                   2                               Concrete Finsher                 14

Surveyor                               2                                Warehouse  Assist                2

Oiler                                      1                                Total                                 184

- CLIENT ISSUES/CONCERN:

1.1.1   Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Relocation of overhead lines at tank area have not been relocated

    - Fire line connection and design.

    - Venezuelan Labor Day Weekend – 1 May 2010 – No Work

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

  - OUTSTANDING DRAWINGS:

    - Grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Foundation drawing 15 kV switchgear at GT 100 & 200

  - DRAWINGS ISSUED:

60-001 thru 60-126

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

- MECHANICAL:

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

8	PICTURES:

GT 100 -  Complete GT Erection