CVG SIDOR POWER PROJECT SITE “B”

DATE: 10 May 2010, Monday PROJECT #: 410-3203 SITE MANAGER: Cole Franklin

TEMPERATURE:  86 F

RANGE: 74 to 89

SITE CONDITIONS: Partly Cloudy and a Light Breeze

PERSONNEL ON SITE:

CONSTRUCTION SUPPORT:

William Lugo - Project Manager (A&B)

Cole Franklin - Site Manager

Ted York - Const Manager

Melinda Siros - Doc Control

Dennis Maloney - T/O Coord & Safety

Ysrin Gomez – Local Safety

Jason Bird - TA/7EA (A&B)

Hal Schulmeyer - Civil Supv

Edward Dubois – QA/QC (A&B)

MATERIAL SUPPORT:

Paul Oliva – Materials (R&R)                                  Jose Angel – Materials

Herman Floras – Materials (“A” Training)

ADMIN SUPPORT:

Daniel Febres – Logistics

Paulo Gomez - Admin

Patricia Munos - Admin

Skeila Garcia - Translator

Mark Hanks - Electrical Supt

Rafael Soriano - QA/QC (A&B)

Kyle Roskan - Civil Supt

Keith McMurray - Scheduler

Felix Martinez - QA/QC (A&B)

SUBCONTRACTOR PERSONNEL:

General Superintendant        1

Foremen			   2

Electricians                            2

Operators                              0                         Surveyor                                1

Carpenters                           14                          Surveyor Helper                    2

Oiler Helper                           1

Crane Operator                     0                           Laborers                                4

Truck Drivers                         0

Concrete Finishers		   0

Oilers                                     1

Plumbers                               2                        Iron Workers			  14

Helpers                                  2

Welders                                 1			Total:				  47

- GENERAL ITEMS:

  - Luis Acevedo from IDG stated in the meeting, 5-3-10, that he is unable to provide any forecast dates at this time do to a redesign of the site which is in process. We are getting close to a work stoppage due to the lack of IFC design drawings. We are in discussions with EDG on this issue.

  - Safety issues are also covered with the contractor in the bi-weekly meeting.

  - GE TA arrived one week early at site today to perform inventory on 7FA. We were able to obtain the additional support from Sidor without the normal advanced request. Extended hours to 1730 will not start till tomorrow due to the late notification.

  - Design progress continues to be an issue. The contractor can be doing a lot more if design for underground and other foundations were available.

- CLIENT ISSUES/CONCERN:

  - Progress on Foundation 7EA and 7FA.

  - Underground piping and duct bank drawings scheduled for review 31 Mar 10.

  - Waiting on trash bins from Sidor for site lay down area. We are going to discuss this with Sidor.

  - Christoph is preparing a drawing showing locations for potable water and fire water tie-in points.

- CIVIL:

  - Subcontractors are installing power and sewage treatment for site trailers. Office furniture was delivered today.

- CONCRETE FOUNDATIONS:

  - Continued installation of rebar and forms for 7EA foundation.

  - Completed installation of embedded conduits for 7EA foundation.

  - Continued installation of anchor bolts for 7EA foundation.

  - Pro Energy requested weld numbers to be added to the weld map for 7EA drain lines, 5-6-10.

  - Concrete pour for 7FA mud mat was postponed from the morning till 1400 hours by Sidor. Pour for 1400 hours was postponed due to the lack of cement for today and tomorrow at approximately 1530 hours. At approximately 1545 we were notified that there is now cement. Concrete arrived at site at 1650 hours.

  - Replacement 7EA Unisorb base plates are being held by customs due to a discrepancy in shipping documents, 5-7-10.

  - Installing rebar for center pedestal for Treated Fuel Tank. Concrete Pour for tomorrow was postponed due to the lack of cement at approximately 1530 hours. At 1545 hours Sidor has cement and will now support the pour tomorrow.

- MECHANICAL:

  - Completed sketch for the 7EA generator replacement jib base plate, 5-8-10. Emailed sketch to Tom Koontz to have a replacement plate fabricated and shipped to site, 5-08-10.

  - Making arrangements to adjust 7EA generator to allow removal of damaged jib plate.

- PIPING:

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS: - Waiting on welding procedures from Consorcio Megavatio for 7EA stack repairs. Provided company name that can help them assemble a QA plan and welding procedures. They stated in the biweekly meeting yesterday that they would put them together. Forecast 5-14-10 for submittal. - Waiting on estimates from Consorcio Megavatio for balance of foundation installations. Forecast 5-8-10 - The internet provider is scheduled to begin installation on 5-11-10 for site trailers.

- CRITICAL AREAS OF CONCERN: Changes in designs are impacting project progress/completion. Shortage of cement is affecting the scheduling of foundations.

  - SAFETY:

    - Consorcio Megavatio will install a bulletin board on site. Forecast 5-14-2010.

    - Weekly safety meetings with Sidor, Concorcio and Pro Energy are scheduled for every Tuesday at 1000 hours at the Plant “A” contractor’s office.

    - Site safety meetings are scheduled for every Monday at 0700 hours at the Plant “A” contractor’s office.

  - OUTSTANDING DRAWINGS:

    - GA, plot plans and foundation drawings all need to be on the same foot print.

    - Duct Bank. Forecast 5-11-2010

    - Underground piping. Forecast 5-5-2010

    - Storm Drain. Forecast 5-12-10

    - 7FA foundations Forecast. 5-11-2010

    - 7FA GSU foundation detailed drawings.

    - Gas Compressor detailed drawings.

    - Balance of foundation details. 5-25 -2010

    - Informed EDG that the water seal shown on the foundation drawings is not available here in country. They are reviewing this issue.

    - Grounding Plan ( Drawings are under review and PES has some issues and concerns with the designs).

Note: Email sent by Cole Franklin to Mike Holland on 4-30-10 regarding priorities and needs. Luis Acevedo forwarded email from Mike Holland with forecast dates and items requiring equipment information. Pro Energy is reviewing the EDG drawing log with what has been issued to the site. Results have been issued.

  - ISSUED DRAWINGS:

    - Foundation Plan for Treated Fuel Tank Rev 3 reflects the current dimensions, rebar and the correct back fill depth.

- PICTURES:

Picture 1: Completing Conduit Installation for 7EA Foundation.

Picture 2: Setting Anchors for 7EA Foundation.

Picture 3: Installing Electric Power and Sewage Treatment for Site Trailers.

Picture 4: Installing Rebar for Center Pedestal of Treated Fuel Tank.

Picture 5: Sidor Replaced Leaking Elbow of Potable Water Line.