CVG SIDOR POWER PROJECT SITE “A”

DATE:  19 May 2010, Wednesday

PROJECT #: 410-3202

LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela

SITE MANAGER: Patrick Melody

TEMPERATURE:  90 F

RANGE: 90 to 95 F

SITE CONDITIONS: Sunny and humid

PERSONNEL ON SITE:

| Hooper, Robert | Interim Proj. Director | Jason, Bird | Tech Adviser 7EA |
| --- | --- | --- | --- |
| Melody, Patrick | Site Manager |  |  |
| Blacke, Edward | Safety Manager | Horn, Ryan | Tool Room Super. |
|  |  | Little, John | Material Coordinator |
| Bretherick, Teresa | Scheduler | Daniels, Julio | Tool Room (Local) |
|  |  | Izquierdo, Weiser | Mat'l. Handler (Local) |
|  |  | Lopez Juan Carlos | Mat'l. Handler (Local) |
| Lance, Trottie | I & C | Ortega, Ramon | Tool Room (Local) |
| Archuleta, Pete | Piping Supt. |  |  |
| Riley, Jasper | Electrical Supt |  |  |
|  |  | Leccia, Karina | Admin Assist |
| Soriano, Rafael | QA/QC Manager | Mendez, Kenia | Admin Assist |
| Thomas, Hankins | QA/QC Manager | Zambrano Natalia | Translator |

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                   4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                    1

Master Operator                    4                               Master Mechanic                   1

Survey Assistant                   2                               Concrete Finsher                 14

Surveyor                               2                                Warehouse  Assist                2

Oiler                                      1                                Total                                 184

- GENERAL ITEMS

    - Design and procurement for the project needs to be completed as soon as possible to support current project schedule.

- CLIENT ISSUES/CONCERNS:

    - Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Overhead lines are preventing excavation of Raw Water Tank and Fuel Storage Tank. Sidor had requested PES to employee an electrical contractor to expedite removal of overhead lines. Sidor will sign a change order for this scope of work. Sidor has secured pricing and established a scope of work with the subcontractor.

    - Fire line connection and design meeting was held with Sidor. Sidor has been requested to provide complete Water Flow Test Data including Static/Residual pressure. Information is required to complete design and procurement activities.

    - SIDOR has provided direction for acceptance / rejection of concrete placements in accordance with PDVSA Concreto.  PES, Wallace, and EDG to review and respond

    - Sidor failed to demobilize 650 ton crane at GT 300 as scheduled. Removal of crane is ongoing.

- CIVIL:

    - GT 100 Excavate duct bank MH 2 to GT 200

    - GT 100 Form/Rebar conduit rack footings

    - GT 200 Form/Rebar pipe rack foundations

    - Back fill Duct banks and structures

    - GT 200 Form/Rebar GSU blast wall

    - GT 300 Form/Rebar GSU blast wall

- CONCRETE FOUNDATIONS:

    - GT 100 Place concrete at cable rack footings

    - GT 200 Place concrete pipe rack piers

    - GT 200 Place concrete pipe rack foundations

    - MH 8 & 9 Forms and Rebar top slab

- MECHANICAL:

    - GT 100 Clean lube oil spools for auxiliary skids

    - GT 300 Exhaust stack weld out

    - Fabricate pipe spools for fire line and raw water line

    - Install concrete expansion anchors for wall installation

    - GT 300 Set walls at generator

    - GT 300 Prep walls for installation

- ELECTRICAL:

    - Install conduit in duct banks

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

    - CPS Schedule development on going. First draft being reviewed by the team.

- CRITICAL AREAS OF CONCERN:

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

    - SAFETY:

      - Develop JSA as needed

      - Inspection of subcontractor power tools.

      - Inspection of motorized equipment prior to usage.

      - Scaffold and trenching inspection is ongoing.

    - OUTSTANDING DRAWINGS:

9.1.2.1	Grounding grid

      - Coordinated underground drawing

      - Design drawings need to be issued

      - Utility Bldg. Layout of electrical equipment.

    - DRAWINGS ISSUED:

8	PICTURES:

Duct Bank Excavation MH 3 to GT 200

GT 300 Erection of Generator Walls

GT 100 Cable Tray Foundations

Offloading Industrial Dolphine