CVG SIDOR POWER PROJECT SITE “B” PROJECT: 410-3203

DATE: 23 April 2010 Friday

TEMPERATURE:  88 F      RANGE: 75 to 90

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager                 Hal Schulmeyer - Civil Supt

Robert James - Safety Mgr                          Gene Phillips - PE Civil - Wallace

Cole Franklin - Site Manager                       Elizabeth Cornett - Doc Control

Ted York - Const Manager                          Dennis Maloney - T/O Coordinator

Felix Martinez - QA/QC                                Mark Hanks - Electrical Supt

Mike Montgomery - QA/QC                          Kyle Roskan - Civil Supt

Daniel Meyer - Materials                               Wilson Confrera - Materials

Ysrin Gomez - Safety

Jason Bird - TA/7EA

SUBCONTRACTOR PERSONNEL:

General Superintendant        1

Foremen			   2

Electricians                            0

Operators                              4                           Surveyor                                1

Carpenters                           12                           Surveyor Helper                    2

Oiler Helper                           1

Crane Operator                     0                           Laborers                                4

Truck Drivers                         5   Concrete Finishers		   0

Oilers                                     1

Plumbers                               0                        Iron Workers			 12

Helpers                                  0

Welders                                 0

TOTAL:    45

- CLIENT ISSUES/CONCERN:

  - Progress Foundations 7EA & 7FA

  - Weather protection for material and equipment in lay down yard Sidor provided Tarps, not installed.

  - Geo tech report (addendum) for 7FA foundations.

  - Underground piping and duct bank drawings scheduled for review 31 Mar 10.

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Trash Bins and Barrels to be supplied by Sidor.

    - Consortium needs to provide a first aid kit.

    - Pro Energy shipped two medical kits for use at site offices.

    - Consortium is going to setup and First Aid office on site.

  - OUTSTANDING DRAWINGS:

    - Plant grounding grid

    - Duct bank

    - Underground piping / storm drain system

    - 7FA foundations

    - Balance of plant foundation details

  - DRAWINGS ISSUED:

    - Later

- SCHEDULED ITEMS: - Still waiting on geo tech report addendum and letter from Consortium regarding excavation of 7FA depth change. - Inventory of 7EA material and equipment is in process. Waiting for forecast date of GE TA to do inventory; and custom clearance for the 7FA materials. Currently o bill of material exists on site for 7FA.It has been requested from GE. - Unisorb has completed fabrication of replacement plates and are shipping. Plant “B” logistics is handling the shipping. - 7EA exhaust stack and base, reviewing plan for repairs and reassembly. Still waiting on welding procedures from contractor. - Site trailers/office current reforecast for delivery is on April 27, 2010. Steps will be supplied with the trailers. - Waiting on proposals of the site trailer location support from Consortio Megavatio (main contractor currently at site), and Consorcio Convica (another civil contractor). - Waiting on review by Christoph of Sidor for Fire Water tie-ins, Potable Water tie-ins and depths of duct banks and utilities for routing of storm drains. - Had meeting today with concrete suppliers, Sidor (Christoph), Derwick Representative and Proenergy Management for Plant A and B. Meeting was to get everyone on the same page for scheduling, supply and demand for our projects.

- CIVIL:

  - Consortium is prepared to pour mud mat for 7EA. No concrete was available.

  - Waiting on soil tests results for 7FA foundation excavation.

  - Continuing 7FA foundation excavation for design change, drawing revision.

  - Continuing excavation of Treated Fuel Tank. Requested soils test and was informed that the compaction tester was broken, sent out for repair and it is the only one.

  - Site trailer location was laid out.

- MECHANICAL:

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

- PICTURES:

Picture 1: 7EA Prepared for Additional Mud Mat. No concrete available.

Picture 2: Waiting for Soils Testing of Treated Fuel Tank Foundation Excavation. No Test Equipment is Available.

Picture 3: Continuing With Excavation for 7FA Foundation Due to Design Change.