CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 24 April 2010 Saturday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager        Scott Kirk – Civil Supt.

Edward Blacke - Safety Mgr.            Clarence Cornett – Civil Supt.

James Siros – Mech. Supt                 Mike Montgomery - QA/QC

Patrick Melody – Site Manager          Elizabeth Cornett – Doc.Cont

Clarence Cornett – Civil Supt.            Kyle Roskan – Civil Supt

David Sewell -  Const. Mgr                 Felix Martenz – QA/QC

Mike Montgomery QA/QC                  John Little – Mat’l Control

Wilson Contreras – Tool Super          Paul Oliva – Mat’l Control

David Jackson -  Mat’l Control            Jason Bird – Tech Assit

Michael Herasimchuk – I/C                Catherine Cameron – Inventory         Dennis Maloney – Turnnover

Daniel Meyer – Mat’l Control

Mark Hanks - Electrical

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                  4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                   1

Master Operator                    4                               Master Mechanic                  1

Survey Assistant                   2                               Concrete Finsher                14

Surveyor                               2                                Warehouse  Assist               2

Oiler                                     1                            Total                                 184

- CLIENT ISSUES/CONCERN:

1.1.1   Location of existing gas line between 7EA and Control Building

    - Relocation of overhead lines at tank area

    - 7EA foundation progress. The contractor has slowed down

    - Fire line connection and design.

    - Unload GT 200 from ship complete

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

    - Advise staff of clinic location and access protocol.

  - OUTSTANDING DRAWINGS:

    - Plant grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Pre Engineered Metal Building erection drawings

  - DRAWINGS ISSUED:

    - To be added later

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

  - GT 100 – Concrete placement auxiliary foundation

  - GT 200 – Inventory GT 200 shipment

  - GT 200 – Set Gen/Tub enclosure on foundation

  - GT 300 – 7EA foundation install embedded ítems

  - GT 300 – 7EA Install top mat reinforcing

  - Duct Banks – FRP MH 2, 3, 4, & 6

  - Gas Compressor Foundation – Concrete placement

  - Office trailer installation complete

  - GT 200 - Excavate for duct bank

- MECHANICAL:

15.2  GT 100 -  Subassembly of air filter house frame and house.

15.3  GT 100 -  Install bolts at roof pleneums

15.3  GT 100 – Install turbine exhaust fans and hoods

- ELECTRICAL:

13.1 Conduit installation at MH 2, 3, 5, & 7

13.2 Site Office Trailer Installation

- PICTURES:

Gas Compressor Foundation

GT 200 Turbine/Generator Enclosure

.

GT 100 Air Filter House Frame