|  |
| --- |
| **CVG SIDOR POWER PROJECT SITE “B”**  **PROJECT: 410-3203** |
| **DATE: 24 April 2010 Saturday** |

**TEMPERATURE: 81 F RANGE: 76 to 90**

**SITE CONDITIONS: Cloudy, (There was a shower yesterday afternoon)**

**PERSONNEL ON SITE:**

William Lugo - Project Manager Hal Schulmeyer - Civil Supt

Robert James - Safety Mgr Gene Phillips - PE Civil - Wallace

Cole Franklin - Site Manager Elizabeth Cornett - Doc Control

Ted York - Const Manager Dennis Maloney - T/O Coordinator

Felix Martinez - QA/QC Mark Hanks - Electrical Supt

Mike Montgomery - QA/QC Kyle Roskan - Civil Supt

Daniel Meyer - Materials Wilson Confrera - Materials

Ysrin Gomez - Safety

Jason Bird - TA/7EA

**SUBCONTRACTOR PERSONNEL:**

General Superintendant 1

Foremen 3

Electricians 0

Operators 4 Surveyor 1

Carpenters 8 Surveyor Helper 2

Oiler Helper 1

Crane Operator 0 Laborers 8

Truck Drivers 2 Concrete Finishers 4

Oilers 1

Plumbers 0 Iron Workers 8

Helpers 0

Welders 0

**TOTAL:**  43

1. **CLIENT ISSUES/CONCERN:** 
   1. Progress Foundation 7EA & 7FA
   2. Weather protection for material and equipment in lay down yard Sidor provided Tarps, not installed.
   3. Geo tech report addendum for 7FA foundations.
   4. Underground piping and duct bank drawings scheduled for review 31 Mar 10.
   5. Running Fire Water and Potable Water to site per red lined drawing.
2. **CRITICAL AREAS OF CONCERN:**
   1. **SAFETY:**
      1. Trash Bins and Barrels to be supplied by Sidor.
      2. Consortium needs to provide a first aid kit.
      3. Pro Energy shipped two medical kits for use at site offices.
      4. Consortium is going to setup and First Aid office on site.
   2. **OUTSTANDING DRAWINGS:** 
      1. Grounding grid
      2. Duct Bank
      3. Underground piping / storm drain system
      4. 7FA foundations
      5. Balance BOP foundation details
   3. **DRAWINGS ISSUED:**
      1. Later

|  |
| --- |
| 1. **SCHEDULED ITEMS:**    1. Still waiting on geo tech report addendum and letter from Consortium regarding excavation of 7FA depth change.    2. Inventory of 7EA material and equipment is in process. Waiting for forecast date of GE TA to do inventory; and custom clearance for the 7FA materials. Currently o bill of material exists on site for 7FA.It has been requested from GE.    3. Unisorb has completed fabrication of replacement plates and are shipping. Plant “B” logistics is handling the shipping.    4. 7EA exhaust stack and base, reviewing plan for repairs and reassembly. Still waiting on welding procedures from contractor.    5. Site trailers/office current reforecast for delivery is on April 27, 2010. Steps will be supplied with the trailers.    6. Waiting on proposal of the site trailer installation support from Consortium.    7. Received proposal from Consorcio Convica for site trailer installation support and reviewed. Awarding concrete pad for trailers today.    8. Waiting on review by Christoph of Sidor for Fire Water tie-ins, Potable Water tie-ins and depths of duct banks and utilities for routing of storm drains.    9. Site letter issued to Consortium Megavatio about outstanding issues. |

1. **CIVIL:**
   1. Consortium poured mud mat for 7EA.
   2. Waiting on soil tests results for 7FA foundation excavation. Consortium is forecasting issuing the letter on the results Monday, April 26, 2010. ProEnergy has stated that if it is not here, to continue digging the same as was performed for the 7EA.
   3. Completed 7FA foundation excavation extension because of design change, drawing revision.
   4. Waiting on soils tests of Treated Fuel Tank. Equipment is forecast to be repaired and recalibrated on Monday. It will not be required if the soils test letter for the 7FA is received Monday and approved.
2. **MECHANICAL:**
3. **ELECTRICAL:**
4. **INSTRUMENTATION AND CONTROLS:**
5. **PICTURES:**



**Picture 1: 7EA Pouring Mud Mat.**



**Picture 2: Continuing Pouring 7EA Mud Mat.**



**Picture 3: Pumping Two Trucks at a Time for 7EA Foundation Mud Mat.**



**Picture 4: 7EA Mud Mat Completed.**



**Picture 5: Completed 7FA Excavation Extension.**



**Picture 6: Modifying 7FA Entrance Ramp to Excavation.**