CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 25 April 2010 Sunday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager

Scott Kirk – Civil Supt.

Edward Blacke - Safety Mgr.            Clarence Cornett – Civil Supt.

James Siros – Mech. Supt

Patrick Melody – Site Manager          Elizabeth Cornett – Doc.Cont

Kyle Roskan – Civil Supt

David Sewell -  Const. Mgr

John Little – Mat’l Control

Wilson Contreras – Tool Super          David Jackson -  Mat’l Control            Jason Bird – Tech Assit

Dennis Maloney – Turnnover

Mark Hanks - Electrical

SUBCONTRACTOR PERSONNEL:

Mechanics                    4

Crane Operator            2

Total                                             6

- CLIENT ISSUES/CONCERN:

  - Location of existing gas line between 7EA and Control Building

  - Relocation of overhead lines at tank area

  - Fire line connection and design

  - Progress of 7EA foundation. The contractor has slowed down

  - Crane rigging crews for SIDOR were not furnished as requested and as agreed.

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

    - Advise staff of clinic location and access protocol.

  - OUTSTANDING DRAWINGS:

    - Grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Pre Engineered Metal Building erection drawings

  - DRAWINGS ISSUED:

    - List to be added later

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

3.1 GT 100 – Installation of bracing for air fliter house supports

- MECHANICAL:

4.1  GT 200 – Prep/Removal for generator installation

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

- PICTURES:

GT 200 Turbine/Generator Enclosure

.

GT 100 Air Filter House Frame