CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 26 April 2010 Monday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager        Scott Kirk – Civil Supt.

Edward Blacke - Safety Mgr.            Clarence Cornett – Civil Supt.

James Siros – Mech. Supt                 Mike Montgomery - QA/QC

Patrick Melody – Site Manager          Elizabeth Cornett – Doc.Cont

Clarence Cornett – Civil Supt.            Kyle Roskan – Civil Supt

David Sewell -  Const. Mgr                 Felix Martenz – QA/QC

Mike Montgomery QA/QC                  John Little – Mat’l Control

Wilson Contreras – Tool Super          Paul Oliva – Mat’l Control

David Jackson -  Mat’l Control            Jason Bird – Tech Assit

Michael Herasimchuk – I/C                Catherine Cameron – Inventory         Dennis Maloney – Turnnover

Daniel Meyer – Mat’l Control

Mark Hanks - Electrical

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                  4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                   1

Master Operator                    4                               Master Mechanic                  1

Survey Assistant                   2                               Concrete Finsher                14

Surveyor                               2                                Warehouse  Assist               2

Oiler                                     1                            Total                                 184

- CLIENT ISSUES/CONCERN:

1.1.1   Location of existing gas line between 7EA and Control Building

    - Relocation of overhead lines at tank area

    - Fire line connection and design.

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

    - Superintendant weekly safety meeting

  - OUTSTANDING DRAWINGS:

    - Grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Pre Engineered Metal Building erection drawings

  - DRAWINGS ISSUED:

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

  - GT 100 -  Excavate duct bank GT 100 to MH 6

  - GT 300 Install embedded items 7EA

  - Excavate ductbank from  MH 6 to Utility Bldg.

  - Excavate MH 9

  - Concrete placement MH 4, slab

  - Conrete placement  Duct bank closures at MH 7 east; MH 5 east, west, north;

- MECHANICAL:

5.1 GT 100 – Subassembly of air filter house.

5.2 GT 200 –Removal generator rooof & wall

5.3 GT 200 – Prep Generator base/ install base plates

- ELECTRICAL:

6.1 Install conduit in duct bank

- INSTRUMENTATION AND CONTROLS:

8	PICTURES: