|  |
| --- |
| **CVG SIDOR POWER PROJECT SITE “A”** |
|  |

**DATE: 28 May 2010, Friday**

**PROJECT #: 410-3202**

**LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela**

**SITE MANAGER: Patrick Melody**

**TEMPERATURE: 88 F**

**RANGE: 85 to 95 F**

**SITE CONDITIONS: Afternoon rain 5 hours**

**PERSONNEL ON SITE:**

|  |  |  |  |
| --- | --- | --- | --- |
| Lugo, Bill | Project Director | Jason Bird | Tech Adviser 7EA |
|  |  |  |  |
| Melody Patrick | Site Manager | Ryan Horn | Tool Room Super. |
| Blacke Edward | Safety Manager | Little John | Material Coordinator |
| James Siros | Mechanical Supt. | Daniels Julio | Tool Room (Local) |
| Archuleta Pete | Piping Supt. | Izquierdo Weiser | Mat'l. Handler (Local) |
| Riley Jasper | Electrical Supt | Lopez Juan Carlos | Mat'l. Handler (Local) |
| Soriano Rafael | QA/QC Manager | Ortega Ramon | Tool Room (Local) |
|  |  |  |  |
|  |  | Leccia Karina | Admin Assist |
|  |  | Rojas, Moises | Local Procurement |
|  |  | Zambrano Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |
|  |  |  |  |
|  |  |  |  |

**SUBCONTRACTOR PERSONNEL:**

Operators 11 Mechanical Assit. 4

Carpenter 29 Electrician 3

Laborers 28 Helper 57

Truck Driver 4 Operator Crane 2

Welders 5 Plumber 2

Oilers 1 Mechanic Heavy 1

Master Operator 4 Master Mechanic 1

Survey Assistant 2 Concrete Finisher 14

Surveyor 2 Warehouse Assist 2

Oiler 1 **Total 174**

1. **GENERAL ITEMS**
   * 1. Design and procurement for the project needs to be completed as soon as possible to support current project schedule.
2. **CLIENT ISSUES/CONCERNS:** 
   * 1. Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.
     2. Overhead lines are preventing excavation of Raw Water Tank and Fuel Storage Tank. Sidor had requested PES to employee an electrical contractor to expedite removal of overhead lines. A PO has been written by PES to Scalia for to expedite removal of overhead lines.
     3. SIDOR has provided direction for acceptance / rejection of concrete placements in accordance with PDVSA Concrete. 38 c will be the maximum temp for concrete for non massive structural concrete placements. Massive concrete placement will be in accordance with ACI requirements utilizing ice in the mix design.
     4. Material from the Industrial dawn has been detained at the port by Customs.
3. **CIVIL:**
   * 1. GT 100 to MH 7 Duct bank backfill
     2. GT 200 to MH 2 Duct bank backfill
     3. GT 300 Strip forms at GSU blast wall
     4. GT 300 Exhaust stack foundation set anchor bolts template
     5. Back fill structures
     6. Excavate from MH 8 to Water Treatment Bldg
     7. SWBD to TA 3 Duct bank concrete placement
4. **CONCRETE FOUNDATIONS:**
   * 1. Utility Bldg Place footing concrete placement
5. **MECHANICAL:**
   * 1. Assist Material control in Identifying material
     2. Fabricate pipe spools for fire line and raw water line
     3. GT 100 Install auxiliary skid piping
     4. GT 200 Install for auxiliary skid
     5. GT 200 Uncrate CO 2 skid
     6. GT 300 Exhaust stack weld out
     7. GT 300 Install Transition duct from turbine to filter inlet
     8. GT 300 Inspect blower motors for damage
     9. GT 300 Install baffles for 2nd section of exhaust stack
     10. GT 300 install cooling water piping for aux skid
     11. Gas compressor clean gear boxes
6. **ELECTRICAL:**
   * 1. Install conduit in duct banks
     2. Unload GT 300 GSU Transformer
7. **INSTRUMENTATION AND CONTROLS:**
8. **SCHEDULED ITEMS:** 
   * 1. CPS Schedule development on going.
9. **CRITICAL AREAS OF CONCERN:**

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

* + 1. **SAFETY:**
       1. Develop JSA as needed
       2. Inspection of subcontractor power tools.
       3. Inspection of motorized equipment prior to usage.
       4. Scaffold and trenching inspections ongoing.
    2. **OUTSTANDING DRAWINGS:**

9.1.2.1 Grounding grid

* + - 1. Coordinated underground drawing
      2. Design drawings need to be issued
      3. Utility Bldg. electrical panel layout
    1. **DRAWINGS ISSUED:**

**10. PICTURES:**

****

**GT 300 7EA Erection**

****

**GT 300 Exhaust Stack Baffles**