| EPC | Weekly Report 29May 2010 |  |
| --- | --- | --- |
| Date: 29May 2010 | Project: Sidor Site A, Puerto Ordaz Venezuela |  |
| Written By: Patrick Melody | ProEnergy EPC Project Mgr ProEnergy Site Manager | William Lugo Patrick Melody |

Table of Contents

1. Executive Summary

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary .

This report provide an overview of the project activities for the week ending 15 May 2010 for the engineering, procurement, and the construction activities on site.

  - Safety & Regulatory Compliance

    - Develop Job Safety Analysis as required.

    - Inspection of motorized equipment prior to usage.

    - Inspection of subcontractor power tools.

  - Personnel/Staffing

| Lugo, Bill | Project Director | Bird, Jason | Tech Adviser 7EA |
| --- | --- | --- | --- |
| Melody, Patrick | Site Manager | Horn, Ryan | Tool Room Super. |
| Blacke, Edward | Safety Manager | Little, John | Mat’l. Coordinator |
| Soriano, Rafael | QA/QC Manager |  |  |
| Siros, James | Mech. Supt. | Daniels, Julio | Tool Room (Local) |
| Archuleta, Pete | Piping Supt. | Izquierdo, Weiser | Mat'l. Handler |
| Riley, Jasper | Electrical Supt | Lopez, Juan Carlos | Mat'l. Handler |
|  |  | Flores, Herman | Tool Room (Local) |
|  |  | Leccia, Karina | Admin Assist |
|  |  | Rojas, Moises | Logistics |
|  |  | Zambrano, Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |

  - Weekly Accomplishments

- GT 100 Complete duct bank MH 7 to GT 100

    - GT 100 Complete cable rack foundations/piers

    - GT 100 Complete placement pipe rack foundations & piers

    - GT 100 Complete install auxiliary skid

    - GT 100 Install auxiliary skid piping

    - GT 200 Complete placement pipe rack footings & piers

    - GT 200 Form/Rebar/Pour cable tray foundations and piers

    - GT 200 Complete install auxiliary skid

    - GT 200 Complete GSU blast wall

    - GT 200 Complete pre alignment

    - GT 200 Complete cable rack foundations/piers

    - GT 200 Form/rebar /pour pipe rack foundation

    - GT 200 Complete duct bank MH 2 to GT 100

    - GT 300 Complete GSU blast wall

    - GT 300 Erect structural columns for sound walls

    - GT 300 Install baffles in Exhaust stack.

    - GT 300 Install EFB piping

    - GT 300 Install generator filter roof panel

    - GT 300 Install accessory enclosure walls

    - GT 300 Set transition to air inlet filter house

    - GT 300 Set forms, reinforcing and anchor bolts stack foundations

    - GT 300 Inspect and service blower motors

    - GT 300 Install cooling water piping

    - GT 300 Unload GSU transformer

    - Utility Bldg. footing concrete placement

    - Install Conduit MH 8 to water treatment building

    - Install Conduit MH 7 to MH 7.

    - Install Conduit SWBD to TA 3

    - Complete black start generator foundation

    - Excavate high voltage duct bank from SWBD to TA4

    - Back fill duct banks and MH’s

    - Fabricate pipe spools for fire protection line

    - Install Hanover gas compressor on foundation

1.4– Scheduling Conflicts

- Development of CPM schedule is ongoing.

  - – Site Managers Commentary and Amplifying Remarks

- Shipments are not being released by customs due to errors in shipping documents. Line items values do not equal the total for the shipment.

- Daily rains and heavy overnight rains are causing delays.

- GT 300 GSU transformer was damaged in shipment. See attached photo.

2 Engineering and Design

2.1 – General Arrangement-

2.2 – Site /Civil /Structural

2.3 – Mechanical

- Fully coordinated underground piping drawings are required.

2.4 – Electrical

    - Additional detail is required to stub up conduit at the location required.

    - Grounding grid drawings are required.

2.5 – Instrumentation

- Ongoing

2.6 – O&M Manuals –

- Ongoing

3 Procurement

3.1 – Purchase Order Requests

- A local vendor list is being developed with the assistance of SIDOR.

- – Equipment & Material Quotations

- Local procurement is hampered by financial restraints

3.3 - Purchase Order –

4 Contracts

4.1 – EPC Contract –

4.2 – Construction Subcontracts –

- A Purchase Order is pending for excavation of underground utilities.

4.3 – Proposal & Quotes

5 Construction

5.1  Schedule

- CPM schedule development is ongoing.

5.2  Equipment Delivery

- Industrial Dawn – 100 boxes/7 containers

- Ocean Titan at Puerto Ordaz pier – Awaiting unloading

-  116 boxes/1 container

5.3  Mechanical

- GT 100 – GT Erection is complete

- GT 200 – GT Erection is complete. Awaiting arrival of turbine for installation.

- GT 300 – GT Erection ongoing

5.4  Electrical

- Installation of Manholes and duct banks is ongoing.

5.5 QA/QC –

- Inspections of concrete placement, excavation, and backfill activities is ongoing.

- SIDOR has provided direction for implementation of PDVESA Concrete specification for non massive concrete placements. Rejected concrete may be used in duct bank placements

6 Startup & Commissioning

- Pending.

7 Startup Mobilization

GT 300 GSU Transformer Shipping Damage

GT 100 Auxiliary Skid

GT 200 Auxiliary Skid

GT 300 Stack Foundation

GT 300 7EA Erection