CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 29 April 2010 Thursday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager       Scott Kirk – Civil Supt.

Edward Blacke - Safety Mgr.            Clarence Cornett – Civil Supt.

James Siros – Mech. Supt                 Mike Montgomery - QA/QC

Patrick Melody – Site Manager          Elizabeth Cornett – Doc.Cont

Clarence Cornett – Civil Supt.            Kyle Roskan – Civil Supt

David Sewell -  Const. Mgr                 Felix Martenz – QA/QC

Mike Montgomery QA/QC                  John Little – Mat’l Control

Wilson Contreras – Tool Super          Paul Oliva – Mat’l Control

David Jackson -  Mat’l Control            Jason Bird – Tech Assit

Michael Herasimchuk – I/C                Catherine Cameron – Inventory

Dennis Maloney – Turnnover

Daniel Meyer – Mat’l Control

Mark Hanks - Electrical

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                  4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                   1

Master Operator                    4                               Master Mechanic                  1

Survey Assistant                   2                               Concrete Finsher                14

Surveyor                               2                                Warehouse  Assist               2

Oiler                                     1                            Total                                 184

- CLIENT ISSUES/CONCERN:

1.1.1   Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Relocation of overhead lines at tank area

    - Fire line connection and design.

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

  - OUTSTANDING DRAWINGS:

    - Grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Pre Engineered Metal Building erection drawings

    - Foundation drawing 15 kV switchgear at GT 100 & 200

  - DRAWINGS ISSUED:

20-051

60-108

60-114

60-117

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

  - GT 100 Install conduit in duct bank GT 100 to MH 6

  - GT 100 Install conduit MH 6 to Utility Bldg, GT 100, 15 kv Sitch

  - GT 300 Complete installation embedded items 7EA

  - MH 4 Concrete placement manhole slab

  - GT 1000 Backfill GSU foundation and duct bank

  - MH 3 Place Flowable Fill

- MECHANICAL:

5.1      GT 100 – Complete Subassembly Air Filter House

5.2.     GT 200 – Installation  Roof Skid

5.3      GT 200 – Install line side cubícales

5.4      GT 200 – Install generator lube oil piping

- ELECTRICAL:

6.1 Install conduit in duct bank

- INSTRUMENTATION AND CONTROLS:

8	PICTURES:

GT 200 Installation Roof Skid

GT 300 – 7EA Preplacement Inspection

GSU 100, 200, 300 and related ductbanks/manholes

Looking West