|  |
| --- |
| **CVG SIDOR POWER PROJECT SITE “B”**  **PROJECT: 410-3203** |
| **DATE: 29 April 2010 Thursday** |

**TEMPERATURE: 86 F RANGE: 74 to 89**

**SITE CONDITIONS:** Sunnyand a light breeze

**PERSONNEL ON SITE:**

William Lugo – Project Manager Hal Schulmeyer - Civil Supt

Robert James - Safety Mgr Gene Phillips - PE Civil - Wallace

Cole Franklin - Site Manager Melinda Siros - Doc Control

Ted York - Const Manager Dennis Maloney - T/O Coordinator

Daniel Febres - Logistics

Keith McMurray - Scheduler

Felix Martinez - QA/QC Mark Hanks - Electrical Supt

Rafael Soriano - QA/QC Kyle Roskan - Civil Supt

Paul Oliva - Materials Wilson Confrera - Materials

Ysrin Gomez - Safety

Jason Bird - TA/7EA

**SUBCONTRACTOR PERSONNEL:**

General Superintendant 1

Foremen 2

Electricians 0

Operators 4 Surveyor 1

Carpenters 14 Surveyor Helper 2

Oiler Helper 1

Crane Operator 0 Laborers 4

Truck Drivers 3

Concrete Finishers 0

Oilers 1

Plumbers 0 Iron Workers 14

Helpers 1

Welders 1

**TOTAL:**  49

1. **CLIENT ISSUES/CONCERN:** 
   1. Progress on Foundation 7EA & 7FA.
   2. Weather protection for material and equipment in lay down yard Sidor provided Tarps, not installed.
   3. Geo tech report addendum for 7FA foundations.
   4. Underground piping and duct bank drawings scheduled for review 31 Mar 10.
   5. Running Fire Water and Potable Water to site per red lined drawing.
   6. Sidor excavated fire water tie-in point at northeast corner of site. Christoph Merle from Sidor is preparing a drawing showing locations for potable water and fire water tie-in points.
2. **CRITICAL AREAS OF CONCERN:**
   1. **SAFETY:**
      1. Trash Bins still haven’t been supplied by Sidor for Lay Down.
      2. Consorcio Megavatio needs to provide a first aid kit.
      3. Consorcio Megavatio is going to setup and First Aid office on site.
      4. Emergency shower and eye wash station is being setup by Consorcio Megavatio.
      5. Consorcio Megavatio will install a bulletin board on site.
      6. Emergency assembly area needs to be established by Consorcio Megavatio.
      7. Hand washing facility for workers is being setup by Consorcio Megavatio.
      8. Equipment needs to be marked with the PPE requirements for operation by Consorcio Megavatio.

Note: Consorcio Megavatio issues were covered in meeting on Tuesday April 27, 2010.

* 1. **OUTSTANDING DRAWINGS:** 
     1. Grounding grid
     2. Duct Bank
     3. Underground piping / storm drain system
     4. 7FA foundations
     5. Balance of foundation details

|  |
| --- |
| 1. **SCHEDULED ITEMS:**    1. Mike Curley with EDG is going to take look at the piping materials and quantities we received for review since we have no design to help verify the quantities are not excessive.    2. Inventory of 7FA material and equipment is in process. Waiting for forecast date of GE TA to do inventory. Currently no bill of material exists on site.    3. Waiting on delivery of replacement 7EA Unisorb base plates and pre-pour items. Plant “B” logistics is handling the shipping.    4. Still waiting on welding procedures from Consorcio Megavatio for 7EA stack repairs. Provided company name that can help them assemble a QA plan and welding procedures.    5. Waiting on estimates from Consorcio Megavatio for balance of foundation installations.    6. Engineering is going to cloud site area drawing to show which foundations that have been issued IFC that are now on hold.    7. Christoph of Sidor is making a drawing to show the locations of the Fire Water and Potable Water tie-ins.    8. Waiting on reply to site letter issued to Consorcio Megavatio about outstanding issues. These have been added to the meeting minutes as well. |

1. **CIVIL:**
   1. Continued installation of rebar and forms for 7EA.
   2. Embeded conduits for 7EA were reported as fabricated and ready for delivery.
   3. Consorcio Megavatio is working on proper documentation for materials and welding for the 7EA drain lines which will be fabricated off site.
   4. Excavation of Oily Water Separator has been completed. Received information from EDG that it is being relocated and this is under discussion. No action to date.
   5. Coinserman, Ca subcontractor continued excavation for water line, installation of the access road and started installation of parking lot.
   6. Balance of trailers for site offices was delivered today. Crane, riggers and rigging is setup for Monday with Sidor for setting trailers on pad.
   7. Continuing compaction tests and installation of structural fill on 7FA.
   8. Continuing compaction tests and installation of structural fill for Treated Fuel Tank.
   9. Rebar was delivered to site for Treated Fuel Tank foundation.
2. **MECHANICAL:**
3. **PIPING:**
4. **ELECTRICAL:**
5. **INSTRUMENTATION AND CONTROLS:**
6. **PICTURES:**



**Picture 1: Fire Water Tie-In for Plant “B”.**



**Picture 2: Installing Structural Fill for Treated Fuel Tank.**



**Picture 3: Installing Structural Fill for Treated Fuel Tank.**



**Picture 4: Installing Structural Fill for 7FA Foundation.**