CVG SIDOR POWER PROJECT SITE “A”

DATE:  29 May 2010, Saturday

PROJECT #: 410-3202

LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela

SITE MANAGER: Patrick Melody

TEMPERATURE:  88 F

RANGE: 85 to 95 F

SITE CONDITIONS: Morning rain 3 hours

PERSONNEL ON SITE:

| Lugo, Bill | Project Director | Jason Bird | Tech Adviser 7EA |
| --- | --- | --- | --- |
| Melody Patrick | Site Manager | Ryan Horn | Tool Room Super. |
| Blacke Edward | Safety Manager | Little John | Material Coordinator |
| James Siros | Mechanical Supt. | Daniels Julio | Tool Room (Local) |
| Archuleta Pete | Piping Supt. | Izquierdo Weiser | Mat'l. Handler (Local) |
| Riley Jasper | Electrical Supt | Lopez Juan Carlos | Mat'l. Handler (Local) |
| Soriano Rafael | QA/QC Manager | Ortega Ramon | Tool Room (Local) |
|  |  | Leccia Karina | Admin Assist |
|  |  | Rojas, Moises | Local Procurement |
|  |  | Zambrano Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                   4

Carpenter                            29                               Electrician                              3

Laborers                              28                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                                Mechanic Heavy                    1

Master Operator                    4                               Master Mechanic                   1

Survey Assistant                   2                               Concrete Finisher                 14

Surveyor                               2                                Warehouse  Assist                2

Oiler                                      1                                Total                                 174

- GENERAL ITEMS

    - Design and procurement for the project needs to be completed as soon as possible to support current project schedule.

- CLIENT ISSUES/CONCERNS:

    - Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Overhead lines are preventing excavation of Raw Water Tank and Fuel Storage Tank. Sidor had requested PES to employee an electrical contractor to expedite removal of overhead lines. A PO has been written by PES to Scalia for to expedite removal of overhead lines.

    - SIDOR has provided direction for acceptance / rejection of concrete placements in accordance with PDVSA Concrete.  38 c will be the maximum temp for concrete for non massive structural concrete placements. Massive concrete placement will be in accordance with ACI requirements utilizing ice in the mix design.

    - Material from the Industrial dawn has been detained at the port by Customs.

- CIVIL:

    - GT 300 Strip forms at GSU blast wall

    - GT 300 Exhaust stack foundation set anchor bolts template

    - Dewater excavations/site

- CONCRETE FOUNDATIONS:

- MECHANICAL:

    - Assist Material control in Identifying material

    - Fabricate pipe spools for fire line and raw water line

    - GT 200 Install auxiliary skid piping

    - GT 300 Exhaust stack weld out

    - GT 300 Set East side wall auxilairy

    - GT 300 Transition to air inlet

    - GT 300 Elbow to the air inlet

    - GT 300 Roof panel over the accessory module

    - Bolt up generator roof air inlet filter

    - Gas compressor clean gear boxes

- ELECTRICAL:

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

    - CPS Schedule development on going.

- CRITICAL AREAS OF CONCERN:

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

    - SAFETY:

      - Develop JSA as needed

      - Inspection of subcontractor power tools.

      - Inspection of motorized equipment prior to usage.

      - Scaffold and trenching inspections ongoing.

    - OUTSTANDING DRAWINGS:

9.1.2.1	Grounding grid

      - Coordinated underground drawing

      - Design drawings need to be issued

      - Utility Bldg. electrical panel layout

    - DRAWINGS ISSUED:

10.	PICTURES:

GT 100 Auxiliary Skid

GT 200 & Utility Bldg excavation for footings

Duct bank flooding

Site flooding from heavy rains over night