CVG SIDOR POWER PROJECT SITE “A” PROJECT: 410-3202

DATE: 30 April 2010 Friday

TEMPERATURE:  88 F      RANGE: 75 to 95

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

William Lugo – Project Manager        Scott Kirk – Civil Supt.

Edward Blacke - Safety Mgr.             Clarence Cornett – Civil Supt.

James Siros – Mech. Supt                 Mike Montgomery - QA/QC

Patrick Melody – Site Manager          Elizabeth Cornett – Doc.Cont

Clarence Cornett – Civil Supt.            Kyle Roskan – Civil Supt

David Sewell -  Const. Mgr                 Felix Martenz – QA/QC

Mike Montgomery QA/QC                  John Little – Mat’l Control

Wilson Contreras – Tool Super          Paul Oliva – Mat’l Control

David Jackson -  Mat’l Control            Jason Bird – Tech Assit

Michael Herasimchuk – I/C                Catherine Cameron – Inventory

Dennis Maloney – Turnnover

Daniel Meyer – Mat’l Control

Mark Hanks - Electrical

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                  4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                   1

Master Operator                    4                               Master Mechanic                  1

Survey Assistant                   2                               Concrete Finsher                14

Surveyor                               2                                Warehouse  Assist               2

Oiler                                     1                            Total                                 184

- CLIENT ISSUES/CONCERN:

1.1.1   Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Relocation of overhead lines at tank area have not been relocated

    - Fire line connection and design.

- CRITICAL AREAS OF CONCERN:

  - SAFETY:

    - Develop JSA as needed

    - Inspection of subcontractor power tools.

    - Inspection of motorized equipment prior to usage.

  - OUTSTANDING DRAWINGS:

    - Grounding grid

    - Coordinated underground drawing

    - Switch yard foundations and related duct banks

    - Foundation drawing 15 kv switch at GT 100 & 200

  - DRAWINGS ISSUED:

60-001 thru 60-126

- SCHEDULED ITEMS: - CPM Schedule development ongoing

- CIVIL:

  - GT 100 Install conduit in duct bank GT 200 to MH 4

  - GT 100 Install conduit MH 6 to GT 100,

  - GT 300 Concrete placement for 7EA foundation

  - MH 4 Concrete placement manhole walls

  - GT 1000 Backfill GSU foundation and duct bank

  - MH 3 Place Flowable Fill

- MECHANICAL:

5.1      GT 100 – Install right and left section of air filter house

5.2.     GT 200 – Installation  transition duct

5.3      GT 200 – Installation of turbine ventilation exhaust fan

- ELECTRICAL:

  - Install trailer breaker

6.2   Install conduit in duct bank

- INSTRUMENTATION AND CONTROLS:

8	PICTURES:

GT 100 Compete Air Filter House Installation

GT 300 7EA Foundation Concrete Placement

Civil Engineering Students on Site Tour