CVG SIDOR POWER PROJECT SITE “A”

DATE:  31 May 2010, Monday

PROJECT #: 410-3202

LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela

SITE MANAGER: Patrick Melody

TEMPERATURE:  88 F

RANGE: 85 to 95 F

SITE CONDITIONS: Sunny and hot

PERSONNEL ON SITE:

| Lugo, Bill | Project Director |  |  |
| --- | --- | --- | --- |
| Melody Patrick | Site Manager | Ryan Horn | Tool Room Super. |
| Blacke Edward | Safety Manager | Little John | Material Coordinator |
| James Siros | Mechanical Supt. | Daniels Julio | Tool Room (Local) |
|  |  | Izquierdo Weiser | Mat'l. Handler (Local) |
| Riley Jasper | Electrical Supt | Lopez Juan Carlos | Mat'l. Handler (Local) |
| Soriano Rafael | QA/QC Manager | Ortega Ramon | Tool Room (Local) |
|  |  | Leccia Karina | Admin Assist |
|  |  | Rojas, Moises | Local Procurement |
|  |  | Zambrano Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |

SUBCONTRACTOR PERSONNEL:

Operators                              9                              Carpenter                            25                               Electrician                              3                             Laborers                              15                              Helper                                  42                             Warehouse  Assist                2

Truck Driver                           6                           Operator Crane                     2

Welders                                 3                             Plumber                                 2

Oilers                                    2                                Mechanic Heavy                    1

Master Operator                    4                               Master Mechanic                   1

Survey Assistant                   2                               Concrete Finisher                 9

Surveyor                               2

Iron Workers                        27

Total                                 157

- GENERAL ITEMS

    - Design and procurement for the project needs to be completed as soon as possible to support current project schedule.

- CLIENT ISSUES/CONCERNS:

    - Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Overhead lines are preventing excavation of Raw Water Tank and Fuel Storage Tank. Sidor had requested PES to employee an electrical contractor to expedite removal of overhead lines. A PO has been written by PES to Scalia to expedite removal of overhead lines.

    - Material from the Industrial dawn has been detained at the port by Customs.

- CIVIL:

    - GT 300 Strip forms at GSU blast wall

    - GT 300 Exhaust stack foundation set anchor bolts template

    - Dewater excavations/site

    - Utility bldg. excavate grade beams

    - GT 200 Strip forms at cable tray piers

    - GT 200 Fine grade for Switch

- CONCRETE FOUNDATIONS:

- MECHANICAL:

    - Assist Material control in Identifying material

    - Fabricate pipe spools for fire line and raw water line

    - GT 200 Install auxiliary skid piping

    - GT 300 Install Insulation at exhaust stack

    - GT 300 Set turbine walls

    - GT 300 Set filter house substructure

    - GT 300 Roof panel at accessory module

    - Gas compressor clean gear boxes

- ELECTRICAL:

6.1.1 Install conduit at duct bank

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

    - CPS Schedule development on going.

- CRITICAL AREAS OF CONCERN:

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

    - SAFETY:

      - Develop JSA as needed

      - Inspection of subcontractor power tools.

      - Inspection of motorized equipment prior to usage.

      - Scaffold and trenching inspections ongoing.

    - OUTSTANDING DRAWINGS:

9.1.2.1	Grounding grid

      - Coordinated underground drawing

      - Design drawings need to be issued

      - Utility Bldg. electrical panel layout

    - DRAWINGS ISSUED:

10.	PICTURES:

GT 200 Auxiliary Skid and Piping

GT 300 7EA Erection

GT 100 Auxiliary Skid and Piping

GT 300 Exhaust Stack Baffle Installations