| EPC | Weekly Report 5 June 2010 |  |
| --- | --- | --- |
| Date: 5 June 2010 | Project: Sidor Site A, Puerto Ordaz Venezuela |  |
| Written By: Patrick Melody | ProEnergy EPC Project Mgr ProEnergy Site Manager | William Lugo Patrick Melody |

Table of Contents

1. Executive Summary

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary .

This report provide an overview of the project activities for the week ending 15 May 2010 for the engineering, procurement, and the construction activities on site.

  - Safety & Regulatory Compliance

    - Develop Job Safety Analysis as required.

    - Inspection of motorized equipment prior to usage.

    - Inspection of subcontractor power tools.

  - Personnel/Staffing

| Lugo, Bill | Project Director |  |  |
| --- | --- | --- | --- |
| Melody, Patrick | Site Manager | Horn, Ryan | Tool Room Super. |
|  |  | Little, John | Mat’l. Coordinator |
| Soriano, Rafael | QA/QC Manager |  |  |
| Siros, James | Mech. Supt. | Daniels, Julio | Tool Room (Local) |
|  |  | Izquierdo, Weiser | Mat'l. Handler |
| Riley, Jasper | Electrical Supt | Lopez, Juan Carlos | Mat'l. Handler |
|  |  | Flores, Herman | Tool Room (Local) |
|  |  | Leccia, Karina | Admin Assist |
|  |  | Rojas, Moises | Logistics |
|  |  | Zambrano, Natalia | Translator |
|  |  | Alvarez Josbett | Translator |
|  |  | Jansen Teodoro | Translator |

  - Weekly Accomplishments

- GT 100 Complete breaker switch foundation

    - GT 100 Complete turbine removal foundation

    - GT 100 Install linear plate in exhaust stack

    - GT 100 Install CO 2 skid

    - GT 200 Complete placement pipe rack footings & piers

    - GT 200 Complete cable tray foundations and piers

    - GT 200 Complete install auxiliary skid

    - GT 200 Install linear plate in exhaust stack

    - GT 200 Complete breaker switch foundation

    - GT 200 Complete turbine removal foundation

    - GT 300 Complete exhaust stack foundation

    - GT 300 Set Exhaust stack base

    - GT 300 Set turbine enclosure walls

    - GT 300 Set filter house substructure

    - GT 300 GT 300 Install accessory roof

    - GT 300 Install gas compressor / coolers

    - GT 300 Align generator /turbine t/ accessory skid

    - GT 300 Install auxiliary skid piping

    - GT 300 Complete filter house installation

    - TA2 – Pour foundation

    - SWBD – Pour foundations

    - Utility Bldg. Complete concrete footing and slab

    - Complete Conduit MH 8 to water treatment building

    - Complete Conduit MH 7 to MH 8

    - Excavate/Install Duct bank from MH 8 to gas compressor.

    - Excavate fire line / string pipe

    - Back fill duct banks and MH’s

    - Fabricate pipe spools for fire protection line

1.4– Scheduling Conflicts

- Development of CPM schedule is nearing complete.  Impacts resulting from lack of progress payments is being reviewed for inclusion

  - – Site Managers Commentary and Amplifying Remarks

- Shipments are not being released by customs due to errors in shipping documents. Line items values do not equal the total for the shipment.

- Civil Contractor is considering reducing manpower due to the payment issue. GT 300 duct bank 7 foundations, switch yard and water treatment building will be adversely affected.

- GT 300 GSU transformer was damaged in shipment. Site has proposed a repair procedure. Awaiting response from vendor.

2 Engineering and Design

2.1 – General Arrangement-

2.2 – Site /Civil /Structural

2.3 – Mechanical

- Fully coordinated underground piping drawings have been recieved.

2.4 – Electrical

    - Additional detail is required to stub up conduit at the location required. A list of foundation has been provided to the engineer for his action.

    - Grounding grid drawings are required.

2.5 – Instrumentation

- Ongoing

2.6 – O&M Manuals –

- Ongoing

3 Procurement

3.1 – Purchase Order Requests

- A local vendor list is being developed with the assistance of SIDOR.

- The lack of Progress Payments is restricting issuing PO’s to local subcontractors and vendors.

- – Equipment & Material Quotations

- Local procurement is hampered by financial restraints

3.3 - Purchase Order –

4 Contracts

4.1 – EPC Contract –

4.2 – Construction Subcontracts –

- A Purchase Order has been issued for excavation of underground process piping/fire line.

4.3 – Proposal & Quotes

5 Construction

- 5.1  Schedule

Impacts resulting from lack of progress payments is being reviewed for inclusion

- CPM schedule development is ongoing.

5.2  Equipment Delivery

5.3  Mechanical

- GT 100 – GT Erection is complete

- GT 200 – GT Erection is complete. Awaiting arrival of turbine for installation.

- GT 300 – GT Erection ongoing

5.4  Electrical

- Installation of Manholes and duct banks is ongoing.

5.5 QA/QC –

- Inspections of concrete placement, excavation, and backfill activities is ongoing.

6 Startup & Commissioning

- Pending.

7 Startup Mobilization

Fire Line Installation

GT 300 Exhaust Stack

Duct Bank Installation MH 8 to Gas Compressor

GT 300 7EA Filter House