CVG SIDOR POWER PROJECT SITE “A”

DATE:  5 May 2010, Wednesday

PROJECT #: 410-3202

LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela

SITE MANAGER: Patrick Melody

TEMPERATURE:  88 F

RANGE: 75 to 95 F

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

Elizabeth Cornett – Doc.Cont            Clarence Cornett – Civil Supt.

Kyle Roskan – Civil Supt                    Ryan Horn – Tool Room Supt

David Sewell -  Const. Mgr                Felix Martenz – QA/QC

John Little – Mat’l Control

Jay Riley – Elect. Supt.

Wilson Contreras – Mech.Supt         Paul Oliva – Mat’l Control

Jason Bird – Tech Assitant

Josbett Alvarez –Admin. Assistant    William Lugo – Project Director

Scott Kirk – Civil Supt.                       Edward Blacke - Safety Mgr 	                       James Siros – Mech. Supt 		    Michael Herasimchuk – I/C                         Catherine Cameron – Inventory        Teodoro Jansen - Translator

Dennis Maloney – Turnnover	    Pete Archeleta - Mechanical

Daniel Meyer – Mat’l Control             Moises Rojas – Logistical Support

Mark Hanks – Electrical                    Teresa Bretherick - Scheduler

Katrina Leccia – Admin. Assistant

Patrick Melody – Site Manager

SUBCONTRACTOR PERSONNEL:

Operators                            11                               Mechanical Assit.                   4

Carpenter                            29                               Electrician                              3

Laborers                              38                               Helper                                  57

Truck Driver                           4                               Operator Crane                     2

Welders                                 5                               Plumber                                 2

Oilers                                    1                               Mechanic Heavy                    1

Master Operator                    4                               Master Mechanic                   1

Survey Assistant                   2                               Concrete Finsher                 14

Surveyor                               2                                Warehouse  Assist                2

Oiler                                      1                                Total                                 184

- GENERAL ITEMS

    - Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

- CLIENT ISSUES/CONCERNS:

    - Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Relocation of overhead lines at fuel oil tank area expected to be complete within the next 7 days.

    - Fire line connection and design meeting to be held 6 May 2010. This activity needs to start next week to support current schedule.

    - Septagon, pre-engineered building supplier, to revise foundation drawings to address Sidor’s concerns. This drawing is needed urgently because this building is in the critical path.

- CIVIL:

    - Duct Bank Concrete placement GT 100 to MH 6

    - Duct Bank Concrete placement GT 200 to MH 4

    - Duct bank Concrete placement MH 3 to MH 4

    - Duct bank Concrete placement GT 6 to utility bldg.

    - Excavate MH 10

    - GT 100 – Place and compact fill at gas compressor

    - GT 300 – Strip forms 7EA foundation

    - Elect MH 9 – Install slab forms and rebar

- CONCRETE FOUNDATIONS:

- MECHANICAL:

    - GT 100 Prep for engine installation

    - GT 100 Turbine compartment bolt up

    - GT 100 Install baffles in Exhaust stack

    - GT 100 Install engine in turbine compartment

    - GT 200 Install east section air filter house

    - GT 200 Prep air filter house for installation

    - GT 200 Install and torque bolts for plenums and roof skids.

    - GT 200 Install generator rundown tank tubing

    - GT 300 Move Exhaust stacks to foundation area

    - GT Prep pipe for fire line loop

- ELECTRICAL:

    - Install conduit in duct banks

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

    - CPS Schedule development on going. First draft being reviewed by the team.

- CRITICAL AREAS OF CONCERN:

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

    - SAFETY:

      - Develop JSA as needed

      - Inspection of subcontractor power tools.

      - Inspection of motorized equipment prior to usage.

    - OUTSTANDING DRAWINGS:

      - Grounding grid

      - Coordinated underground drawing

      - Switch yard foundations and related duct banks

      - Cable rack foundation drawings

      - Design drawings need to be issued

    - DRAWINGS ISSUED:

      - Foundation Drawing for 15 KV switch

8	PICTURES:

GT 100 Install Turbine

GT 200 Air Filter House Installation