CVG SIDOR POWER PROJECT SITE “A”

DATE:  9 May 2010, Sunday

PROJECT #: 410-3202

LOCATION: SIDOR Industrial Area, Puerto Ordaz, Venezuela

SITE MANAGER: Patrick Melody

TEMPERATURE:  88 F

RANGE: 75 to 95 F

SITE CONDITIONS: Sunny with Scattered Clouds

PERSONNEL ON SITE:

| Lugo Bill | Project Manager | Jason Bird | Tech Adviser 7EA |
| --- | --- | --- | --- |
| Melody Patrick | Site Manager | Allan Hill | Tech Adviser LM 600 |
| Sewell David | Const. Manager |  |  |
| Blacke Edward | Safety Manager |  |  |
| Urbana Diomarys | Local Safety Manager |  |  |
| Siros James | Mech. Supt. |  |  |
| Archuleta Pete | Piping Supt. |  |  |
| Soriano Rafael | QA/QC Manager |  |  |

SUBCONTRACTOR PERSONNEL:

Welder  4

Pipe Fitter 2

Helpers 2

Foreman 1

- GENERAL ITEMS

    - Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

- CLIENT ISSUES/CONCERNS:

    - Location of existing gas line between 7EA and Control Building remains undeterminable after test pitting.

    - Relocation of overhead lines at fuel oil tank area expected to be complete within the next 7 days. Overhead lines are preventing excavation of Raw Water Tank.

    - Fire line connection and design meeting to be held 10 May 2010. This activity needs to start next week to support current schedule.

    - Septagon, pre-engineered building supplier, to revise foundation drawings to address Sidor’s concerns. This drawing is needed urgently because this building is in the critical path.

- CIVIL:

- CONCRETE FOUNDATIONS:

    - GT 100 Pipe Rack Foundation Delayed

    - GT 100 MUD Mat Cable Tray Foundation to GSU Delayed

    - Elect. MH 10 Concrete placement walls Delayed

    - GT 100 GSU Blast Wall concrete placement Delayed

    - Elect MH 6 Flowable fill Delayed

    - Duct Bank Concrete placement GT 200 15 kv Breaker to Load Breaker Delayed

- MECHANICAL:

    - GT 100 Exhaust stack seal weld

    - GT 300 Exhaust stack weld prep

    - GT 300 Install fixators

    - Fabricate pipe for fire line loop

- ELECTRICAL:

    - Install conduit in duct banks

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

    - CPS Schedule development on going. First draft being reviewed by the team.

- CRITICAL AREAS OF CONCERN:

The lack of availability of cement has caused the delay of numerous concrete pours as shown under Section 4 of this report. Concrete will not be available until Monday, 10 May 2010. 3 day delay.

Design and procurement for the project needs to be completed to as soon as possible to support current project schedule.

    - SAFETY:

      - Develop JSA as needed

      - Inspection of subcontractor power tools.

      - Inspection of motorized equipment prior to usage.

    - OUTSTANDING DRAWINGS:

9.1.2.1	Grounding grid

      - Coordinated underground drawing

      - Switch yard foundations and related duct banks

      - Cable rack foundation drawings

      - Design drawings need to be issued

      - Utility Bldg. Housekeeping pads for electrical equipment.

    - DRAWINGS ISSUED:

8	PICTURES:

GT 300 Fixator Installation