DATE 28 March 2010 Saturday

PROJECT # 410-3202

LOCATION- CVG Sidor Power Project Site A

SITE MANAGER- Patrick Melody

TEMPERATURE - 90 F. SITE CONDITIONS- Sunny and dry

RANGE 80 to 92

PERSONNEL ON SITE William Lugo – General Manager Scott Kirk – Civil Supt. Edward Blacke - Safety Mgr. Clarence Cornett – Civil Supt. James Sirros – Mech. Supt Mike Montgomery - QA/QC Patrick Melody – Site Manager Elizabeth Cornett - Document Control Clarence Cornett – Civil Supt. Gene Phillips – PE Civil - Wallace David Sewell - Const. Mgr Kyle Roskan – Civil Supt. Mike Montgomery QA/QC Hal schumeyer – Civil Supt Felix Martenz – QA/QC Shane Parks – EDGI Terry Stewart – EDGI Les Pry - EDGI

Subcontractor Personnel: General Superintendant 4 Electicians 2 Operators 12 Surveyor 3 Carpenters 24 Surveyor Helper 1 Steel Fabricators 32 Oiler Helper 1 Crane Operator 1 Laborers 36 Truck Drivers 4 Oilers 1 TOTAL 124 Plumbers 3 Helpers 3 Welders 2 Daily progress - QC inspection of GT foundation at GT 100 - Install conduit at GT 100 - Fine grade at GT 300 - Remove material from conex boxes for GT100 - Strip forms at GT 200 - Install and compact select fill at Gas Compressor - Fabricating conduit for GSU 100, 200 & 7EA - Receive anchor bolts for 7EA - Prep engine and generator skif for erection Second Shift

CLIENT ISSUES/CONCERN: Removal of H Frame at Water Treatment Building Power lines at east side of site need to be relocated for tank construction. Trash dumpsters are needed for metal and trash.

CRITICAL AREAS OF CONCERN

SCHEDULED ITEMS

.