## Recap
ProEnergy EPC
Job Description: |  |  | "1ea Fr VII EA and 1ea VII FA GTGs Simple Cycle Dual Fuel"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  |  | 2010-01-25
I. Balance of Plant Frame VII EA | [8 empty] | US $
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 370.3704 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 185.1852 | calc
|  | 103 | Concrete Foundations |  |  | 14931.9444 | 1941.1528 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 442.2222 | calc
|  | 106 | Gravel - Sand |  |  |  | 230.5556 | calc
|  | 107 | Structual Steel |  |  |  | 142.5 | calc
|  | 108 | Fencing |  |  |  | 91.25 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 3403.2361 |  | 3403.2361
| 200 Buildings | [5 empty] | 664.5 | calc | 664.5
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 10781 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 34020 | 2572.606 | calc
|  | 330 | Mechanical Subcontractor |  |  | 28706.4 | 2170.7895 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 1200 | calc
[7 empty] | 16724.3955 |  | 16724.3955
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 1329 | calc
|  | 420 | Substation Equipment |  |  |  | 68 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 22524.48 | 1703.3102 | calc
|  | 440 | Substation Subcontractor |  |  | 430.92 | 32.5863 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 1350 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 29160 | 2205.0909 | calc
[7 empty] | 6687.9874 |  | 6687.9874
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 215 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 4536 | 343.0141 | calc
[7 empty] | 558.0141 |  | 558.0141
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 745 | calc
|  | 620 | Telephone System |  |  |  | 15 | calc
|  | 630 | Public Address System |  |  |  | 15 | calc
|  | 640 | TV / Security |  |  |  | 10 | calc
[7 empty] | 785 |  | 785
700 Plant Erection
|  | 700 | Plant Erection |  |  | 49928.4 | 3775.6056 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 169306.2 | 3775.6056 |  | 3775.6056
| 800 Equipment Rental | [5 empty] | 1655 | calc | 1655
| 900 Painting | [5 empty] | 235 | calc | 235
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 689.92 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 0 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 0 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 689.92 |  | 689.92
| 1100 Site Costs | [5 empty] | 473.2 | calc | 473.2
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 695 | calc
|  | 1202 | Local Eng |  |  |  | 305 | calc
[7 empty] | 1000 |  | 1000
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 1068 | calc
|  | 1320 | Inspectors |  |  |  | 0 | calc
[7 empty] | 1068 |  | 1068
| 1400 Travel & Perdiem | [5 empty] | 763.35 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 763.35 |  | 763.35
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 270 | 2500 | 675 | plgd /1000
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 30 | 2000 | 60 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 30 | 2000 | 60 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 90 | 2000 | 180 | plgd /1000
|  | 1507 | Controls Rep |  | 60 | 2000 | 120 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2500 | 0 | plgd /1000
[7 empty] | 1095 |  | 1095
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 20 | plgd /1000
|  | 1602 | Concrete |  |  |  | 75 | plgd /1000
|  | 1603 | X Ray |  |  |  | 75 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 90 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 40 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 300 |  | 300
| 1700 Legal | [5 empty] | 30 | plgd /1000 | 30
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 400 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 400 |  | 400
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 400 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 3% | 15728 | 471.84 | calc
|  | 2150 | Labor Contingency |  | 3% | 12803.0026 | 384.0901 | calc
[7 empty] | 1255.9301 |  | 1255.9301
[5 empty] | BOP Cost |  |  |  | 41564.1388
[5 empty] | % Markup |  |  | 20% | 8312.8278
[5 empty] | BOP Sales Price |  |  |  | 49876.9665
II. One GE Fr VII FA from T 1002B
| 5010 BOP Cost of 1 ea VII FA | [5 empty] | 47719
0
[5 empty] | Cost of GTG |  | 47719 |  | 47719
[5 empty] | Markup |  |  | 20% | 9543.8
[5 empty] | VII FA Sales Price |  |  |  | 57262.8
[5 empty] | Total Plant Sales Price |  |  |  | 107139.7665
[5 empty] | Total Cost per KW |  |  |  | 428.5591

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [5 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [5 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Clearing/Grubbing |  |  | 500 | 400 | 1 | 200000 | 7407.4074 | 50 | 370370.3704
2
3 | Demolition
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Containment Systems
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
370.3704

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
8 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
9 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
10
11 | Main Plant Area |  |  |  | 500 | 400 | 1 | 200000 | 7407.4074 | 25 | 185185.1852
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 185.1852

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [7 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [7 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy
1 | POWER ISLAND |  |  | Price: 650
2 | GT Turbine |  |  | 1 | 68 | 20 | 7 | 9520 | 352.5926 | 650 | 229185.1852 | 1762.963
3 | GT Generator |  |  | 1 | 28 | 19 | 8 | 4256 | 157.6296 | 650 | 102459.2593 | 788.1481
4 | Exhaust Stack |  |  | 1 | 35 | 35 | 6 | 7350 | 272.2222 | 650 | 176944.4444 | 1361.1111
5 | Leg A |  |  | 1 | 27 | 7 | 3 | 567 | 21 | 650 | 13650 | 105
6 | Leg B |  |  | 1 | 27 | 27 | 3 | 2187 | 81 | 650 | 52650 | 405
7 | Base |  |  | 1 | 25 | 14 | 4 | 1400 | 51.8519 | 650 | 33703.7037 | 259.2593
8 | Exhaust Gas Blowers |  |  | 1 | 14 | 4 | 2 | 112 | 4.1481 | 650 | 2696.2963 | 20.7407
9 | Air Processing Skid |  |  | 1 | 8 | 6 | 1 | 48 | 1.7778 | 650 | 1155.5556 | 8.8889
10 | Gas Valve Module |  |  | 1 | 12 | 9 | 1 | 108 | 4 | 650 | 2600 | 20
11 | Mech Elec Bldg Vault |  |  | 1 | 40 | 23 | 1.5 | 1380 | 51.1111 | 650 | 33222.2222 | 255.5556
12 | Inlet Air Filter House |  |  | 1 | 43 | 5 | 2 | 430 | 15.9259 | 650 | 10351.8519 | 79.6296
13 | Accessory Module |  |  | 1 | 20 | 18 | 2 | 720 | 26.6667 | 650 | 17333.3333 | 133.3333
14 | Exhaust Frame Blower |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
15 | PEEC Building |  |  | 1 | 42 | 12 | 2 | 1008 | 37.3333 | 650 | 24266.6667 | 186.6667
16 | PDC Building |  |  | 1 | 42 | 12 | 1 | 504 | 18.6667 | 650 | 12133.3333 | 93.3333
17 | Fuel Gas Heater Module |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
18 | 15 KV Breaker Module |  |  | 1 | 20 | 12 | 1 | 240 | 8.8889 | 650 | 5777.7778 | 44.4444
19 | Aux Transformers |  |  | 2 | 20 | 15 | 1 | 600 | 22.2222 | 650 | 14444.4444 | 111.1111
| Mist Eliminator Containment |  |  | 1 | 16 | 16 | 0.5 | 128 | 4.7407 | 650 | 3081.4815 | 23.7037
| Mist Eliminator |  |  | 1 | 6 | 6 | 5 | 180 | 6.6667 | 650 | 4333.3333 | 33.3333
| SCR Package |  |  | 0 | 130 | 16 | 3 | 0 | 0 | 650 | 0 | 0
| NH3 Tank and Pumps |  |  | 0 | 40 | 40 | 2 | 0 | 0 | 650 | 0 | 0
| NH3 Skid adjacent to SCR |  |  | 0 | 20 | 15 | 1 | 0 | 0 | 650 | 0 | 0
| SCR Stack |  |  | 0 | 25 | 25 | 4 | 0 | 0 | 650 | 0 | 0
0
20 | BALANCE OF PLANT
21 | LO Fin Fan Coolers |  |  | 1 | 60 | 30 | 1 | 1800 | 66.6667 | 650 | 43333.3333 | 333.3333
22 | Fuel Gas Regulator Skid |  |  | 1 | 18 | 8 | 1 | 144 | 5.3333 | 650 | 3466.6667 | 26.6667
23 | Fuel Gas GTG Meter Skid |  |  | 1 | 25 | 6 | 1 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
24 | LO Cooling Water Pumps |  |  | 1 | 12 | 8 | 1 | 96 | 3.5556 | 650 | 2311.1111 | 17.7778
25 | Fuel Gas Separator |  |  | 1 | 12 | 8 | 2 | 192 | 7.1111 | 650 | 4622.2222 | 35.5556
26 | Fuel Gas Scrubber Skid |  |  | 1 | 15 | 12 | 1 | 180 | 6.6667 | 650 | 4333.3333 | 33.3333
27 | Water Wash System |  |  | 1 | 12 | 12 | 1.5 | 216 | 8 | 650 | 5200 | 40
28 | Waste Oil/Water Storage Tank |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
29 | Oily Water Separator |  |  | 1 | 30 | 20 | 0.5 | 300 | 11.1111 | 650 | 7222.2222 | 55.5556
30 | Lubricant Storage Area |  |  | 1 | 45 | 30 | 1 | 1350 | 50 | 650 | 32500 | 250
31 | Instrument Air Comp Skid |  |  | 1 | 10 | 8 | 1 | 80 | 2.963 | 650 | 1925.9259 | 14.8148
32 | Pipe Rack Stanchons |  |  | 15 | 2.5 | 2.5 | 6 | 562.5 | 20.8333 | 650 | 13541.6667 | 104.1667
33 | 15KV Cable Tray Stanchons |  |  | 4 | 2.5 | 2.5 | 6 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
34 | Fire Water Pump Skid |  |  | 0 | 15 | 30 | 1 | 0 | 0 | 650 | 0 | 0
35 | Area Light Poles |  |  | 4 | 2.5 | 3 | 5 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
36 | Aux Trans fndns |  |  | 2 | 10 | 15 | 1.5 | 450 | 16.6667 | 650 | 10833.3333 | 83.3333
37 | Cable Trenches see est |  |  | 2 | 180 | 12 | 0.5 | 2160 | 80 | 650 | 52000 | 400
38 | Water Treatment Plant |  |  | 1 | 60 | 50 | 1 | 3000 | 111.1111 | 650 | 72222.2222 | 555.5556
39 | Compressor Bases |  |  | 3 | 25 | 12 | 5 | 4500 | 166.6667 | 650 | 108333.3333 | 833.3333
40 | Compressor Fin Fans |  |  | 3 | 15 | 15 | 1 | 675 | 25 | 650 | 16250 | 125
41 | Raw Diesel Tank |  |  | 1 | 55 | 55 | 1 | 3025 | 112.037 | 650 | 72824.0741 | 560.1852
| Treated Diesel Tank |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 650 | 48750 | 375
| DFO Treatment Centrifuges |  |  | 3 | 15 | 4 | 2 | 360 | 13.3333 | 650 | 8666.6667 | 66.6667
| DFO Pumps |  |  | 4 | 10 | 3 | 1 | 120 | 4.4444 | 650 | 2888.8889 | 22.2222
| DFO Filter Skids |  |  | 2 | 10 | 10 | 1 | 200 | 7.4074 | 650 | 4814.8148 | 37.037
42 | Demin Water Pump skid |  |  | 2 | 15 | 8 | 1 | 240 | 8.8889 | 650 | 5777.7778 | 44.4444
43 | Demin Stg Tanks ____ Gal |  |  | 2 | 35 | 35 | 1 | 2450 | 90.7407 | 650 | 58981.4815 | 453.7037
44 | Demin Forwarding Pumps |  |  | 2 | 6 | 4 | 1 | 48 | 1.7778 | 650 | 1155.5556 | 8.8889
45 | Chemical Injection Skid |  |  | 1 | 12 | 12 | 1 | 144 | 5.3333 | 650 | 3466.6667 | 26.6667
46 | Raw Water Tank Base |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 650 | 48750 | 375
47 | Fire Water Tank base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
48 | Emer Generator Base |  |  | 1 | 30 | 15 | 3 | 1350 | 50 | 650 | 32500 | 250
49
50 | BUILDINGS
51 | Control Bldg/Office |  |  | 1 | 60 | 50 | 1 | 3000 | 111.1111 | 650 | 72222.2222 | 555.5556
52 | Warehouse/Maintenance |  |  | 1 | 75 | 50 | 1 | 3750 | 138.8889 | 650 | 90277.7778 | 694.4444
53 | Water Treatment Bldg |  |  | 1 | 60 | 50 | 1 | 3000 | 111.1111 | 650 | 72222.2222 | 555.5556
54 | Gas Compressor Shed |  |  | 1 | 60 | 35 | 1 | 2100 | 77.7778 | 650 | 50555.5556 | 388.8889
55 | Electrical Bldg |  |  | 1 | 42 | 20 | 1 | 840 | 31.1111 | 650 | 20222.2222 | 155.5556
56 | Pwr Blk Utility Bldg's |  |  | 0 | 30 | 20 | 1 | 0 | 0 | 650 | 0 | 0
57 | Substation Bldg |  |  | 1 | 15 | 12 | 1 | 180 | 6.6667 | 650 | 4333.3333 | 33.3333
58 | Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
59 | Liquid Fuel Unloading |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
60 | DFO Pump Shed |  |  | 0 | 20 | 40 | 1 | 0 | 0 | 650 | 0 | 0
61 | DFO Treatment Shed |  |  | 1 | 30 | 50 | 1 | 1500 | 55.5556 | 650 | 36111.1111 | 277.7778
62
63 | SUBSTATION
64 | GSU Transformer |  |  | 1 | 35 | 35 | 3 | 3675 | 136.1111 | 650 | 88472.2222 | 680.5556
65 | (___)KV SF6 Circuit Breaker |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
66 | (___)KV Disc Switch w/ Stand |  |  | 1 | 10 | 15 | 1 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
67 | Dead End Tower |  |  | 0 | 15 | 10 | 3 | 0 | 0 | 650 | 0 | 0
68 | Transmission Line Poles |  |  | 0 | 5 | 5 | 20 | 0 | 0 | 650 | 0 | 0
69 | Insulator Support Base |  |  | 6 | 3 | 3 | 5 | 270 | 10 | 650 | 6500 | 50
70 | PT Support Base |  |  | 3 | 3 | 3 | 5 | 135 | 5 | 650 | 3250 | 25
71 | Static Pole Base |  |  | 2 | 3 | 3 | 6 | 108 | 4 | 650 | 2600 | 20
72 | GSU Blast Wall |  |  | 1 | 67 | 32 | 1 | 2144 | 79.4074 | 650 | 51614.8148 | 397.037
73 | GSU Containment |  |  | 0 | 35 | 51 | 1 | 0 | 0 | 650 | 0 | 0
74 |  |  | Total Cost of Foundations | Cubic: 2986.3889; Total: 1941.1528 | 14931.9444
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [7 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [7 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description | [7 empty] | Cu | Price | Total
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 60 | 40 | 3 | 3 | 0 | 450 | 0
3 | Pilings Eexhaust Stack |  |  |  | 0 | 12 | 40 | 3 | 3 | 0 | 450 | 0
4 | Pilings GSU and Substation |  |  |  | 0 | 24 | 40 | 3 | 3 | 0 | 450 | 0
5 | Pilings BOP |  |  |  | 0 | 24 | 40 | 3 | 3 | 0 | 450 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings SCR x _1____ |  |  |  | 0 | 46 | 40 | 3 | 3 | 0 | 550 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls |  | Total Price: 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 500 | 0
2 | Gen Removal Areas |  |  | 40 | 20 | 1.5 | 1200 | 44.4444 | 500 | 22222.2222
3 | Turbine Removal Areas |  |  | 30 | 20 | 1.5 | 900 | 33.3333 | 500 | 16666.6667
4 | Entry Ways |  |  | 45 | 12 | 1 | 540 | 20 | 500 | 10000
5 | Walk ways |  |  | 80 | 6 | 0.5 | 240 | 8.8889 | 500 | 4444.4444
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 500 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 1000 | 20 | 0.7 | 14000 | 518.5185 | 500 | 259259.2593
12 | Parking Lot |  |  | 200 | 50 | 0.7 | 7000 | 259.2593 | 500 | 129629.6296
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 442.2222
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [7 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [7 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price
1
2 | Main Plant Area (less substa) |  |  | 1 | 550 | 400 | 0.5 | 110000 | 4074.0741 | 6762.963 | 25 | 169074.0741
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 25 | 0
5
6 | Substation |  |  | 1 | 300 | 100 | 1 | 30000 | 1111.1111 | 1844.4444 | 25 | 46111.1111
7
8 | Road ways |  |  | 1 | 1000 | 20 | 0.5 | 10000 | 370.3704 | 614.8148 | 25 | 15370.3704
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | Total: 230.5556

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [5 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [5 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | # of | Qty | Price | Total
No. | [5 empty] | Lbs / Tons |  |  | Price
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 3 | 3500 | 10500
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [5 empty] | 4 | 3000 | 12000
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 1 | 15000 | 15000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 1 | 25000 | 25000
10
11 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 1 | 40000 | 40000
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 40000 | 40000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 142.5

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 1500 | 15 | 22500
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 1500 | 23 | 34500
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 300 | 23 | 6900
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 3 | 3000 | 9000
10 | Motor Operated Double Gate(s) |  |  |  |  | 1 | 10000 | 10000
11 | Personnel Gate(s) |  |  |  |  | 3 | 450 | 1350
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 1 | 7000 | 7000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 91.25

## 109 Architectual
ARCHITECTUAL TREATMENT
[5 empty] | (1,000's) |  |  | 109
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1
2 | Trees and/or Shrubs - Revegetation
3 | Boundry Road |  |  |  |  | 0 | 0 | 0
4 | Within site |  |  |  |  | 0 | 0 | 0
5 | [5 empty] | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39
40 |  |  | Total Cost of Arch Treatment |  |  |  |  | 0

## 110 Evap Pond
EVAPORATION POND
|  |  |  | (1,000's) | [5 empty] | 110
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yard | cy | Price
1 | Storm Water Evap Pond |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7
8
9
10
11 | [8 empty] | Price
12 | [6 empty] | sf |  | sf
13 | Liner |  |  | 0 | 0 |  | 0 |  | 3 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 | [9 empty] | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [5 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [5 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price
1 | Fuel Gas Compressor Shed |  |  |  | 60 | 35 | 2100 | 40 | 84000
2 | Control/Office |  |  |  | 60 | 50 | 3000 | 65 | 195000
3 | Water Treatment |  |  |  | 75 | 50 | 3750 | 45 | 168750
4 | Electric Bldg |  |  |  | 0 | 10 | 0 | 85 | 0
5 | Warehouse/Maintenance |  |  |  | 75 | 50 | 3750 | 45 | 168750
6 | Substation Bldg |  |  |  | 20 | 15 | 300 | 40 | 12000
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0
9 | DFO Pump Shed |  |  |  | 20 | 30 | 600 | 40 | 24000
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 15 | 20 | 300 | 40 | 12000
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 664.5

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [9 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [9 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [9 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
| GTG |  |  | Unit: 3%; Hours: 9
1 | GTG Type GE 7EA |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 12 | 60 | 6480 | 75.6204 | 490020.192
2 | Lube oils and Chemicals |  |  | 1 | 50000 | 50000 | 2500 | 2500 | 9 | 3 | 6 | 162 | 75.6204 | 12250.5048
3 | Exhaust Stack |  |  | 0 | 900000 | 0 | 130000 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
4 | Project Grouting |  |  | 1 | 75000 | 75000 | 2250 | 2250 | 9 | 0 | 0 | 0 | 75.6204 | 0
5 | Lube Oil Cooling Fin Fans |  |  | 3 | 75000 | 225000 | 10000 | 30000 | 9 | 6 | 8 | 1296 | 75.6204 | 98004.0384
6 | Anchor Bolts |  |  | 1 | 85000 | 85000 | 2550 | 2550 | 9 | 0 | 0 | 0 | 75.6204 | 0
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 3500000 | 0 | 300000 | 0 | 9 | 12 | 90 | 0 | 75.6204 | 0
18 | NH3 Tank w/ pumps |  |  | 0 | 320000 | 0 | 0 | 0 | 9 | 4 | 30 | 0 | 75.6204 | 0
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
30 | Inlet Fogging System |  |  | 1 | 25000 | 25000 | 750 | 750 | 9 | 4 | 6 | 216 | 75.6204 | 16334.0064
31 | Inlet Evap Cooling System |  |  | 0 | 400000 | 0 | 0 | 0 | 9 | 6 | 10 | 0 | 75.6204 | 0
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
33 | Cooling Water Circulation Pumps |  |  | 2 | 15000 | 30000 | 500 | 1000 | 9 | 2 | 3 | 108 | 75.6204 | 8167.0032
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 2 | 850000 | 1700000 | 15000 | 30000 | 9 | 6 | 8 | 864 | 75.6204 | 65336.0256
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 1 | 285000 | 285000 | 7000 | 7000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
40 | Fuel Gas Scrubber |  |  | 1 | 160000 | 160000 | 2500 | 2500 | 9 | 2 | 3 | 54 | 75.6204 | 4083.5016
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 108 | 75.6204 | 8167.0032
42 | ESD Valve, ___" ___# |  |  | 1 | 20000 | 20000 | 600 | 600 | 9 | 0 | 0 | 0 | 75.6204 | 0
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  | 0 | 30000 | 0 | 1500 | 0 | 9 | 3 | 4 | 0 | 75.6204 | 0
46 | Metering Skid |  |  | 1 | 155000 | 155000 | 4650 | 4650 | 9 | 3 | 4 | 108 | 75.6204 | 8167.0032
47 | Forwarding Pump Skid |  |  | 1 | 30000 | 30000 | 1500 | 1500 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524
48 | Transfer Pump Skid |  |  | 1 | 30000 | 30000 | 1500 | 1500 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524
49 | Fuel Heating |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
50 | Filters Skids |  |  | 1 | 85000 | 85000 | 15000 | 15000 | 9 | 4 | 4 | 144 | 75.6204 | 10889.3376
51 | Centrifuge |  |  | 3 | 500000 | 1500000 | 45000 | 135000 | 9 | 6 | 6 | 972 | 75.6204 | 73503.0288
52 | Injection Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
53 | Storage Tank Raw 500000 Gal |  |  | 1 | 600000 | 600000 | 50000 | 50000 | 9 | 6 | 8 | 432 | 75.6204 | 32668.0128
54 | Day Tank Treated 150000 Gal |  |  | 1 | 250000 | 250000 | 20000 | 20000 | 9 | 4 | 4 | 144 | 75.6204 | 10889.3376
55
56 | Water Supply System
57 | Raw Water Storage Tank 500 M gal |  |  | 1 | 300000 | 300000 | 5000 | 5000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
58 | Raw Water Supply Pumps |  |  | 2 | 15000 | 30000 | 900 | 1800 | 9 | 2 | 3 | 108 | 75.6204 | 8167.0032
59 | Raw Water Forwarding Pumps |  |  | 2 | 15000 | 30000 | 900 | 1800 | 9 | 2 | 3 | 108 | 75.6204 | 8167.0032
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 1 | 125000 | 125000 | 3750 | 3750 | 9 | 3 | 4 | 108 | 75.6204 | 8167.0032
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
64 | Demin Treatment System 180,000 GPD |  |  | 1 | 550000 | 550000 | 100000 | 100000 | 9 | 6 | 16 | 864 | 75.6204 | 65336.0256
65 | Demin Storage SS Tank 300000 gal |  |  | 1 | 500000 | 500000 | 40000 | 40000 | 9 | 6 | 5 | 270 | 75.6204 | 20417.508
66 | Demin water fiberglass tank |  |  | 2 | 25000 | 50000 | 2500 | 5000 | 9 | 3 | 4 | 216 | 75.6204 | 16334.0064
67 | Demin forwarding pumps |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 9 | 3 | 3 | 162 | 75.6204 | 12250.5048
68 | Demin Filter Skid |  |  | 1 | 86000 | 86000 | 2580 | 2580 | 9 | 4 | 4 | 144 | 75.6204 | 10889.3376
69 | Potable Water System |  |  | 1 | 15000 | 15000 | 1500 | 1500 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 1 | 55000 | 55000 | 5000 | 5000 | 9 | 4 | 6 | 216 | 75.6204 | 16334.0064
73 | Oily Waste Tank 10000 gal |  |  | 1 | 10000 | 10000 | 1500 | 1500 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524
74 | Waste Water Tank 10000 gal |  |  | 1 | 10000 | 10000 | 1500 | 1500 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 2 | 10000 | 20000 | 600 | 1200 | 9 | 2 | 2 | 72 | 75.6204 | 5444.6688
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
79 | Fire Water System, valves, hydrants, monitors |  |  | 1 | 550000 | 550000 | 16500 | 16500 | 9 | 8 | 20 | 1440 | 75.6204 | 108893.376
80
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 1 | 80000 | 80000 | 2400 | 2400 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
89 | Black Start Generator |  |  | 1 | 3000000 | 3000000 | 35000 | 35000 | 9 | 4 | 8 | 288 | 75.6204 | 21778.6752
90 | Sanitary Sewer Septic System |  |  | 1 | 25000 | 25000 | 750 | 750 | 9 | 0 | 0 | 0 | 75.6204 | 0
91 |  |  |  | Hours: 9
92
93 |  |  | Total Cost | Total: 10781; Frt: 534.48; Qty: 15948
94 |  |  |  | Total: 1205.9941
[9 empty] | Total Manhours |  |  | 15948
[9 empty] | Times Prod Factor |  | 1.8 | 28706.4 | 75.6204 | 2170.7895
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 1200000 | 1200000 | 36000 | 36000 | 9 | 14 | 150 | 18900 | 75.6204 | 1429225.56
96 |  |  | Total Cost | Total: 1200; Frt: 36; Qty: 18900; Total: 1429225.56
97
98 |  |  |  | Hours: Total Manhours; Qty: 18900
99 |  |  |  | Hours: Times Prod Factor; Qty: 1.8; Qty: 34020; Rate: 75.6204; Total: 2572.606
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 40
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 14
58
[8 empty] | Contr G&A 8% |  | 4.64
[8 empty] | Contr Mark up 15% |  | 8.7
71.34
[7 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [11 empty] | Date: |  | 2010-01-25
Customer: |  | CVG/SIDOR | [11 empty] | Quote No: |  | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [11 empty] | Est By: |  | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | Power Island Equipment | [7 empty] | 3% |  | 9
2 | Gas Turbine Generator |  |  |  |  | 1 |  | 0 | 0 | 0 | 9 | 12 | 60 | 6480 | 75.6204 | 490020.192
3 | HRSG |  |  |  |  | 0 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
4 | SCR |  |  |  |  | 0 |  | 0 | 0 | 0 | 9 | 8 | 35 | 0 | 75.6204 | 0
5 | STG Cooling Tower |  |  |  |  | 0 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
6 | STG Cooling Tower |  |  |  |  | 0 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
7 | Fogging Package |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344
8 | Water Treatment Package |  |  |  |  | 1 |  | 0 | 0 | 0 | 9 | 6 | 18 | 972 | 75.6204 | 73503.0288
9 | [13 empty] | 0 | 75.6204 | 0
10 | 15KV | [13 empty] | 75.6204
11 | Generator Breaker(s) |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344
12 | Distribution Breaker(s) |  |  |  |  | 2 | 45000 | 90000 | 2700 | 5400 | 9 | 4 | 4 | 288 | 75.6204 | 21778.6752
13 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 0 | 75.6204 | 0
14 | Cable Bus Duct |  |  |  |  | 1 | 250000 | 250000 | 7500 | 7500 | 9 | 4 | 8 | 288 | 75.6204 | 21778.6752
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 4 | 0 | 75.6204 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 6 | 0 | 75.6204 | 0
17 | 5KV | [13 empty] | 75.6204
18 | Distribution Breaker(s) |  |  |  |  | 3 | 40000 | 120000 | 3600 | 10800 | 9 | 2 | 5 | 270 | 75.6204 | 20417.508
19 | Distribution Panel w/ Auto Sync |  |  |  |  | 1 | 140000 | 140000 | 4200 | 4200 | 9 | 2 | 6 | 108 | 75.6204 | 8167.0032
20 | MCC's |  |  |  |  | 2 | 30000 | 60000 | 1800 | 3600 | 9 | 1 | 1 | 18 | 75.6204 | 1361.1672
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 6 | 0 | 75.6204 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
23 | 600V | [13 empty] | 75.6204
24 | Distribution Panel(s) |  |  |  |  | 1 | 30000 | 30000 | 5000 | 5000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
25 | GTG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 4 | 0 | 75.6204 | 0
27 | SCR MCC |  |  |  |  | 0 | 15000 | 0 | 1000 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
28 | BOP MCC(s) |  |  |  |  | 1 | 45000 | 45000 | 2000 | 2000 | 9 | 2 | 6 | 108 | 75.6204 | 8167.0032
29 | Water Treatment MCC(s) |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 9 | 2 | 4 | 72 | 75.6204 | 5444.6688
30 | DFO MCC |  |  |  |  | 1 | 45000 | 45000 | 1350 | 1350 | 9 | 2 | 8 | 144 | 75.6204 | 10889.3376
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0
32 | Aux Transformer(s) | [13 empty] | 75.6204
33 | 15/5KV __2.5_ MVA |  |  |  |  | 1 | 120000 | 120000 | 10000 | 10000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
34 | 15/600V ___2 _ MVA |  |  |  |  | 1 | 80000 | 80000 | 5000 | 5000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
35 | 600/120/208V ________ KVA |  |  |  |  | 1 | 7000 | 7000 | 1500 | 1500 | 9 | 3 | 6 | 162 | 75.6204 | 12250.5048
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
38 | Area Lighting | [13 empty] | 75.6204
39 | Poles _______ High |  |  |  |  | 4 | 1500 | 6000 | 300 | 1200 | 9 | 3 | 2 | 216 | 75.6204 | 16334.0064
40 | Floodlights _______ Watts |  |  |  |  | 12 | 500 | 6000 | 75 | 900 | 9 | 1 | 0.2 | 21.6 | 75.6204 | 1633.4006
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 60 | 0 | 75.6204 | 0
43 | Other Systems | [13 empty] | 75.6204
44 | UPS |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 9 | 2 | 4 | 72 | 75.6204 | 5444.6688
45 | DC |  |  |  |  | 1 | 30000 | 30000 | 2500 | 2500 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754
46 | Cathodic Protection |  |  |  |  | 1 | 15000 | 15000 | 450 | 450 | 9 | 4 | 12 | 432 | 75.6204 | 32668.0128
47 | Lightning Protection |  |  |  |  | 1 | 15000 | 15000 | 450 | 450 | 9 | 4 | 12 | 432 | 75.6204 | 32668.0128
48 | Heat Trace |  |  |  |  | 0 | 200000 | 0 | 2000 | 2000 | 9 | 4 | 45 | 0 | 75.6204 | 0
49 | [14 empty] | 75.6204
50 | Temporary Electric |  |  |  |  | 1 | 60000 | 60000 | 1800 | 1800 | 9 | 2 | 45 | 810 | 75.6204 | 61252.524
51 | Electrical Control Module |  |  |  |  | 1 | 135000 | 135000 | 5000 | 5000 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344
52 | [6 empty] | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 1329 |  | 72.9 |  |  |  | 12513.6 |  | 946.2834
[12 empty] | Productivity | 1.8 | 22524.48 | 75.6204 | 1703.3102
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 1350000 | 1350000 | 40500 | 40500 | 9 | 12 | 150 | 16200 | 75.6204 | 1225050.48
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 1350 |  | 40.5 |  |  |  | 16200 |  | 1225.0505
58 | [10 empty] | Total Manhours |  |  | 16200
59 | [10 empty] | Times Prod Factor |  | 1.8 | 29160 | 75.6204 | 2205.0909
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 40
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 14
58
[13 empty] | Contr G&A 8% |  | 4.64
[13 empty] | Contr Mark up 15% |  | 8.7
71.34
[12 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N87: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q79: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [12 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [12 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [12 empty] | Est By:
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  | Unit: 3%; Hours: 9
2 | Main Power Transformer _69 KV, _100_ MVA | [5 empty] | 0 | 0 | 0 | 0 | 9 | 4 | 10 | 0 | 75.6204 | 0
3 | SF6 Circuit Breaker(s) ____ KV | [5 empty] | 0 | 0 | 0 | 0 | 9 | 3 | 10 | 0 | 75.6204 | 0
4 | Disconnect Switches ______ KV | [5 empty] | 0 | 0 | 0 | 0 | 9 | 3 | 6 | 0 | 75.6204 | 0
5 | Station Post Insulators ____ KV | [5 empty] | 0 | 0 | 0 | 0 | 9 | 2 | 0.05 | 0 | 75.6204 | 0
6 | Insulator Stanchons ______ High | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.5 | 0 | 75.6204 | 0
7 | Insulator Stanchons ______ High | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.4 | 0 | 75.6204 | 0
8 | Dead End Tower(s) |  |  |  |  | 1 | 40000 | 40000 | 5000 | 5000 | 9 | 4 | 5 | 180 | 75.6204 | 13611.672
9 | Alum Bus ______ Dia | [5 empty] | 0 | 0 | 8 | 0 | 9 | 1 | 0.08 | 0 | 75.6204 | 0
10 | Alum Bus Conn's | [5 empty] | 0 | 0 | 0 | 0 | 9 | 3 | 35 | 0 | 75.6204 | 0
11 | Alum Bus End Plugs _____ Dia | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.05 | 0 | 75.6204 | 0
12 | Alum Bus Support Clamps | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 75.6204 | 0
13 | Alum Bus "V" Conn's | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 75.6204 | 0
14 | Static Wire Poles, ____ High | [5 empty] | 4000 | 0 | 1500 | 0 | 9 | 4 | 1 | 0 | 75.6204 | 0
15 | Area Lighting Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 75.6204 | 0
16 | Flood Lights, ______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0
17 | #4/0 Grounding Conductor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.03 | 0 | 75.6204 | 0
18 | 3/4"x10'-0" Ground Rods & Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.04 | 0 | 75.6204 | 0
19 | #90 Cadweld Shots |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.3 | 0 | 75.6204 | 0
20 | Metering CT's & CPT's | [5 empty] | 25000 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0 | 0
21 | Station Metering w/ In & Out Capabilities | [5 empty] | 50000 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 75.6204 | 0
22 | Station Protective Relay(s) | [5 empty] | 50000 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
23 | Station RTU |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
24 | 125V DC System |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0
25 | Transmission Line Poles |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 2 | 0 | 75.6204 | 0
26 | Transmission Line Strain Insulators |  |  |  |  | 6 | 500 | 3000 | 90 | 540 | 9 | 1 | 0.1 | 5.4 | 75.6204 | 408.3502 | 0
27 | Cable Bus, Type _____, Size _____ |  |  |  |  | 1 | 25000 | 25000 | 500 | 500 | 9 | 3 | 2 | 54 | 75.6204 | 4083.5016
28 | Main Power Transformer Oil, ______ Gal | [5 empty] | 70000 | 0 | 0 | 0 | 9 | 2 | 3 | 0 | 75.6204 | 0
29 | Main Power Transformer Dress Out & Test | [5 empty] | 70000 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 75.6204 | 0
30 | Fiber Optic Cable w/ Messenger Cable | [5 empty] | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 75.6204 | 0 | 0
31 | Fiber Optic Cable Fittings & Terminations |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0
32 |  |  |  | Hours: 9; Rate: 75.6204
33 |  |  |  | Hours: 9; Rate: 75.6204
34 |  |  |  | Hours: 9; Rate: 75.6204
35 |  |  |  | Hours: 9; Rate: 75.6204; Total: 0
36 |  |  | Total Cost of Substation Equipment | Total: 68; Frt: 6.04; Qty: 239.4; Total: 18.1035
[12 empty] | Total Hours |  | 239.4
[12 empty] | Prod Factor | 1.8 | 430.92 | 75.6204 | 32.5863
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 40
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 14
58
[13 empty] | Contr G&A 8% |  | 4.64
[13 empty] | Contr Mark up 15% |  | 8.7
71.34
[12 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N61: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q53: Insert Rate Here:

## 510 CEMS
CEM's
[5 empty] | (1,000's) |  |  | 510
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Cems | Cost | Cost
1
2 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 120000 | 0
3
4 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 230000 | 0
5
6 | Installation Support |  |  |  |  | 0 | 18000 | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of CEM's |  |  |  |  | 0

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [8 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [8 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [8 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  | Hours: 9
2 | Instrumentation for GTG |  |  | 1 | 110000 | 110000 | 9 | 4 | 40 | 1440 | 75.6204 | 108893.376
3 |  |  |  | Hours: 9; Rate: 75.6204; Total: 0
4 | Instrumentation for SCR |  |  | 0 | 75000 | 0 | 9 | 4 | 12 | 0 | 75.6204 | 0
5 |  |  |  | Hours: 9; Rate: 75.6204
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 75.6204 | 0
7 |  |  |  | Hours: 9; Rate: 75.6204
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 25000 | 25000 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344
9 |  |  |  | Hours: 9; Rate: 75.6204
10 | Instrumentation for DFO Treatment |  |  | 1 | 35000 | 35000 | 9 | 2 | 10 | 180 | 75.6204 | 13611.672
11 |  |  |  | Hours: 9; Rate: 75.6204
12 | Instrumentation for gas compressors |  |  | 3 | 15000 | 45000 | 9 | 4 | 5 | 540 | 75.6204 | 40835.016
13 |  |  |  | Hours: 9; Rate: 75.6204
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 9 | 4 | 7 | 0 | 75.6204 | 0
15 |  |  |  | Hours: 9; Rate: 75.6204
16 |  |  |  | Hours: 9; Rate: 75.6204
17 |  |  |  | Hours: 9; Rate: 75.6204
18 |  |  |  | Hours: 9; Rate: 75.6204
19 |  |  |  | Hours: 9; Rate: 75.6204
20 |  |  |  | Hours: 9; Rate: 75.6204
21 |  |  |  | Hours: 9; Rate: 75.6204
22 |  |  |  | Hours: 9; Rate: 75.6204
23 |  |  | Total Cost of Plant Instrumentation | Total: 215; Qty: 2520; Total: 190.5634
[8 empty] | Total Hours |  | 2520
[8 empty] | Prod Factor | 1.8 | 4536 | 75.6204 | 343.0141
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 40
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 14
58
[9 empty] | Contr G&A 8% |  | 4.64
[9 empty] | Contr Mark up 15% |  | 8.7
71.34
[8 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [6 empty] | Cost | Cost
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 550000 | 650000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 1 | 50000 | 50000
5
6 | Documentation |  |  |  |  | 1 | 45000 | 45000
7
8 |  |  |  |  | Total DCS |  |  | 745
9
10 | PBX Communications System |  |  |  |  | 1 | 15000 | 15
11
12 | Loud Speaker System |  |  |  |  | 1 | 15000 | 15
13
14 | TV / Security System |  |  |  |  | 1 | 10000 | 10
15
16
17
[7 empty] | taxable | 700.04

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  |  | 9
2 | GTG Erection |  |  | 1 | 9 | 20 | 140 | 25200 | 75.6204 | 1905634.08
3 |  |  |  |  | 9 |  |  |  | 75.6204
4 | HRSG Erection |  |  | 0 | 9 | 10 | 60 | 0 | 75.6204 | 0
5 |  |  |  |  | 9 |  |  |  | 75.6204
6 | SCR Erection |  |  | 0 | 9 | 10 | 75 | 0 | 75.6204 | 0
7 |  |  |  |  | 9 |  |  |  | 75.6204
8 | Water Treatment and FW Systems |  |  | 1 | 9 | 6 | 10 | 540 | 75.6204 | 40835.016
9 |  |  |  |  | 9 |  |  |  | 75.6204
10 | DFO Treatment System |  |  | 1 | 9 | 6 | 8 | 432 | 75.6204 | 32668.0128
11 |  |  |  |  | 9 |  |  |  | 75.6204
12 | BOP Equip Erection |  |  | 1 | 9 | 6 | 15 | 810 | 75.6204 | 61252.524
13 |  |  |  |  | 9 |  |  |  | 75.6204
14 | Gas Compressor Erection |  |  | 3 | 9 | 6 | 4 | 648 | 75.6204 | 49002.0192
15 |  |  |  |  | 9 |  |  |  | 75.6204
16 | Black Start Gen |  |  | 1 | 9 | 4 | 3 | 108 | 75.6204 | 8167.0032
17 |  |  |  |  | 9 |  |  |  | 75.6204
18 | Fire Water Pump Skid |  |  | 0 | 9 | 4 | 3 | 0 | 75.6204 | 0
19 |  |  |  |  | 9 |  |  |  | 75.6204
20 | STG Erection |  |  | 0 | 9 | 12 | 36 | 0 | 75.6204 | 0
21 |  |  |  |  | 9 |  |  |  | 75.6204
22 | STG Cooling Tower |  |  | 0 | 9 | 8 | 8 | 0 | 75.6204 | 0
23 |  |  |  |  | 9 |  |  |  | 75.6204
24 |  |  |  |  | 9 |  |  |  | 75.6204
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 27738 |  | 2097.5587
[6 empty] | Total Hours |  | 27738
[6 empty] | Prod Factor | 1.8 | 49928.4 | 75.6204 | 3775.6056
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 40
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 14
58
[7 empty] | Contr G&A 8% |  | 4.64
[7 empty] | Contr Mark up 15% |  | 8.7
71.34
[6 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total
No. | [5 empty] | Units | Unit | Days | Per Day | Cost
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 1 | 30 | 30 | 15000 | 450000
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 1 | 130 | 130 | 5000 | 650000
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 2 | 140 | 280 | 100 | 28000
8 | 1 ea Man Lift |  |  |  |  | 2 | 140 | 280 | 100 | 28000
9 | 2 ea Welders |  |  |  |  | 4 | 130 | 520 | 100 | 52000
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 45 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 60 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 90 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 90 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 90 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 2 | 2 | 4 | 5000 | 20000
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 2 | 3 | 6 | 3000 | 18000
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 120 | 120 | 3000 | 360000
51 | 2 ea Fork Lifts |  |  |  |  | 1 | 130 | 130 | 100 | 13000
52 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 100 | 0
53 | 2 ea Pick ups |  |  |  |  | 2 | 150 | 300 | 100 | 30000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 0 | 0 | 0 | 100 | 0
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 3 | 0 | 15000 | 0
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 2 | 2 | 3000 | 6000
60 | 2 ea Man Lifts |  |  |  |  | 0 | 45 | 0 | 80 | 0
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 1802 |  | 1655

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Paint for GTG |  |  |  |  | 1 | 90000 | 90000
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 1 | 15000 | 15000
9
10 | Paint for BOP Equipment |  |  |  |  | 1 | 45000 | 45000
11
12 | Paint for Gas Compressor |  |  |  |  | 3 | 15000 | 45000
13
14 | Paint for Water Treatment |  |  |  |  | 1 | 20000 | 20000
15
16 | Paint for DFO Treatment |  |  |  |  | 1 | 20000 | 20000
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 235

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 534.48 | 534.48
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 72.9 | 72.9
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 6.04 | 6.04
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 36 | 36
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 40.5 | 40.5
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 689.92

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG/SIDOR | [6 empty] | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 4 | 7 | 4500 | 126000
3 | Porta Potties |  |  |  |  | 4 | 7 | 700 | 19600
4 | Water and Ice |  |  |  |  | 3 | 7 | 500 | 10500
5 | Fed X |  |  |  |  | 1 | 7 | 300 | 2100
6 | Telephone |  |  |  |  | 1 | 7 | 2500 | 17500
7 | Office Supplies |  |  |  |  | 1 | 7 | 1000 | 7000
8 | [6 empty] | 7
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 7 | 3500 | 24500
10 | Misc Items |  |  |  |  | 1 | 7 | 3000 | 21000
11 |  |  | Total Monthly Cost | [5 empty] | 228200
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 228200 |  | 228200
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 150000
21 | Cad Station | [8 empty] | 10000
22 | Computers | [8 empty] | 15000
23 | Telephone System and Satalite Dish | [8 empty] | 15000
24 | Plotter | [8 empty] | 0
25 | Fax Machine and Printers | [8 empty] | 5000
26 | Misc equip | [8 empty] | 50000
27 | Signs | [8 empty] | 0
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 473.2

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Conceptual Engineering |  |  |  |  | 1 | 25000 | 25000
3
4 | Detailed Engineering per GTG |  |  |  |  | 1 | 450000 | 450000
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering for DFO Treatment System |  |  |  |  | 1 | 25000 | 25000
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 3 | 15000 | 45000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 1 | 25000 | 25000
13
14 | Detailed Engineering for Civil / Structural Steel |  |  |  |  | 1 | 125000 | 125000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 695

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Soils & Environmental Eng - Soil Test - Topo |  |  |  |  | 1 | 80000 | 80000
3
4 | Civil Engineer |  |  |  |  | 5 | 15000 | 75000
5
6 | Mechanical Engineer |  |  |  |  | 5 | 15000 | 75000
7
8 | Electrical Engineer |  |  |  |  | 5 | 15000 | 75000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 305

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Mos | Per Mo | Cost
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 7 | 16000 | 112000
2 | Admin Mgr Months on Project |  |  |  |  | 7 | 7000 | 49000
3 | Scheduler |  |  |  |  | 5 | 8000 | 40000
4 | Purchasing Agent |  |  |  |  | 3 | 8000 | 24000
5 | Expediter |  |  |  |  | 3 | 5000 | 15000
6 | Home Office Logistic Coordinator |  |  |  |  | 0 | 9000 | 0
7
8
9 | [6 empty] | 240000
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 7 | 6000 | 42000
18 | Construction Mngr |  |  |  |  | 7 | 16000 | 112000
19 | Contract Cost Admin |  |  |  |  | 0 | 10000 | 0
20 | Scheduler |  |  |  |  | 3 | 8000 | 24000
21 | Mechanical Supervisor |  |  |  |  | 6 | 12000 | 72000
22 | Electrical Supervisor |  |  |  |  | 6 | 12000 | 72000
23 | Civil Supervisor |  |  |  |  | 4 | 12000 | 48000
24 | Clerks |  |  |  |  | 6 | 5000 | 30000
25 | Warehousemen |  |  |  |  | 6 | 6000 | 36000
26 | Draftsman |  |  |  |  | 2 | 7000 | 14000
27 | Security |  |  |  |  | 7 | 15000 | 105000
28 | Safety |  |  |  |  | 7 | 8000 | 56000
29 | QA/QC Mngr |  |  |  |  | 7 | 8000 | 56000
30
31
32 | [6 empty] | 667000
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 9 | 14000 | 126000
35
36
37
38 | Training |  |  |  |  | 1 | 35000 | 35000
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 1068
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
47 | Mechanical __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
48 | Electrical __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 0 | 11500 | 0
50
51 |  |  |  |  | Total Inspectors |  |  | 0
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Units | Per Unit | Cost
1
2 | Project & Construciton Management
3 | R T Air Fares |  |  |  |  | 100 | 2000 | 200000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 50 | 4100 | 205000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 35 | 2000 | 70000
6 | Misc expenditures |  |  |  |  | 1 | 75000 | 75000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 1800 | 52 | 93600
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 6 | 2000 | 12000
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 15 | 4100 | 61500
16 | Auto Rental for Eng Days at Site |  |  |  |  | 75 | 150 | 11250
17 | Misc Travel Expentitures |  |  |  |  | 1 | 35000 | 35000
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 763.35
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36

## 1900 Sales Tax
SALES TAXES
[5 empty] | (1,000's) |  |  | 1900
Project Name: |  | CVG/SIDOR Power Plant B (VII EA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG/SIDOR |  |  |  |  | Quote No: | T 1002A-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WTS/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Total | State | Total
No. | [5 empty] | Cost | Tax | Taxes
1
2 | Major Mechanical Equipment |  |  |  |  | 11981 | 0.08 | 958.48
3
4 | Major Electrical Equipment |  |  |  |  | 2679 | 0.08 | 214.32
5
6 | Substation Equipment |  |  |  |  | 68 | 0.08 | 5.44
7
8 | DCS Eqipment |  |  |  |  | 700.04 | 0.08 | 56.0032
9
10 | Instrument |  |  |  |  | 215 | 0.08 | 17.2
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28 |  |  | Total Cost of Plant Sales Taxes |  |  |  |  | 0