## Recap
ProEnergy EPC
Job Description: |  |  | "1 ea GE VII FA S.C. and 1 ea VII EA S.C. Dual Fuel"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  |  | 2010-01-25
I. Balance of Plant
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 509.2593 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 254.6296 | calc
|  | 103 | Concrete Foundations |  |  | 11228.7037 | 1459.7315 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 481.3519 | calc
|  | 106 | Gravel - Sand |  |  |  | 230.7093 | calc
|  | 107 | Structual Steel |  |  |  | 119.5 | calc
|  | 108 | Fencing |  |  |  | 84.9 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 3140.0815 |  | 3140.0815
| 200 Buildings | [5 empty] | 153 | calc | 153
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 7440 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 11340 | 857.5353 | calc
|  | 330 | Mechanical Subcontractor |  |  | 37600.2 | 2843.3422 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 750 | calc
[7 empty] | 11890.8775 |  | 11890.8775
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 4028.8 | calc
|  | 420 | Substation Equipment |  |  |  | 0 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 29710.8 | 2246.7426 | calc
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 850 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 19440 | 1470.0606 | calc
[7 empty] | 8595.6032 |  | 8595.6032
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 165 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 972 | 73.503 | calc
[7 empty] | 238.503 |  | 238.503
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 125 | calc
|  | 620 | Telephone System |  |  |  | 10 | calc
|  | 630 | Public Address System |  |  |  | 10 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 145 |  | 145
700 Plant Erection
|  | 700 | Plant Erection |  |  | 61722 | 4667.4423 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 160785 | 4667.4423 |  | 4667.4423
| 800 Equipment Rental | [5 empty] | 2444 | calc | 2444
| 900 Painting | [5 empty] | 335 | calc | 335
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 670.95 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 0 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 0 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 670.95 |  | 670.95
| 1100 Site Costs | [5 empty] | 494.4 | calc | 494.4
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 1005 | calc
|  | 1202 | Local Eng |  |  |  | 365 | calc
[7 empty] | 1370 |  | 1370
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 1207 | calc
|  | 1320 | Inspectors |  |  |  | 299 | calc
[7 empty] | 1506 |  | 1506
| 1400 Travel & Perdiem | [5 empty] | 929.2 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 929.2 |  | 929.2
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 270 | 2500 | 675 | plgd /1000
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 30 | 2000 | 60 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 0 | 2000 | 0 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 90 | 2500 | 225 | plgd /1000
|  | 1507 | Controls Rep |  | 50 | 2500 | 125 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 1085 |  | 1085
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 25 | plgd /1000
|  | 1602 | Concrete |  |  |  | 90 | plgd /1000
|  | 1603 | X Ray |  |  |  | 90 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 140 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 40 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 385 |  | 385
| 1700 Legal | [5 empty] | 50 | plgd /1000 | 50
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 500 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 500 |  | 500
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 400 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 3% | 13378.8 | 401.364 | calc
|  | 2150 | Labor Contingency |  | 3% | 12158.626 | 364.7588 | calc
[7 empty] | 1166.1228 |  | 1166.1228
[5 empty] | BOP Cost |  |  |  | 39766.1803
[5 empty] | % Markup |  |  | 20% | 7953.2361
[5 empty] | BOP Sales Price |  |  |  | 47719.4163

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [5 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [5 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Clearing/Grubbing |  |  | 550 | 500 | 1 | 275000 | 10185.1852 | 50 | 509259.2593
2
3 | Demolition
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Containment Systems
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
509.2593

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
7 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
8 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
9 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
10 | [9 empty] | 12
11 | Main Plant Area |  |  |  | 550 | 500 | 1 | 275000 | 10185.1852 | 25 | 254629.6296
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 254.6296

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [7 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [7 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5 | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy | E=Est
1 | POWER ISLAND | [8 empty] | 650
2 | GT Generators |  |  | 1 | 150 | 20 | 6 | 18000 | 666.6667 | 650 | 433333.3333 | 3333.3333
3 | Exhaust Stack |  |  | 1 | 35 | 35 | 6 | 7350 | 272.2222 | 650 | 176944.4444 | 1361.1111
4 | HRSG |  |  | 0 | 75 | 16 | 4 | 0 | 0 | 650 | 0 | 0
5 | SCR |  |  | 0 | 52 | 16 | 4 | 0 | 0 | 650 | 0 | 0
6 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
7 | GTG Fin Fan LO Coolers |  |  | 12 | 20 | 20 | 1 | 4800 | 177.7778 | 650 | 115555.5556 | 888.8889
8 | STG Inlet Chillers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
9 | STG Condenser Fndn |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
10 | Aux Skid(s) for GTG |  |  | 2 | 30 | 30 | 1 | 1800 | 66.6667 | 650 | 43333.3333 | 333.3333
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | 1 | 20 | 8 | 2 | 320 | 11.8519 | 650 | 7703.7037 | 59.2593
16 | Fuel Gas GTG Meter Skid |  |  | 1 | 20 | 6 | 2 | 240 | 8.8889 | 650 | 5777.7778 | 44.4444
17 | Fin Fan L O Coolers |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 650 | 0 | 0
18 | Gas Compressors |  |  | 3 | 40 | 15 | 4 | 7200 | 266.6667 | 650 | 173333.3333 | 1333.3333
19 | Fuel Gas Plant Metering Skid |  |  | 1 | 25 | 8 | 2 | 400 | 14.8148 | 650 | 9629.6296 | 74.0741
20 | Comp Fin Fans |  |  | 3 | 20 | 20 | 2 | 2400 | 88.8889 | 650 | 57777.7778 | 444.4444
21 | Waste Oil/Water Storage Tank |  |  | 1 | 15 | 12 | 1 | 180 | 6.6667 | 650 | 4333.3333 | 33.3333
22 | Oily Water Separator |  |  | 1 | 30 | 20 | 0.5 | 300 | 11.1111 | 650 | 7222.2222 | 55.5556
23 | Lubricant Storage Area |  |  | 1 | 45 | 30 | 1 | 1350 | 50 | 650 | 32500 | 250
24 | Instrument Air Comp Skid |  |  | 1 | 10 | 8 | 1 | 80 | 2.963 | 650 | 1925.9259 | 14.8148
25 | Pipe Rack Stanchons |  |  | 14 | 2.5 | 2.5 | 6 | 525 | 19.4444 | 650 | 12638.8889 | 97.2222
26 | 15KV Cable Tray Stanchons |  |  | 4 | 2.5 | 2.5 | 6 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
27 | Fire Water Pump Skid |  |  | 0 | 15 | 30 | 1 | 0 | 0 | 650 | 0 | 0
28 | Area Light Poles |  |  | 4 | 2.5 | 3 | 5 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
29 | Aux Trans fndns |  |  | 4 | 10 | 15 | 1.5 | 900 | 33.3333 | 650 | 21666.6667 | 166.6667
30 | Cable Trenches see est |  |  | 1 | 220 | 12 | 0.5 | 1320 | 48.8889 | 650 | 31777.7778 | 244.4444
31 | Water Treatment Plant |  |  | 0 | 40 | 50 | 1 | 0 | 0 | 650 | 0 | 0
32 | DFO Forwarding Pump Skid |  |  | 1 | 15 | 8 | 2 | 240 | 8.8889 | 650 | 5777.7778 | 44.4444
33 | DFO Filter Skid |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
34 | BFW Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
35 | Demin Water Pump skid |  |  | 1 | 15 | 8 | 1 | 120 | 4.4444 | 650 | 2888.8889 | 22.2222
36 | Demin Stg Tanks ____ Gal |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
37 | Demin Forwarding Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
38 | Chemical Injection Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
39 | Raw Water Tank Base |  |  | 0 | 40 | 40 | 11 | 0 | 0 | 650 | 0 | 0
40 | Fire Water Tank base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
41 | Emer Generator Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
42
43 | BUILDINGS
44 | Control Bldg/Office |  |  | 0 | 50 | 60 | 1 | 0 | 0 | 650 | 0 | 0
45 | Warehouse/Maintenance |  |  | 0 | 60 | 75 | 0 | 0 | 0 | 650 | 0 | 0
46 | Water Treatment Bldg |  |  | 0 | 150 | 75 | 1 | 0 | 0 | 650 | 0 | 0
47 | Gas Compressor Bldg |  |  | 1 | 90 | 45 | 1 | 4050 | 150 | 650 | 97500 | 750
48 | Electrical Bldg |  |  | 0 | 42 | 20 | 1 | 0 | 0 | 650 | 0 | 0
49 | Pwr Blk Utility Bldg's |  |  | 1 | 40 | 20 | 1 | 800 | 29.6296 | 650 | 19259.2593 | 148.1481
50 | Substation Bldg |  |  | 1 | 15 | 12 | 1 | 180 | 6.6667 | 650 | 4333.3333 | 33.3333
51 | Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
52 | Liquid Fuel Unloading |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
53 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
54 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
55
56 | SUBSTATION
57 | GSU Transformer |  |  | 1 | 35 | 35 | 4 | 4900 | 181.4815 | 650 | 117962.963 | 907.4074
58 | (___)KV SF6 Circuit Breaker |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 650 | 5416.6667 | 41.6667
59 | (___)KV Disc Switch w/ Stand |  |  | 1 | 10 | 15 | 1 | 150 | 5.5556 | 650 | 3611.1111 | 27.7778
60 | Dead End Tower |  |  | 2 | 15 | 10 | 3 | 900 | 33.3333 | 650 | 21666.6667 | 166.6667
61 | Transmission Line Poles |  |  | 0 | 5 | 5 | 20 | 0 | 0 | 650 | 0 | 0
62 | Insulator Support Base |  |  | 21 | 3 | 3 | 5 | 945 | 35 | 650 | 22750 | 175
63 | PT Support Base |  |  | 3 | 3 | 3 | 5 | 135 | 5 | 650 | 3250 | 25
64 | Static Pole Base |  |  | 2 | 5 | 5 | 6 | 300 | 11.1111 | 650 | 7222.2222 | 55.5556
65
66
67 |  |  | Total Cost of Foundations | [5 empty] | 2245.7407 |  | 1459.7315 | 11228.7037
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [7 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [7 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description | [7 empty] | Cu | Price | Total | Q=Quote
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price | E=Est
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls | [8 empty] | 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 550 | 0
2 | Gen Removal Areas |  |  | 50 | 30 | 1 | 1500 | 55.5556 | 550 | 30555.5556
3 | Turbine Removal Areas |  |  | 50 | 30 | 1 | 1500 | 55.5556 | 550 | 30555.5556
4 | Entry Ways |  |  | 20 | 8 | 0.5 | 80 | 2.963 | 550 | 1629.6296
5 | Walk ways |  |  | 150 | 6 | 0.5 | 450 | 16.6667 | 550 | 9166.6667
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 550 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 900 | 20 | 0.7 | 12600 | 466.6667 | 550 | 256666.6667
12 | Parking Lot |  |  | 200 | 75 | 0.5 | 7500 | 277.7778 | 550 | 152777.7778
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 481.3519
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [7 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [7 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [7 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price | E=Est
1
2 | Main Plant Area (less substa) |  |  | 1 | 550 | 500 | 0.5 | 137500 | 5092.5926 | 8453.7037 | 25 | 211342.5926
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 25 | 0
5
6 | Substation |  |  | 0 | 400 | 150 | 1 | 0 | 0 | 0 | 25 | 0
7
8 | Road ways |  |  | 1 | 900 | 20 | 0.7 | 12600 | 466.6667 | 774.6667 | 25 | 19366.6667
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | [8 empty] | 230.7093

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [5 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [5 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | # of | Qty | Price | Total | Q=Quote
No. | [5 empty] | Lbs / Tons |  |  | Price | E=Est
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 8 | 4000 | 32000
4 | [8 empty] | 0
5 | 18 KV ISO Phase Bus Stanchons | [5 empty] | 5 | 3500 | 17500
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 1 | 20000 | 20000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 0 | 0 | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 0 | 0 | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 50000 | 50000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 119.5

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | or Ftg | Price | Price | E=Est
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 1500 | 15 | 22500
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 1800 | 23 | 41400
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 500 | 23 | 11500
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 2 | 4000 | 8000
10 | Motor Operated Double Gate(s) |  |  |  |  | 0 | 7000 | 0
11 | Personnel Gate(s) |  |  |  |  | 3 | 500 | 1500
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 0 | 10000 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 84.9

## 109 Architectual
ARCHITECTUAL TREATMENT
[5 empty] | (1,000's) |  |  | 109
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | or Ftg | Price | Price | E=Est
1
2 | Trees and/or Shrubs - Revegetation
3 | Boundry Road |  |  |  |  | 0 | 0 | 0
4 | Within site |  |  |  |  | 0 | 0 | 0
5 | [5 empty] | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39
40 |  |  | Total Cost of Arch Treatment |  |  |  |  | 0

## 110 Evap Pond
EVAPORATION POND
|  |  |  | (1,000's) | [5 empty] | 110
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yard | cy | Price | E=Est
1 | Storm Water Evap Pond |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7
8
9
10
11 | [8 empty] | Price
12 | [6 empty] | sf |  | sf
13 | Liner |  |  | 0 | 0 |  | 0 |  | 3 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 | [9 empty] | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [5 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [5 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [5 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price | E=Est
1 | Fuel Gas Compressor Shed |  |  |  | 80 | 35 | 2800 | 45 | 126000
2 | Control/Office |  |  |  | 0 | 50 | 0 | 55 | 0
3 | Water Treatment |  |  |  | 0 | 0 | 0 | 0 | 0
4 | Electric Bldg |  |  |  | 0 | 15 | 0 | 50 | 0
5 | Warehouse/Maintenance |  |  |  | 0 | 60 | 0 | 45 | 0
6 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0
9 | Pump Room |  |  |  | 30 | 20 | 600 | 45 | 27000
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 0 | 20 | 0 | 45 | 0
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 153

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [9 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [9 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [9 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
[15 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
| GTG | [5 empty] | 3% |  | 9
1 | GTG Type - GE VII FA Reassembley |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 10 | 120 | 10800 | 75.6204 | 816700.32 |  | E
2 | Lube oils and Chemicals |  |  | 1 | 150000 | 150000 | 4500 | 4500 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754 |  | E
3 | Exhaust Stack |  |  | 1 | 1500000 | 1500000 | 200000 | 200000 | 9 | 6 | 4 | 216 | 75.6204 | 16334.0064 |  | E
4 | Project Grouting |  |  | 1 | 150000 | 150000 | 4500 | 4500 | 9 | 4 | 5 | 180 | 75.6204 | 13611.672 |  | E
5 | GTG Tools |  |  | 1 | 125000 | 125000 | 3750 | 3750 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
6 | Anchor Bolts |  |  | 1 | 150000 | 150000 | 4500 | 4500 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
7 | Lube Oil Cooler Fin Fans |  |  | 12 | 35000 | 420000 | 10000 | 120000 | 9 | 4 | 10 | 4320 | 75.6204 | 326680.128
| Lube Oil Circulation Pumps 100 HP |  |  | 2 | 50000 | 100000 | 2000 | 4000 | 9 | 4 | 4 | 288 | 75.6204 | 21778.6752
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
31 | Inlet Evap Cooling System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
33 | Cooling Water Circulation Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 2 | 1700000 | 3400000 | 25000 | 50000 | 9 | 6 | 12 | 1296 | 75.6204 | 98004.0384 |  | E
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 1 | 325000 | 325000 | 9750 | 9750 | 9 | 4 | 4 | 144 | 75.6204 | 10889.3376 |  | E
40 | Fuel Gas Turbine Metering Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
41 | Fuel Gas Filter Skid & Mnt (750) KW Htr(Htr in Elect) |  |  | 1 | 220000 | 220000 | 6600 | 6600 | 9 | 4 | 6 | 216 | 75.6204 | 16334.0064 |  | E
42 | ESD Valve, ___" ___# |  |  | 1 | 35000 | 35000 | 1050 | 1050 | 9 | 2 | 2 | 36 | 75.6204 | 2722.3344 |  | E
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
46 | Metering Skid |  |  | 1 | 200000 | 200000 | 6000 | 6000 | 9 | 4 | 5 | 180 | 75.6204 | 13611.672 |  | E
47 | Forwarding Pump Skid |  |  | 1 | 40000 | 40000 | 1200 | 1200 | 9 | 4 | 7 | 252 | 75.6204 | 19056.3408 |  | E
48 | Transfer Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
49 | Fuel Heating |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
50 | Filters |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 9 | 3 | 4 | 216 | 75.6204 | 16334.0064 |  | E
51 | Centrifuge |  |  | 0 | 350000 | 0 | 70000 | 0 | 9 | 6 | 8 | 0 | 75.6204 | 0 |  | E
52 | Injection Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
53 | Storage Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 8 | 0 | 75.6204 | 0 |  | E
54 | Day Tank 500000 gal |  |  | 0 | 600000 | 0 | 25000 | 0 | 9 | 6 | 4 | 0 | 75.6204 | 0 |  | E
55
56 | Water Supply System
57 | Raw Water Storage Tank M gal |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
58 | Raw Water Supply Pumps |  |  | 2 | 25000 | 50000 | 1500 | 3000 | 9 | 3 | 3 | 162 | 75.6204 | 12250.5048 |  | E
59 | Raw Water Forwarding Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 0 | 85000 | 0 | 0 | 0 | 9 | 3 | 4 | 0 | 75.6204 | 0 |  | E
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
64 | Demin Treatment System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
66 | Demin water fiberglass tank |  |  | 0 | 25000 | 0 | 0 | 0 | 9 | 4 | 6 | 0 | 75.6204 | 0 |  | E
67 | Demin forwarding pumps |  |  | 2 | 25000 | 50000 | 1500 | 3000 | 9 | 3 | 4 | 216 | 75.6204 | 16334.0064 |  | E
68 | Turbine Wash Water Skid and Tank |  |  | 1 | 85000 | 85000 | 2550 | 2550 | 9 | 4 | 6 | 216 | 75.6204 | 16334.0064 |  | E
69 | Demin Water Tank, SS 300M gal |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 1 | 60000 | 60000 | 1800 | 1800 | 9 | 4 | 7 | 252 | 75.6204 | 19056.3408 |  | E
73 | Oily Waste Tank 10000 gal |  |  | 1 | 10000 | 10000 | 300 | 300 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524 |  | E
74 | Waste Water Tank 10000 gal |  |  | 1 | 10000 | 10000 | 300 | 300 | 9 | 3 | 3 | 81 | 75.6204 | 6125.2524 |  | E
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 2 | 15000 | 30000 | 900 | 1800 | 9 | 3 | 3 | 162 | 75.6204 | 12250.5048 |  | E
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
79 | Fire Water System, valves, hydrants, monitors |  |  | 1 | 150000 | 150000 | 5500 | 5500 | 9 | 6 | 20 | 1080 | 75.6204 | 81670.032 |  | E
80 | [15 empty] | E
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 1 | 80000 | 80000 | 2400 | 2400 | 9 | 4 | 6 | 216 | 75.6204 | 16334.0064 |  | E
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
89 | Anti-Icing Ducting |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
90 | H2 Bottles |  |  | 4 | 15000 | 60000 | 1800 | 7200 | 9 | 2 | 2 | 144 | 75.6204 | 10889.3376 |  | E
91 | [8 empty] | 9
92
93 |  |  | Total Cost |  |  | 7440 |  | 446.1 |  |  |  | 20889
94 | [13 empty] | 1579.6345
[9 empty] | Total Manhours |  |  | 20889
[9 empty] | Times Prod Factor |  | 1.8 | 37600.2 | 75.6204 | 2843.3422
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 750000 | 750000 | 22500 | 22500 | 9 | 10 | 70 | 6300 | 75.6204 | 476408.52 |  | E
96 |  |  | Total Cost |  |  | 750 |  | 22.5 |  |  |  | 6300 |  | 476408.52
97
98 | [8 empty] | Total Manhours |  |  | 6300
99 | [8 empty] | Times Prod Factor |  | 1.8 | 11340 | 75.6204 | 857.5353
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 40
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 14
58
[8 empty] | Contr G&A 8% |  | 4.64
[8 empty] | Contr Mark up 15% |  | 8.7
71.34
[7 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K128: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N120: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [11 empty] | Date: |  | 2010-01-25
Customer: |  | CVG- SIDOR | [11 empty] | Quote No: |  | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [11 empty] | Est By: |  | WT/DW/CD
Bid Due Date: |  | 2010-01-25
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | Power Island Equipment | [7 empty] | 3% |  | 9
2 | Gas Turbine Generator - GE VII EA Install |  |  |  |  | 1 |  |  | 0 |  | 9 | 12 | 90 | 9720 | 75.6204 | 735030.288 |  | E
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
6 | GTG LO FIN FAN Coolers |  |  |  |  | 12 |  |  | 0 |  | 9 | 4 | 4 | 1728 | 75.6204 | 130672.0512 |  | E
7 | Chiller Package |  |  |  |  | 0 |  |  | 0 |  | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
8 | Water Treatment Package |  |  |  |  | 0 |  |  | 0 |  | 9 | 0 | 0 | 0 | 75.6204 | 0 |  | E
9 | [13 empty] | 0 | 75.6204 | 0
10 | 18KV | [13 empty] | 75.6204
11 | Generator Breaker(s) 8000 Amp |  |  |  |  | 1 | 580000 | 580000 | 25000 | 25000 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344 |  | E
12 | Distribution Breaker(s) |  |  |  |  | 2 | 75000 | 150000 | 4500 | 9000 | 9 | 4 | 4 | 288 | 75.6204 | 21778.6752 |  | E
13 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 0 | 75.6204 | 0 |  | E
14 | [5 empty] | 0 | 350000 | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 75.6204 | 0 |  | E
15 | ISO Phase Bus for 18KV feed to GSU |  |  |  |  | 1 | 2000000 | 2000000 | 50000 | 50000 | 9 | 5 | 20 | 900 | 75.6204 | 68058.36
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 6 | 0 | 75.6204 | 0
17 | 5KV | [13 empty] | 75.6204
18 | Distribution Breaker(s) |  |  |  |  | 4 | 65000 | 260000 | 7800 | 31200 | 9 | 2 | 5 | 360 | 75.6204 | 27223.344 |  | E
19 | Dist Panel and Generator Sync |  |  |  |  | 0 | 150000 | 0 | 5000 | 0 | 9 | 3 | 6 | 0 | 75.6204 | 0 |  | E
20 | MCC's |  |  |  |  | 2 | 30000 | 60000 | 1500 | 3000 | 9 | 2 | 4 | 144 | 75.6204 | 10889.3376 |  | E
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 6 | 0 | 75.6204 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0
23 | 600V | [13 empty] | 75.6204
24 | Distribution Panel(s) |  |  |  |  | 1 | 300000 | 300000 | 9000 | 9000 | 9 | 3 | 10 | 270 | 75.6204 | 20417.508 |  | E
25 | GTG MCC(s) |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 3 | 7 | 189 | 75.6204 | 14292.2556 |  | E
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 4 | 0 | 75.6204 | 0 |  | E
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0 |  | E
28 | BOP MCC(s) |  |  |  |  | 1 | 35000 | 35000 | 1050 | 1050 | 9 | 2 | 3 | 54 | 75.6204 | 4083.5016 |  | E
29 | Water Treatment MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.3 | 0 | 75.6204 | 0 |  | E
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 8 | 0 | 75.6204 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0
32 | Aux Transformer(s) | [13 empty] | 75.6204
33 | 15/5KV ___3_ MVA |  |  |  |  | 2 | 200000 | 400000 | 15000 | 30000 | 9 | 3 | 8 | 432 | 75.6204 | 32668.0128 |  | E
34 | 15/600V ___2_ MVA |  |  |  |  | 1 | 100000 | 100000 | 10000 | 10000 | 9 | 3 | 5 | 135 | 75.6204 | 10208.754 |  | E
35 | 600/120/208V ________ KVA |  |  |  |  | 2 | 5000 | 10000 | 300 | 600 | 9 | 2 | 4 | 144 | 75.6204 | 10889.3376 |  | E
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
38 | Area Lighting | [13 empty] | 75.6204
39 | Poles _______ High |  |  |  |  | 4 | 1500 | 6000 | 500 | 2000 | 9 | 2 | 1 | 72 | 75.6204 | 5444.6688 |  | E
40 | Floodlights _______ Watts |  |  |  |  | 12 | 650 | 7800 | 50 | 600 | 9 | 2 | 0.5 | 108 | 75.6204 | 8167.0032 |  | E
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 60 | 0 | 75.6204 | 0
43 | Other Systems |  |  |  |  | 0 | [8 empty] | 75.6204
44 | UPS |  |  |  |  | 1 | 15000 | 15000 | 1500 | 1500 | 9 | 2 | 4 | 72 | 75.6204 | 5444.6688 |  | E
45 | DC |  |  |  |  | 1 | 25000 | 25000 | 1500 | 1500 | 9 | 2 | 5 | 90 | 75.6204 | 6805.836 |  | E
46 | Cathodic Protection |  |  |  |  | 1 | 20000 | 20000 | 600 | 600 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344 |  | E
47 | Lightning Protection |  |  |  |  | 1 | 20000 | 20000 | 600 | 600 | 9 | 4 | 10 | 360 | 75.6204 | 27223.344 |  | E
48 | [11 empty] | 0 | 0 | 0 | 75.6204 | 0
49 | [14 empty] | 75.6204
50 | Temporary Electric |  |  |  |  | 1 | 40000 | 40000 | 1200 | 1200 | 9 | 2 | 40 | 720 | 75.6204 | 54446.688 |  | E
51 | Black Start Generator 3 MW |  |  |  |  | 0 | 550000 | 0 | 35000 | 0 | 9 | 4 | 15 | 0 | 75.6204 | 0 |  | E
52 | [6 empty] | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 75.6204 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 4028.8 |  | 176.85 |  |  |  | 16506 |  | 1248.1903
[12 empty] | Productivity | 1.8 | 29710.8 | 75.6204 | 2246.7426
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 850000 | 850000 | 25500 | 25500 | 9 | 10 | 120 | 10800 | 75.6204 | 816700.32 |  | E
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 850 |  | 25.5 |  |  |  | 10800 |  | 816.7003
58 | [10 empty] | Total Manhours |  |  | 10800
59 | [10 empty] | Times Prod Factor |  | 1.8 | 19440 | 75.6204 | 1470.0606
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 40
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 14
58
[13 empty] | Contr G&A 8% |  | 4.64
[13 empty] | Contr Mark up 15% |  | 8.7
71.34
[12 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N87: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q79: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [12 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [12 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [12 empty] | Est By:
Bid Due Date: |  | 2010-01-25
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | [8 empty] | 3% |  | 9
2 | Main Power Transformer 176 MVA 18KV/115KV | [5 empty] | 2400000 | 0 | 250000 | 0 | 9 | 8 | 15 | 0 | 75.6204 | 0 |  | E
| Aux Power Transformer 15 MVA 230KV/5KV | [5 empty] | 0 | 0 | 75000 | 0 | 9 | 4 | 6 | 0 | 75.6204 | 0
3 | SF6 Circuit Breaker(s) ____ KV | [5 empty] | 75000 | 0 | 5000 | 0 | 9 | 2 | 10 | 0 | 75.6204 | 0 |  | E
4 | Disconnect Switches ______ KV | [5 empty] | 25000 | 0 | 4000 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0 |  | E
5 | Station Post Insulators ____ KV | [5 empty] | 500 | 0 | 0 | 0 | 9 | 2 | 0.05 | 0 | 75.6204 | 0 |  | E
6 | Insulator Stanchons ______ High | [5 empty] | 2500 | 0 | 0 | 0 | 9 | 1 | 0.5 | 0 | 75.6204 | 0 |  | E
7 | Insulator Stanchons ______ High | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.4 | 0 | 75.6204 | 0 |  | E
8 | Dead End Tower(s) | [5 empty] | 45000 | 0 | 0 | 0 | 9 | 6 | 5 | 0 | 75.6204 | 0 |  | E
9 | Alum Bus ______ Dia | [5 empty] | 20 | 0 | 5 | 0 | 9 | 1 | 0.08 | 0 | 75.6204 | 0 |  | E
10 | Alum Bus Conn's | [5 empty] | 30 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 75.6204 | 0 |  | E
11 | Alum Bus End Plugs _____ Dia | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.05 | 0 | 75.6204 | 0 |  | E
12 | Alum Bus Support Clamps | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 75.6204 | 0 |  | E
13 | Alum Bus "V" Conn's | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 75.6204 | 0 |  | E
14 | Static Wire Poles, ____ High | [5 empty] | 5000 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 75.6204 | 0 |  | E
15 | Area Lighting Poles, ____ High | [5 empty] | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 75.6204 | 0 |  | E
16 | Flood Lights, ______ Watts | [5 empty] | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0 |  | E
17 | #4/0 Grounding Conductor | [5 empty] | 30000 | 0 | 0 | 0 | 9 | 4 | 30 | 0 | 75.6204 | 0 |  | E
18 | 3/4"x10'-0" Ground Rods & Clamps | [5 empty] | 0 | 0 | 0 | 0 | 9 | 1 | 0.04 | 0 | 75.6204 | 0 |  | E
19 | #90 Cadweld Shots | [5 empty] | 0 | 0 | 0 | 0 | 9 | 2 | 0.3 | 0 | 75.6204 | 0 |  | E
20 | Metering CT's & CPT's | [5 empty] | 50000 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0 |  | E | 0
21 | Station Metering w/ In & Out Capabilities | [5 empty] | 50000 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 75.6204 | 0 |  | E
22 | Station Protective Relay(s) | [5 empty] | 50000 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0 |  | E
23 | Station RTU | [5 empty] | 0 | 0 | 0 | 0 | 9 | 3 | 5 | 0 | 75.6204 | 0 |  | E
24 | 125V DC System | [5 empty] | 20000 | 0 | 0 | 0 | 9 | 2 | 4 | 0 | 75.6204 | 0 |  | E
25 | Transmission Line Poles | [5 empty] | 20000 | 0 | 0 | 0 | 9 | 6 | 2 | 0 | 75.6204 | 0 |  | E
26 | Transmission Line Strain Insulators | [5 empty] | 500 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 75.6204 | 0 |  | E | 0
27 | Cable Bus, Type _____, Size _____ | [5 empty] | 75000 | 0 | 0 | 0 | 9 | 6 | 30 | 0 | 75.6204 | 0 |  | E
28 | Main Power Transformer Oil, ______ Gal | [5 empty] | 120000 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 75.6204 | 0 |  | E
29 | Main Power Transformer Dress Out & Test | [5 empty] | 75000 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 75.6204 | 0 |  | E
30 | Fiber Optic Cable w/ Messenger Cable | [5 empty] | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 75.6204 | 0 |  | E | 0
31 | Fiber Optic Cable Fittings & Terminations | [5 empty] | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 75.6204 | 0 |  | E
32 | [10 empty] | 9 |  |  |  | 75.6204
33 | [10 empty] | 9 |  |  |  | 75.6204
34 | [10 empty] | 9 |  |  |  | 75.6204
35 | [10 empty] | 9 |  |  |  | 75.6204 | 0
36 |  |  | Total Cost of Substation Equipment |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
[12 empty] | Total Hours |  | 0
[12 empty] | Prod Factor | 1.8 | 0 | 75.6204 | 0
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 40
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 14
58
[13 empty] | Contr G&A 8% |  | 4.64
[13 empty] | Contr Mark up 15% |  | 8.7
71.34
[12 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N62: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q54: Insert Rate Here:

## 510 CEMS
CEM's
[5 empty] | (1,000's) |  |  | 510
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Cems | Cost | Cost | E=Est
1
2 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 225000 | 0
3
4 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 130000 | 0
5
6 | Installation Support |  |  |  |  | 0 | 18000 | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of CEM's |  |  |  |  | 0

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [8 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [8 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [8 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
[13 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | [6 empty] | 9
2 | Instrumentation for GTG |  |  | 1 | 125000 | 125000 | 9 | 2 | 10 | 180 | 75.6204 | 13611.672 |  | E
3 | [6 empty] | 9 |  |  |  | 75.6204 | 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 75.6204 | 0 |  | E
5 | [6 empty] | 9 |  |  |  | 75.6204
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 75.6204 | 0 |  | E
7 | [6 empty] | 9 |  |  |  | 75.6204
8 | Instrumentation for Injection Water Treatment |  |  | 0 | 0 | 0 | 9 | 2 | 20 | 0 | 75.6204 | 0 |  | E
9 | [6 empty] | 9 |  |  |  | 75.6204
10 | Instrumentation for Waste Water Treatment |  |  | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 75.6204 | 0 |  | E
11 | [6 empty] | 9 |  |  |  | 75.6204
12 | Instrumentation for gas compressors |  |  | 2 | 20000 | 40000 | 9 | 4 | 5 | 360 | 75.6204 | 27223.344 |  | E
13 | [6 empty] | 9 |  |  |  | 75.6204
14 | Labor to Install CEMS relocated from KY |  |  | 0 | 0 | 0 | 9 | 4 | 9 | 0 | 75.6204 | 0 |  | E
15 | [6 empty] | 9 |  |  |  | 75.6204
16 | [6 empty] | 9 |  |  |  | 75.6204
17 | [6 empty] | 9 |  |  |  | 75.6204
18 | [6 empty] | 9 |  |  |  | 75.6204
19 | [6 empty] | 9 |  |  |  | 75.6204
20 | [6 empty] | 9 |  |  |  | 75.6204
21 | [6 empty] | 9 |  |  |  | 75.6204
22 | [6 empty] | 9 |  |  |  | 75.6204
23 |  |  | Total Cost of Plant Instrumentation |  |  | 165 |  |  |  | 540 |  | 40.835
[8 empty] | Total Hours |  | 540
[8 empty] | Prod Factor | 1.8 | 972 | 75.6204 | 73.503
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 40
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 14
58
[9 empty] | Contr G&A 8% |  | 4.64
[9 empty] | Contr Mark up 15% |  | 8.7
71.34
[8 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [6 empty] | Cost | Cost | E=Est
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 75000 | 75000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 1 | 25000 | 25000
5
6 | Documentation |  |  |  |  | 1 | 25000 | 25000
7
8 |  |  |  |  | Total DCS |  |  | 125
9
10 | PBX Communications System |  |  |  |  | 1 | 10000 | 10
11
12 | Loud Speaker System |  |  |  |  | 1 | 10000 | 10
13
14 | TV / Security System |  |  |  |  | 0 | 10000 | 0
15
16
17
[7 empty] | taxable | 100020

## 700 Erection
PLANT Disassy and Re- ERECTION
(1,000's)
700
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est
1 |  |  |  |  | 9
2 | GTG VII FA Dissassy |  |  | 0 | 9 | 24 | 90 | 0 | 75.6204 | 0 | E
3 |  |  |  |  | 9 |  |  |  | 75.6204
4 | GTG VII FA Re-erection |  |  | 1 | 9 | 24 | 150 | 32400 | 75.6204 | 2450100.96 | E
5 |  |  |  |  | 9 |  |  |  | 75.6204
6 | SCR Erection |  |  | 0 | 9 | 10 | 60 | 0 | 75.6204 | 0 | E
7 |  |  |  |  | 9 |  |  |  | 75.6204
8 | Water Treatment and FW Systems |  |  | 0 | 9 | 6 | 20 | 0 | 75.6204 | 0 | E
9 |  |  |  |  | 9 |  |  |  | 75.6204
10 | Waste Water Treatment System |  |  | 0 | 9 | 6 | 20 | 0 | 75.6204 | 0 | E
11 |  |  |  |  | 9 |  |  |  | 75.6204
12 | BOP Equip Erection |  |  | 1 | 9 | 6 | 15 | 810 | 75.6204 | 61252.524 | E
13 |  |  |  |  | 9 |  |  |  | 75.6204
14 | Gas Compressor Erection |  |  | 2 | 9 | 6 | 10 | 1080 | 75.6204 | 81670.032 | E
15 |  |  |  |  | 9 |  |  |  | 75.6204
16 | Evap Cooling Erection |  |  | 0 | 9 | 4 | 4 | 0 | 75.6204 | 0 | E
17 |  |  |  |  | 9 |  |  |  | 75.6204
18 | Fire Water Pump Skid |  |  | 0 | 9 | 4 | 3 | 0 | 75.6204 | 0 | E
19 |  |  |  |  | 9 |  |  |  | 75.6204
20 | STG Erection |  |  | 0 | 9 | 12 | 36 | 0 | 75.6204 | 0 | E
21 |  |  |  |  | 9 |  |  |  | 75.6204
22 | STG Cooling Tower |  |  | 0 | 9 | 8 | 8 | 0 | 75.6204 | 0 | E
23 |  |  |  |  | 9 |  |  |  | 75.6204
24 |  |  |  |  | 9 |  |  |  | 75.6204
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 34290 |  | 2593.0235
[6 empty] | Total Hours |  | 34290
[6 empty] | Prod Factor | 1.8 | 61722 | 75.6204 | 4667.4423
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 40
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 14
58
[7 empty] | Contr G&A 8% |  | 4.64
[7 empty] | Contr Mark up 15% |  | 8.7
71.34
[6 empty] | 45 | Hour Work Week = |  | 75.6204
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL and MISC MATERIALS
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total | Q=Quote
No. | [5 empty] | Units | Unit | Days | Per Day | Cost | E=Est
1 | GTG Equip Rental per ea GTG for Disassy
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 45 | 0 | 4000 | 0
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 90 | 0 | 2000 | 0
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 90 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 0 | 90 | 0 | 70 | 0
8 | 1 ea Man Lift |  |  |  |  | 0 | 0 | 0 | 80 | 0
9 | 2 ea Welders |  |  |  |  | 0 | 90 | 0 | 60 | 0
10
11 | GTG Equip Rental for GTG Re - Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 1 | 60 | 60 | 15000 | 900000
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 1 | 120 | 120 | 5000 | 600000
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 2 | 120 | 240 | 100 | 24000
17 | 2 ea Sky Tracs |  |  |  |  | 2 | 120 | 240 | 100 | 24000
18 | 5 ea Welders |  |  |  |  | 5 | 90 | 450 | 100 | 45000
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 150 | 150 | 3000 | 450000
51 | 2 ea Fork Lifts |  |  |  |  | 1 | 120 | 120 | 100 | 12000
52 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 100 | 0
53 | 2 ea Pick ups |  |  |  |  | 2 | 150 | 300 | 100 | 30000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 1 | 90 | 90 | 100 | 9000
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 15 | 0 | 4000 | 0
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 20 | 0 | 1500 | 0
60 | 2 ea Man Lifts |  |  |  |  | 0 | 20 | 0 | 80 | 0
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64 | Misc materials and crating for disassy |  |  |  |  | 0 |  |  |  | 0
65 | Misc materials for Re - Erection |  |  |  |  | 0 |  |  |  | 350000
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 1770 |  | 2444

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Paint for GTG Package |  |  |  |  | 1 | 200000 | 200000 | E
3
4 | Paint for Exhaust Stack |  |  |  |  | 1 | 75000 | 75000 | E
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0 | E
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 1 | 35000 | 35000 | E
9
10 | Paint for BOP Equipment |  |  |  |  | 1 | 25000 | 25000 | E
11
12 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0 | E
13
14 | Paint for Water Treatment |  |  |  |  | 0 | 15000 | 0 | E
15
16 | Paint for Waste Water Treatment |  |  |  |  | 0 | 15000 | 0 | E
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0 | E
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 335

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 446.1 | 446.1 | E
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 176.85 | 176.85 | E
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 0 | 0 | E
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 22.5 | 22.5 | E
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 25.5 | 25.5 | E
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 670.95

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) | [6 empty] | Date: | 2010-01-25
Customer: |  | CVG- SIDOR | [6 empty] | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn | [6 empty] | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total | Q=Quote
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost | E=Est
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 4 | 7 | 4500 | 126000 |  | E
3 | Porta Potties |  |  |  |  | 4 | 7 | 700 | 19600 |  | E
4 | Water and Ice |  |  |  |  | 4 | 7 | 500 | 14000 |  | E
5 | Fed X |  |  |  |  | 1 | 7 | 400 | 2800 |  | E
6 | Telephone |  |  |  |  | 1 | 7 | 2500 | 17500 |  | E
7 | Office Supplies |  |  |  |  | 1 | 7 | 1500 | 10500 |  | E
8 | [6 empty] | 7
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 7 | 4000 | 28000 |  | E
10 | Misc Items |  |  |  |  | 1 | 7 | 3000 | 21000 |  | E
11 |  |  | Total Monthly Cost | [5 empty] | 239400
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 239400 |  | 239400
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 150000 | E
21 | Cad Station | [8 empty] | 0 | E
22 | Computers | [8 empty] | 10000 | E
23 | Telephone System and Satalite Dish | [8 empty] | 15000 | E
24 | Plotter | [8 empty] | 0 | E
25 | Fax Machine and Printers | [8 empty] | 5000 | E
26 | Misc equip | [8 empty] | 75000 | E
27 | Signs | [8 empty] | 0 | E
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 494.4

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Conceptual Engineering WGPS |  |  |  |  | 1 | 30000 | 30000 | E
3
4 | Detailed Engineering per GTG |  |  |  |  | 1 | 750000 | 750000
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 0 | 0 | 0
11
12 | Detailed Engineering for civil/structural |  |  |  |  | 1 | 155000 | 155000
13
14 | Documentation |  |  |  |  | 1 | 70000 | 70000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 1005

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Soils & Environmental Eng - Soil Test - Topo |  |  |  |  | 1 | 80000 | 80000
3
4 | Civil Engineer |  |  |  |  | 5 | 15000 | 75000
5
6 | Mechanical Engineer |  |  |  |  | 7 | 15000 | 105000
7
8 | Electrical Engineer |  |  |  |  | 7 | 15000 | 105000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 365

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Cost | Total | Q=Quote
No. | [5 empty] | Mos | Per Mo | Cost | E=Est
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 7 | 16000 | 112000 | E
2 | Admin Mgr Months on Project |  |  |  |  | 7 | 8000 | 56000 | E
3 | Scheduler |  |  |  |  | 4 | 8000 | 32000 | E
4 | Purchasing Agent |  |  |  |  | 3 | 8000 | 24000 | E
5 | Expediter |  |  |  |  | 3 | 5000 | 15000 | E
6 | Home Office Logistic Coordinator |  |  |  |  | 0 | 9000 | 0 | E
7
8
9 | [6 empty] | 239000 |  | E
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 7 | 4000 | 28000 | E
18 | Construction Mngr |  |  |  |  | 7 | 16000 | 112000 | E
19 | Contract Cost Admin |  |  |  |  | 0 | 10000 | 0 | E
20 | Scheduler |  |  |  |  | 3 | 8000 | 24000 | E
21 | Mechanical Supervisor |  |  |  |  | 7 | 14000 | 98000 | E
22 | Electrical Supervisor |  |  |  |  | 7 | 14000 | 98000 | E
23 | Civil Supervisor |  |  |  |  | 7 | 14000 | 98000 | E
24 | Clerks |  |  |  |  | 15 | 5000 | 75000 | E
25 | Warehousemen |  |  |  |  | 15 | 5000 | 75000 | E
26 | Draftsman |  |  |  |  | 4 | 6000 | 24000 | E
27 | Security |  |  |  |  | 7 | 15000 | 105000 | E
28 | Safety |  |  |  |  | 7 | 9000 | 63000 | E
29 | QA/QC Mngr |  |  |  |  | 7 | 12000 | 84000 | E
30
31
32 | [6 empty] | 884000 |  | E
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 6 | 14000 | 84000 | E
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0 | E
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 1207
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 6 | 11500 | 69000
47 | Mechanical __ ea ___ mos |  |  |  |  | 8 | 11500 | 92000
48 | Electrical __ ea ___ mos |  |  |  |  | 8 | 11500 | 92000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 4 | 11500 | 46000
50
51 |  |  |  |  | Total Inspectors |  |  | 299000
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | No. | Cost | Total |  | Q=Quote
No. | [5 empty] | Units | Per Unit | Cost |  | E=Est
1
2 | Project & Construciton Management
3 | R T Air Fares |  |  |  |  | 100 | 2000 | 200000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 70 | 4100 | 287000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 14 | 3000 | 42000
6 | Misc expenditures |  |  |  |  | 1 | 150000 | 150000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 2100 | 52 | 109200
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 6 | 2000 | 12000 |  | E
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 15 | 4100 | 61500 |  | E
16 | Auto Rental for Eng Days at Site |  |  |  |  | 450 | 150 | 67500 |  | E
17 | Misc Travel Expentitures |  |  |  |  | 0 | 0 | 0 |  | E
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 929.2
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36

## 1900 Sales Tax
SALES TAXES
[5 empty] | (1,000's) |  |  | 1900
Project Name: |  | CVG-SIDOR Power Plant B (VII FA) |  |  |  |  | Date: | 2010-01-25
Customer: |  | CVG- SIDOR |  |  |  |  | Quote No: | T 1002B-2
Location: |  | Puerto Ordaz, Venn |  |  |  |  | Est By: | WT/DW/CD
Bid Due Date: |  | 2010-01-25
Item |  | Description |  |  |  | Total | State | Total
No. | [5 empty] | Cost | Tax | Taxes
1
2 | Major Mechanical Equipment |  |  |  |  | 8190 | 0.085 | 696.15
3
4 | Major Electrical Equipment |  |  |  |  | 4878.8 | 0 | 0
5
6 | Substation Equipment |  |  |  |  | 0 | 0 | 0
7
8 | DCS Eqipment |  |  |  |  | 100020 | 0 | 0
9
10 | Instrument |  |  |  |  | 165 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28 |  |  | Total Cost of Plant Sales Taxes |  |  |  |  | 0