Table of Contents

1. Executive Summary

EPC

Weekly Report  26 June to 2 July 2010Date: 27-June-10Project: Sidor Site B, Puerto Ordaz Venezuela Written By: Cole Franklin ProEnergy EPC Project Mgr

ProEnergy Site Manager

William Lugo

Cole Franklin

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start-Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary.

This review is for the week from 26 June to 2 July 2010.  Safety is good, housekeeping good, morale is deteriorating.  The commercial issues at Site A are continuing to cause problems at Site B.  If we cannot separate the two sites B will continue to have problems caused by issues at site A.   Engineering drawings show a lack of review and attention to details. Material deliveries are still problematic.  Need to develop a means of tracking material from requisition, purchase, shipment, and finally to site, that allows Site to know where the material is in the cycle.

The 7EA turbine, generator, and aux units were set onto the foundation this week.  The foundation remains a problem, for some undiscovered reason the two pressure grout companies we have contacted have not replied.  I have had the owner of the testing lab company contact a third company who has opened discussions regarding the work of stiffening the foundation  if necessary.  The owner of the testing lab and the grout company are presently on a project in Maturin and have not returned to Puerto Ordaz as predicted this week.

The PEECC for the 7EA unit 100 was ready to pour on Wednesday no concrete, Thursday and Friday was rescheduled, but no concrete pump on Friday ultimately delayed the pour till next Tuesday.  The same delay occurred with the oily water separator, but we were able to pour the base and sump Friday morning before the contractor left.  The crane provided by Sidor continues  set on the foundation and has not been repaired.  erected on the new fill.   This required a change order to Concorcio.  I prepared a draft CO and sent it to for review, he subsequently released it.

I will discuss with Sidor the possible options to get contractors past Sidor’s gate.  We do not have a contract with Sidor and their procedures keep causing us problems with getting our contractors in.

Contractor quality is good, but contractor lack of craft and equipment is causing slippage of the schedule.  The contractor is willing, but we are nearing the point where Contractor will have no work.  We have forestalled this by moving from 7FA to 7EA stack to PECC, and now starting the oily water separator again.  We are in a situation where we will start forming the 7FA stack instead of forming against the 7FA foundation we will have to form all 4 sides and then pour the slab between.  This is not the most effective way, but will allow us to continue while waiting for the anchor bolts.  This will require a change to the rebar shown on the drawings which did not take into consideration what Sidor is producing.

I am trying to get a PO opened for a contractor to start duct bank and U/G excavation so we can open up other areas to work on the 7EA.

The 7FA rebar is as far as is possible without embeds and anchor bolts, the Unisorb pre pour package is not at site as of end of this week (on hold).  The anchor bolts for the turbine and auxiliary pkg. are not on site.

We wrote the contractor a letter stating we will not proceed with any work without written notice.  We are only presently able to work the 7EA (unit 100) GSU (this will require the final information regarding the duct bank immediately adjacent to the foundation), the 7FA foundation (three parts), the 7EA foundations (presently as far as we can go except the PEECC columns, which will pour Tuesday next), oily water separator walls, and waste tanks.

1.1 Safety & Regulatory Compliance –

- General Safety will be maintained at all times on site.

- Daily safety audits are now in place, weekly recap to office.

- Contractor installed safety signs on site, marked out traffic lanes to eliminate outside traffic from site and installed a safety bulletin board in their lunch room.  The permanent Bulletin board will be installed when the commercial issues are resolved.

- The safety people and contractor are preparing a recap of all man-hours worked.

  - Personnel/Staffing –

Cole Franklin (Site Manager)

Keith McMurray (scheduler shared A&B presently on R&R)

Paola Gomez (administrative assist. Local hire)

Patricia Munoz (administrative assist. Local hire)

Daniel Febres (logistics support local hire part time)

Ysren Gomez (Local hire safety supervisor)

Kyle Rosken (Civil Superintendant shared A &B)

Mark Hawks (Electrical supervisor shared A &B)

Felix Martinez (QA/QC supervisor currently shared A & B)

Paulo Olivio (Material coordinador B)

1.3 Weekly Accomplishments

- The 7EA stack forms are removed, part of the stack has been moved to site to begin repairs and installation.

- The 7EA generator, turbine and aux package are installed on foundation.

- Contractor has finished 7FA conduit

- Contractor has poured oily water separator base and sump.

- Contractor is ready to pour PEECC columns

  - Scheduling Conflicts –

- We have gotten no schedule relief from Derwick for the delays in payment, delays for soils on “B”, lack of concrete or delay in delivery, poor quality of the concrete in the 7EA slab.  We need to prepare for this at a higher level than site and force the issue.

- The duct bank and manholes / hand holes are critical around 7EA.  Still no finalized drawings.  This has a more than 60 day impact on the project.

- Prepared a PO to Coinserma for duct bank and manholes.  The work is on hold for commercial issues.  We still need finalized drawings, but will not wait anymore.

- Materials for piping and a large portion of the duct bank conduit are not available at site.

- 7EA PEEC (has a material issue, need embed plates), GSU can not start until crane has de mobilized after repairs to crane, and 7FA need anchor bolts.  I recommend we issue sub-contracts for U/G piping.  This requires engineering and commercial resolution.  The piping materials are not available at site (in Houston).

- The master Bill of Materials for all materials.  We received piping and equipment BOP updated

- Received a P.O. log for all materials ordered to ensure we do not lose more time waiting for material not ordered

1.5– Site Managers Commentary and Amplifying Remarks

The core drilling of the 7
EA slab shows areas of porosity in the cores.  We have now contacted three companied for pressure grouting, possible our credit history is causing problems with getting contractors to respond.  There was a report on the radio this week that PES has been paid, but is withholding monies from contractors regardless.

Contractor entry into Sidor is a major problem must be resolved before we have several contractors working and all out time is devoted to getting contractor personnel into plant.

The progress is not good against the critical path.  Coinserma is willing to start manhole and duct banks in the North end of the site, as soon as they receive a PO.  I think if the foundation locations are fixed we will start the underground as soon as possible.  Sidor did not accept the rebar details in the manholes or hand holes.  We are directed by EDGI that they will not prepare the manhole drawings and issued the previous drawings in error.  They indicate we will use the Sidor typical drawings.  This will require a change for the manhole depth and subsequently the duct bank depth.  EDGI has finally acknowledged the issue with excavating immediately adjacent to foundations and the risk of the soils subsiding below the foundations.

I currently have QA supervisor (shared), scheduler (shared), and electrical supervisor (shared) on site.  I am a little overwhelmed trying to do the PO’s and cash flow and review drawings myself.  EDGI wrote a letter stating we at B are unreasonable in asking for proper drawings, EDGI states there have been more drawings prepared for B than A.  If EDGI checked their own drawings we would not red line them and EDGI would not need to prepare more drawings.  I have not reviewed in detail the drawings based on this recently and now Sidor has entered the fray against EDGI.   We are seeing some slippage due to the above mentioned items and have no way at present to mitigate the slippage, we cannot put EDGI in front of the client as the reason for delays, they are our sub-contractor.  I am preparing Change Order drafts for everything I know has been a schedule impact and reviewing the same against the contract.

- Engineering and Design

2.1.1 Received the following drawings this week;

- Cannot review drawings in timely fashion, they are also delivered to Sidor for review at the same time as to us.

2.1.2 Grounding

- The grounding shown on grounding drawings is not in accordance with the discussion with Sidor regarding grounding of equipment.  This will become a major issue.  Need to put it to bed!

2.1.3 Geo tech membrane treated fuel oil tank

- The geo tech fabric needs to be ordered for fuel oil tank.  Prepared the PO for the material, but is on hold for payment

  - – Site /Civil /Structural

    - The 7EA PEECC base is complete.

    - 7EA Stack forms are removed

    - 7FA is pending anchor bolts and embeds.

    - Oily water base and sump are poured

    - Contractor is waiting for next week to start backfill under the 7FA stack, need to move equipment from A

  - – Mechanical –

    - The 7EA Turbine, Generator, and aux unit are placed on foundation

    - Alignment is held because the mechanical contractor demobilized for lack of payment.

    - The stack for 7EA is being moved to site

    - Unisorb fixators not on site for 7FA, all remaining bolts and embeds from 7FA drawings were ordered 29 June

2.4 – Electrical –

2.4.1 EDGI indicated we are unreasonable, U/G and duct bank has been on site priority list  since March and published since April 5.

2.5 – Instrumentation - To Be Completed

2.6 – O&M Manuals –

2.6.1 Received 7FA O & M manual, need to transmit to Sidor officially one copy.

3. Procurement

3.1 – Purchase Order Requests

- RFP for anchor bolts 7FA to Sedalia local purchases on hold

- RFP for conduit duct banks north and south 7EA to Sedalia local purchases on hold

- RFP for PEECC embeds to Sedalia local purchases on hold

- RFP for storage container material storages on hold

- RFP for construction power parts (issue CO to Derwick) local purchases on hold

- RFP for construction office distribution panel purchases on hold

3.2 – Equipment & Material Quotations –

- Completed  Cash flow analysis including all identified PO required

3.3 - Purchase Order

  - Several PO prepared, none Issued this week

4. Contract

4.1 – EPC Contract –

- CO 001 sent of Poor Soils Site B

- CO002 sent for Backfill under crane due to CO001

- CO 003 construction power distribution to site materials

- CO 004 core drilling to Derwick for Sidor provided concrete

4.2 – Construction Subcontracts –

  - Negotiation ongoing for actualizing sub-contract for electrical and civil underground, and piping, all works currently slowed for commercial issues and engineering

4.3 – Proposal & Quotes

  - Prepared and issued contract RFP for supplying power to the lay down yard and modifying two sea containers into an office and environmentally controlled storage. Two proposals were received are on hold.

5. Construction

5.1 – Schedule

  - Schedule was not issued this week.  There is significant slippage from original estimates due to soils, labor, material, and engineering issues.  Prepared a Soils Change Order CO 001, prepared total quantities

  - Prepared a Soils Change Order for crane placement for 7EA CO 002

5.2 – Equipment Delivery – in progress

5.2.1 Material issues, early delivery of packing list, and P.O.s are a major problem

5.3 – Mechanical –

5.4 – Electrical –

5.5 QA/QC –

- Ongoing inspections concrete, formworks and anchor bolts.

6 Startup & Commissioning –

7 Startup Mobilization - None

Picture 1: 7FA ready to start back fill for next fdn, forms available (right side)

Picture 2: Oily Water Separator base and sump 2 July

Picture 3: 7EA turbine on slab 29 June

Picture 4: 7EA generator on slab 29 June