Table of Contents

1. Executive Summary

EPC

Weekly Report  29 May-4 June 2010Date: 5-June-10Project: Sidor Site B, Puerto Ordaz Venezuela Written By: Cole Franklin ProEnergy EPC Project Mgr

ProEnergy Site Manager

William Lugo

Cole Franklin

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary.

This review is for the week from 29 May to 4 June 2010.  Safety is good, housekeeping is relatively good.  Due to commercial issues the contractor will not send additional manpower or materials to support the site. They also stated they would not start a second shift at this time.  The lack of completed engineering drawings continues to be a problem. Engineering drawings show a lack of review and attention to details. Material deliveries are still problematic the Bill of Materials for Piping, Electrical, Instruments, and equipment are not available at site.

The pedestal for the 7EA unit 100 was poured on Monday.  Forms were removed this week and back fill on the South side for crane placement is completed.  The crane provided by Sidor has not mobilized.  Christoph Merle is checking to see if there is some schedule conflict with crane availability.

We had problems with the 7EA concrete pour.  The meeting with Sidor, PES, and the batch plant managers to discuss the steps necessary for the prevention of a similar situation is scheduled for Monday at 9AM.  The same batch plants provided concrete for Plant A, without and major problems.  This was the first pour on Plant B, Plant A borrowed our QA supervisors and had a QA supervisor at each batch plant as well as a QA person checking the incoming concrete to site.  There was only one QA at site when this was poured, probably contributing to the frequency of rejected concrete trucks.  Suggest we bring in additional QA personnel for the large pours 7FA and compressor foundations.

Contractor quality is good, but contractor lack of craft and equipment is causing slippage of the schedule.  The contractor in conjunction with us has dramatically improved this week; we are not diluting the contractor effort, but have limited work to the most meaning full areas.

The first cylinder break tests were done this week for the 7EA fdn.  One cylinder test was only 30% of design strength at 3 days.  We had another cylinder broken at 7 days and have discovered it only tested 33%.  This is a major issue; we have developed a plan to ascertain if this is bad management of the cylinders by the testing lab or if we have a problem.  We are trying to set up a core drilling company to test drilled cores, and then will determine if we need to continue with other remediation.  I am also exploring the availability of a pressure grouting contractor to strengthen the weak area.  If we in fact have a problem we will then be prepared to repair it.

Contractor requires Purchase Orders to work on anything other than the two large foundations.

1.1 Safety & Regulatory Compliance –

- General Safety will be maintained at all times on site.

- Daily safety audits are now in place, weekly recap to office.

- Contractor installed safety signs on site, marked out traffic lanes to eliminate outside traffic from site and installed a safety bulletin board in their lunch room.  The permanent Bulletin board will be installed when the commercial issues are resolved.

  - Personnel/Staffing –

Cole Franklin (Site Manager)

Keith McMurray (scheduler)

Paola Gomez (administrative assist. Local hire)

Patricia Munoz (administrative assist. Local hire)

Daniel Febres (logistics support local hire)

Ysren Gomez (Local hire safety supervisor)

Kyle Rosken (Civil Superintendant returned to B Wednesday)

Mark Hawks (Electrical supervisor returned to B Wednesday) R&R

Felix Martinez (QA/QC supervisor currently shared A & B)

Paulo Olivio (Material coordinador B)

1.3 Weekly Accomplishments

- The 7EA pedestal was poured Monday,

- Contractor finished 7FA lower mat and side rebar, and will finish the top mat by Wednesday next week.

  - Scheduling Conflicts –

- The duct bank and manholes / hand holes are critical around 7EA.  Still no finalized drawings.  They were scheduled for Monday, now slipped to late week.  This has a more than 60 day impact on the project.

- The U/G piping comments have not been resolved

- PES reviewed the 7FA equipment list and informed engineering that it appears that all of the equipment is not represented on the plot plan.   Engineering and Tom Koontz have met and I understand this will be resolved next week.  Last forecast date for completion of this was 3 June.

- Plan to issue a sub-contract to start the work of installing duct banks and underground piping, but we will need finalized drawings and resolution of commercial issues before we can proceed.

- Materials for piping and a large portion of the duct bank conduit are not available at site.

- This effectively stops all but the 7EA, 7EA PEEC (has a drawings technical issue), GSU (has a drawings technical issue and requires embeds, drawings for embeds issued Thursday), and 7EA stack order the anchor bolts), and 7FA.  I recommend we issue sub-contracts for U/G piping.  This requires engineering and commercial resolution.  The piping materials will be ordered from site if they are not available when we need them. We continue to communicate daily with engineering to resolve the engineering issues.

- The master Bill of Materials for all materials.

- Finalized Equipment list

- P.O. log for all materials ordered to ensure we do not lose more time waiting for material not ordered

1.5– Site Managers Commentary and Amplifying Remarks

The progress has picked up considering small crew and lack of materials, lack of equipment, lack of labor, and lack of engineering.  The schedule is presently a large issue and we have been hesitant to deliver a schedule that has no change of circumstance to support it.

- Engineering and Design

2.1.1 Received the following drawings this week;

- Area lighting

- Revised Anchor bolt details 7FA

- Revised foundation plan still does not give all coordinates for foundations

- Tank drawings and calcs

- Unisorb anchor bolt drawings (Vendor drawings)

- Valve list

- Cable tray supports

- Unit 100 Conduit penetrations revised

2.1.2 The grounding shown on grounding drawings is not in accordance with the discussion with Sidor regarding grounding of equipment.  This will become a major issue.  Need to put it to bed!

2.1.3 The geo tech fabric needs to be ordered for fuel oil tank requires final resolution from engineering and commercial issue resolution.

  - – Site /Civil /Structural –

    - The 7EA pedestal is complete.

    - Completed installing 7FA vertical rebar and upper mat.

    - Finished 80% of forms for first pour.

    - 7EA foundation had 2 bad cylinder breaks

2.3 – Mechanical –

2.3.1 The 7EA turbine replacement thrust pin plate is being fabricated. Forecast delivery is 5-29-10.  Delivery delayed for commercial issues.

2.3.2 Unisorb fixators adjusted and ready to be placed on 7EA foundation, all pre-work done.

2.4 – Electrical –

2.4.1 Duct bank drawings to be reissued next week

2.5 – Instrumentation - To Be Completed

2.6 – O&M Manuals –

2.6.1 7 EA O & M from another site on site.

3. Procurement

3.1 – Purchase Order Requests

- RFP for anchor bolts 7EA stack

- RFP for anchor bolts 7FA

- RFP for conduit duct banks north and south 7EA

- RFP for storage container material storages

- RFP for construction power parts

- RFP for construction office distribution panel

3.2 – Equipment & Material Quotations –

- In the process

3.3 - Purchase Order

4. Contract

4.1 – EPC Contract –

4.2 – Construction Subcontracts –

  - Negotiation ongoing for actualizing sub-contract for electrical and civil underground, and piping, all works currently slowed for commercial issues and engineering

4.3 – Proposal & Quotes

  - Prepared and issued contract RFP for supplying power to the lay down yard and modifying two sea containers into an office and environmentally controlled storage. Two proposals were received and are under review.

5. Construction

5.1 – Schedule

- Schedule was issued.  There is significant slippage from original estimates due to soils, labor, material, and engineering issues.

5.2 – Equipment Delivery – in progress

5.2.1 Material issues and packing list P.O.s are a major problem

5.3 – Mechanical –

5.4 – Electrical –

5.5 QA/QC –

- Ongoing inspections on 7EA foundation, 7FA foundation, and rebar and anchor bolts for 7FA.

- Discovered lack of documentation for 7EA anchor bolts or proper markings on bolts and nuts. NCR 001 was issued to procurement.  MTR received Friday afternoon under review to close NCR 001.

6 Startup & Commissioning –

  - The blank turn over manuals are being prepared for both sites.

7 Startup Mobilization - None

Picture 1: form removal 7EA fdn note backfill

Picture 2: Installing Rebar for 7FA Foundation