Table of Contents

1. Executive Summary

EPC

Weekly Report  3 to 9 July 2010Date: 10-July-10Project: Sidor Site B, Puerto Ordaz Venezuela Written By: Cole Franklin ProEnergy EPC Project Mgr

ProEnergy Site Manager

William Lugo

Cole Franklin

1.1 Safety and Regulatory Compliance

1.2 Personnel/Staffing

1.3 Weekly Accomplishments

1.4 Scheduling Conflicts

1.5 Site Manager Commentary and Amplifying Remarks

2. Engineering and Design

2.1 General Arrangement

2.2 Site/Civil/ Structural

2.3 Mechanical

2.4 Electrical

2.5 Instruments & Control

2.6 O&M Manuals

3. Procurement

3.1 Purchase Order Requests

3.2 Equipment & Material Quotations

3.3 Purchase Order

4. Contracts

4.1 EPC Contract

4.2 Construction Subcontracts

4.3 Proposal and Quotes

5. Construction

5.1 Schedule

5.2 Equipment Delivery Status (expediting report)

5.3 Civil

5.3.1 Site Preparation

5.3.2 Centerline Foundation

5.3.3 GSU Foundation

5.3.4 Auxiliary Foundations

5.4.1 Centerline Equipment Installation

5.4.2 Centerline Piping Installation

5.4.3 Auxiliary Piping Installation

5.4.4 Underground Piping Installation

5.4.5 Above Ground Piping Installation

5.4.6 Balance of Plant (BOP) Piping Installation

5.5 Electrical

5.5.1 Duct Bank Installation

5.5.2 Centerline Electrical Installation

5.5.3 Auxiliary Electrical Installation

5.5.4 Balance of Plant (BOP) Installation

5.6 QA/QC

5.6.1 Equipment Testing

5.6.2 Nonconformity Report

5.6.3 Drawing Revisions

5.6.4 CWI Reports

5.6.5 As-built Drawings

6 Start-Up & Commissioning

6.1 Schedule

6.2 Equipment Status

6.3 Punch list

6.4 Equipment Checkout

6.5 Equipment Functional Test

6.6 Equipment Turnover

6.7 Performance Testing

6.8 Emission Testing

7 Mobilization

7.1 Schedule

7.2 Operating Procedure Development

7.3 Operation Staff Training

7.4 Spare Parts/Inventory Status

1. Executive Summary.

This review is for the week from 3 to 9 July 2010.  Safety is good, housekeeping good.  The commercial issues at Site A are continuing to cause problems at Site B.  Material purchase and delivery is still problematic.  Need to develop a means of tracking material from requisition, purchase, shipment, and finally to site, that allows Site to know where the material is in the cycle.

Site office door was broken last night.  Thieves entered the office and stole the monitors (three each) and possible undisclosed material.  When staff returns Monday we will have a complete inventory and report available.

The 7EA turbine, generator, and aux units were preliminary aligned this week.  The foundation issue was discussed with engineering and a plan is resolved for repairs.  The injection grouting has not been done.  We need to purchase a core drill to continue the installation of the enclosures.  We drilled 24 holes and hit rebar on 22.  The Concorcio gave a quote for core drilling, but the price is more than equivalent US $100 per each 7” deep 1” diameter hole.

The PEECC for the 7EA unit 100 was poured on Wednesday without pump.  The delay was one week.  The crane provided by Sidor continues setting on the GSU foundation site and has not been repaired.  Sidor asked us to complete setting the 7FA by Aug 15.  The movement of the crane mob and de-mob alone is 25 days, plus 10 days to install bolts, pour, and then cure time for slab, makes this unsupportable.  Sidor has not presented a graphic to show the plan for locating the crane.  We will strategize after we have this information from the crane company.

I will discuss with Sidor the possible options to get contractors past Sidor’s gate.  We do not have a contract with Sidor and their procedures keep causing us problems with getting our contractors in.

Contractor quality is good, but contractor lack of craft and equipment is causing slippage of the schedule.  The contractor is willing, but we are nearing the point where Contractor will have no work.  We have forestalled this by moving from 7FA to 7FA stack and 7FA silencer, and continuing the oily water separator forming for walls.

I am trying to get a PO opened for a contractor to start duct bank and U/G excavation so we can open up other areas to work on the 7EA.

The 7FA rebar is as far as is possible without embeds and anchor bolts, the Unisorb pre pour package is not at site as of end of this week (on hold).  The anchor bolts support steel for inlet, exhaust, acoustic, and aux pkgs are on order

1.1 Safety & Regulatory Compliance –

- General Safety will be maintained at all times on site.

- Daily safety audits are now in place, weekly recap to office.

- Contractor installed safety signs on site, marked out traffic lanes to eliminate outside traffic from site and installed a safety bulletin board in their lunch room.  The permanent Bulletin board will be installed when the commercial issues are resolved.

- The safety people and contractor are preparing a recap of all man-hours worked.

  - Personnel/Staffing –

Cole Franklin (Site Manager)

Keith McMurray (scheduler shared A&)

Paola Gomez (administrative assist. Local hire)

Patricia Munoz (administrative assist. Local hire)

Daniel Febres (logistics support local hire part time)

Ysren Gomez (Local hire safety supervisor)

Kyle Rosken (Civil Superintendant shared A &B)

Mark Hawks (Electrical supervisor shared A &B)

Felix Martinez (QA/QC supervisor currently shared A & B)

Paulo Olivio (Material coordinador B started R & R)

1.3 Weekly Accomplishments

- The 7EA PEEC column are poured

- The 7EA generator, turbine and aux package are preliminary aligned.

- The 7FA silencer is ready to pour mud mat with backfill completed

- The 7FA stack is ready to pour mud mat with backfill completed

- Contractor continues forming walls oily water separator.

- Concrete ordered for mud mats for Monday

  - Scheduling Conflicts –

- The duct bank and manholes / hand holes are critical around 7EA.  Still no finalized drawings.  This has a more than 60 day impact on the project.

- Prepared a PO to Coinserma for duct bank and manholes.  The work is on hold for commercial issues.  We still need finalized drawings, but will not wait anymore.

- Met with Mondher Labbane for a sanity check to see if we could pour foundations before duct bank, he agreed we should wait for duct banks to be installed or move them if necessary.  He gave me a sketch of the duct banks that is different from the one I have for information of the developing duct banks.

- Materials for piping and a large portion of the duct bank conduit are not available at site.  Materials at site are being “loaned” to Site A, to be repaced asap.

- GSU can not start until crane has de mobilized after repairs to crane

- 7FA need anchor bolts.

- I recommend we issue sub-contracts for U/G piping.  This requires engineering and commercial resolution.  The piping materials are not available at site (in Houston).

- The master Bill of Materials for all materials.  We received piping and equipment BOP updated

- Received a P.O. log for all materials ordered to ensure we do not lose more time waiting for material not ordered

1.5– Site Managers Commentary and Amplifying Remarks

We have met with Mondher Labbane and discussed the findings of the 7EA slab, we continue with the build of the 7EA.

We finally received a copy of the manhole drawings from Sidor, this can be used when we issue the PO for duct banks.

Contractor entry into Sidor is a major problem must be resolved before we have several contractors working and all out time is devoted to getting contractor personnel into plant.

The progress is not good against the critical path.  Coinserma is willing to start manhole and duct banks in the North end of the site, as soon as they receive a PO.  I think if the foundation locations are fixed we will start the underground as soon as possible.

We are seeing some slippage due to the above mentioned items and have no way at present to mitigate the slippage, we cannot put EDGI in front of the client as the reason for delays, they are our sub-contractor.  I am preparing Change Order drafts for everything I know has been a schedule impact and reviewing the same against the contract.

- Engineering and Design

2.1.1 Received the following drawings this week;

- Cannot review drawings in timely fashion, they are also delivered to Sidor for review at the same time as to us.

2.1.2 Grounding

- The grounding shown on grounding drawings is not in accordance with the discussion with Sidor regarding grounding of equipment.  This will become a major issue.  Need to put it to bed!

2.1.3 Geo tech membrane treated fuel oil tank

- The geo tech fabric needs to be ordered for fuel oil tank.  Prepared the PO for the material, but is on hold for payment

  - – Site /Civil /Structural

    - The 7EA PEECC columns complete.

    - 7FA Stack mud mat ready to pour

    - 7FA is pending anchor bolts and embeds.

    - Oily water walls continue

    - Started and completed backfill under stack and silencer for 7FA

  - – Mechanical –

    - The 7EA Turbine, Generator, and aux unit are aligned

    - The stack for 7EA is being moved to site hold

    - Unisorb fixators not on site for 7FA, all remaining bolts and embeds from 7FA drawings were ordered 29 June

2.4 – Electrical –

2.4.1 EDGI indicated we are unreasonable, U/G and duct bank has been on site priority list  since March and published since April 5.

2.5 – Instrumentation - To Be Completed

2.6 – O&M Manuals –

2.6.1 Received 7FA O & M manual, need to transmit to Sidor officially one copy.  We are holding this at this time.

3. Procurement

3.1 – Purchase Order Requests

- RFP for conduit for duct banks north and south 7EA to Sedalia local purchases on hold

- RFP for PEECC embeds from mechanical contractor on hold

- RFP for storage container material storages on hold

- RFP for construction power parts (issue CO to Derwick) local purchases on hold

- RFP for construction office distribution panel purchases released for purchase

3.2 – Equipment & Material Quotations –

- Completed  Cash flow analysis including all identified PO required

3.3 - Purchase Order

  - Several PO prepared, none Issued this week

4. Contract

4.1 – EPC Contract –

- CO 001 sent of Poor Soils Site B

- CO002 sent for Backfill under crane due to CO001

- CO 003 construction power distribution to site materials

- CO 004 core drilling to Derwick for Sidor provided concrete

4.2 – Construction Subcontracts –

  - Negotiation ongoing for actualizing sub-contract for electrical and civil underground, and piping, all works currently slowed for commercial issues and engineering

4.3 – Proposal & Quotes

  - Need to prepare a quote to purchase and back charge to SIDOR a  175 kVA transformer for site power at Site B, to replace the Sidor provided transformer taken to Site A when Site A transformer failed.

5. Construction

5.1 – Schedule

  - Schedule was not issued this week.  There is significant slippage from original estimates due to soils, labor, material, and engineering issues.

5.2 – Equipment Delivery – in progress

5.2.1 Material issues, early delivery of packing list before receipt of material, and P.O.s are a major problem

5.3 – Mechanical –

5.3.1 alignement of 7EAa preliminary complete

5.4 – Electrical –

5.5 QA/QC –

- Ongoing inspections concrete, formworks and anchor bolts.

6 Startup & Commissioning –

7 Startup Mobilization - None

Picture 1: 7FA ready to start back fill for next fdn, fill mat’l, forms available (right side)

Picture 2: Oily Water Separator base and sump 9 July

Picture 3: 7EA turbine alignment

Picture 4: 7EA crane blocking GSU 100