# CVG SIDOR POWER PROJECT SITE “B”

# DATE: 1 July 2010, Thursday # PROJECT #: 410-3203 # SITE MANAGER: Cole Franklin

TEMPERATURE:  84 F

RANGE: 73 to 93

SITE CONDITIONS: rain afternoon

PERSONNEL ON SITE:

CONSTRUCTION SUPPORT:

William Lugo - Project Mgr (A&B)

Cole Franklin - Site Manager

Ysrin Gomez – Local Safety (Local)

Keith McMurray - Scheduler (A&B)

Mark Hanks - Electrical Supt (A&B)

Kyle Roskam - Civil Supt (A&B)

Felix Martinez-QA/QC (A&B)

MATERIAL SUPPORT:

José Ángel Gonzales – Material (Local)

Paul Olivo – Materials

ADMIN SUPPORT:

Daniel Febres – Logísticas (Local) parcial

Paola Gómez – Administración (Local)

Patricia Muños – Administración (Local)

Skeila Garcia – Translator & Doc Control (Local)

SUBCONTRACTOR PERSONNEL:

General Superintendant		1

Safety					1

Foremen				3

Electricians				4

Operators				0                        Surveyor				1

Carpenters				7    Surveyor Helper			2

Oiler Helper				0

Crane Operator			0                           Laborers				4

Truck Drivers				0

Concrete Finishers			0

Oilers					0

Plumbers				0                        Iron Workers				10

Helpers				4

Welders				2

Total:					39

- GENERAL ITEMS:

  - We will prepare a CO to Derwick for the core drilling and core testing of the additional cores on the 7EA fdn..

  - Contacted a pressure grouting company to come to site to prepare a quote and advise what is necessary to start this work as soon as possible.  No response today from original companies, the core drilling company will send another representative and the engineer who conducted the soils report and managed the core drilling will write us a specification for pressure grouting for review and possible submittal for quotation.

  - Little work on 7FA foundation, the anchor bolts are not on site.  Lack of anchor bolts is a day per day delay to schedule.   Had teleconference to discuss the bolts and have assured the bolts not on order will be ordered today.  We are trying to improve the delivery

  - Will pour 7EA PEECC columns Thursday embed plates will be modified and epoxy grouted in, Sidor was not able to provide concrete today

  - The base and sump for oily water separator will pour Thursday morning.  Sidor was not able to provide concrete today

  - We prepared the PO for signature and hopefully will start excavation for duct bank this week

  - Need plot plan showing reduced BERM for Diesel tank, need to determine if moving the Over Head 13.8 line is necessary.  This is also essential in starting the storm drains.

  - Need to order Geo Tech Membrane for Treated fuel oil tank.  PO prepared, Commercial issue

  - Proposal for modifying sea containers for lay down area office, temperature controlled storage and running power to area offer is on hold pending resolution of commercial issues.

  - RFP for trash containers and disposal of trash is prepared pending new quotes, and commercial issue resolution.

  - The erection of the crane is not completed.  CO 002 to Derwick pending for soils.

  - GSU embeds PO on commercial hold, when released need to include in the air freight from US with anchor bolts for 7FA

- CLIENT ISSUES/CONCERN:

  - Client advised they do not accept the response from EDGI regarding location of Treated Fuel tank.  Meeting cancelled at site with Sidor engineering and PEC.  EDGI says this is PEC issue

  - Client has sent a flurry of e-mail to EDGI regarding engineering drawings issues.

  - Client is concerned for the Septagon building details and does not want the problems currently encountered in A to be duplicated in B

  - Request for purchase for trash bins for site lay down area and construction site released RFP for delivery dates. Sidor has provided one container for wood and trash; still require one more for steel scrap and regular emptying of the both.

- CIVIL:

  - Lack of anchor bolts for 7FA foundation continued delay;

  - Lack Embeds for PEECC will prepare plates at site to epoxy grout in hold commercial

  - Oily water separator water stop material on site will pour Thursday.  No concrete

  - Lack of resolution for Treated Fuel Oil Tank location.

  - Prepared PO for local purchase for Geotech membrane.

- CONCRETE FOUNDATIONS:

  - Work today on the 7FA was halted by contractor.

  - Issued RFP for 7FA Unisorb anchor bolts, local orders cancelled, now on order by Sedalia as of today 29June.

  - Issued RFP for PEECC embeds. On hold

- MECHANICAL:

5.1 Will issue PO for start of 7EA stack repairs and erection, Monday on hold.

5.2 Sidor crane broke down delayed most of the day to lift.  Two day delay for crane in way to start GSU foundation

- PIPING:

6.1 Sidor has indicated we should treat any area where crane can cross as a road crossing.  We need to know within the next 2 weeks what is necessary for a road crossing for both U/G and duct bank.

- ELECTRICAL:

  - Loaned 2000 lf of conduit to Site A.  They will order to replace it, will need it within 2 weeks.

  - Will add a lighting breaker panel for office trailers, very concerned for the “piggybacking” of wires into the breaker we installed.  This is a safety issue.  On hold awaiting resolution of commercial issues, with all the rain we have asked this be turned on.

  - Concorcio gave us a list of materials for the site construction power transformer installation.  PO prepared and CO to Derwick sent

  - The embed plates for the GSU 7EA, PO prepared and quotation available to order the embed plates.  On hold

7.5 The sub contractor Coinserma prepared a new bid we prepared PO.  The execution of this scope will require a large amount of PES time to supervise this work, need to have an electrical local field engineer full time for this.  We received and e-mail from EDGI, we will cancel the manholes drawings and use Sidor’s design, asked Sidor for a copy in the contractor’s meeting today.  They will send tomorrow.

7.6 The underground piping and duct bank is now critical path and is driving the schedule, can afford no more delays.

- INSTRUMENTATION AND CONTROLS:

- SCHEDULED ITEMS:

9.1 General Schedule issues

The schedule is predicated by the following:

- Commercial issues are resolved to local purchase materials

- Contractor increases manpower to work in all areas

- Contractor works two shifts

- The Underground and duct bank is started week of 7 June and does not slip more

- Sedalia material delivers are forthcoming to meet demand

9.2 Milestone Payment Estimated Delivery

- Completed Milestone Payments (50%)

Complete

- Gas Turbines on Foundation (10%)

July 19, 2010 this has slipped, we must come up with an incentive to contractor to accelerate the schedule and we must receive the materials for the foundations

- Civil Foundations Complete (25%)

Sep 15, 2010 (*) see above

- Electrical/Mechanical Complete (10%)

Dec 3, 2010 (*) see above

- Start- up Complete and Ready to Export Power (5%)

Dec 11, 2010 (*)

* Note (*): These dates are estimated based on current uncertain conditions (lack of payment, cash issues, material/equipment deliveries on hold, contractors working at very slow pace, etc).. They will be revised as soon as the schedule review is complete and a clearer path forward is known.

9.3 Payment milestones

- Unit 100 – 7EA

Nov 29, 2010 (*)

- Unit 200 – 7FA

Dec 11, 2010 (*)

- CRITICAL AREAS OF CONCERN:

  - We again checked the site for the anchor bolts for the 7FA.  Revisited the original spreadsheet, finding one error in size and have sent the revised spread sheet of anchor bolts for the 7FA and the packing list for the bolts we thought were for the 7FA (received at Site A boxes CVG-A-001-006 and CVG-A-032-037) to Juli Wilson and Bob Dodson.  We had a conference call and are assured all bolts are not on order.

  - Wrote a report with Jason Byrd regarding loading and transportation of the 7EA from Site A to Site B.  There is a potential for unknown damage to turbine.

  - The 7EA foundation concrete breaks are below acceptable; the core drilling has indicated an area in the suspect zone of porous con  Prepared a report based on final breaks and have sent it to open discussions to assure all are on the same page and all optiona are explored.

  - Lack of materials (anchor bolts 7FA, embed plates 
PEECC for 7EA, embed for GSU

  - Sidor cited numerous Site A problems with foundations for buildings, and building fabrication.  Request we review this to prevent the same problems at Site B.  Sidor has also questioned why no rest rooms in buildings.

  - Need finalized design or if that cannot be completed, need to include all equipment on GA and freeze the design with Sidor approval.

  - Material deliveries and the trickle down caused by commercial issues seriously retard our ability to execute schedule

  - SAFETY:

    - Concorcio Megavatio reported job site information board was assembled and ready to bring to site for installation.   Pending resolution of commercial issues.

  - OUTSTANDING DRAWINGS:

| Drawings Issue | Forecast date | New F/C date | Closed |
| --- | --- | --- | --- |
| GSU 7EA | 15May10 | 25May10 | Will pour when crane moves after setting unit 100 turbine generator |
| Balance of FDN drawings | 25May10 | 3Jun10 |  |
| Treated Fuel Tank updated drawings | 29May10 | 1Jun10 |  |
| GSU 7FA | 21May10 | 2 Jun10 | Not critical |
| Duct Bank | 17May | 28 June 10 | Received dwgs 25 June discussed in contractor’s meeting with EDGI |
| Design essentially complete | 31 May | No forecast date | No forecast date |

    - A spread sheet of all the pending drawing issues noted here is being consolidated; these issues will be captured for both sites.

  - ISSUED DRAWINGS:

Received revised electrical duct bank dwgs

11. PICTURES:

Photo 1: 7EA cores to break at Sidor’s request

Note porosity and texture

Photo 2: 7EA core holes relative to turbine anchors