## Recap
ProEnergy EPC
Job Description: |  |  | "Curapao 2ea 7 FA's and 2ea LM 6000's"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  |  | 2010-11-04
[10 empty] | US $ Portion | BsF Portion
I. Balance of Plant | [10 empty] | 8
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 385.5556 | calc |  | 77.1111 | 2467.5556
|  | 102 | Excavation - Fill |  |  | Mhrs | 355.5556 | calc |  | 71.1111 | 2275.5556
|  | 103 | Concrete Foundations |  |  | 26391.2037 | 3611.3194 | calc |  | 722.2639 | 23112.4444
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 1614.4074 | calc |  | 322.8815 | 10332.2074
|  | 106 | Gravel - Sand |  |  |  | 821.0544 | calc |  | 164.2109 | 5254.7484
|  | 107 | Structual Steel |  |  |  | 460.5 | calc |  | 460.5
|  | 108 | Fencing |  |  |  | 200.1 | calc |  | 40.02 | 1280.64
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 7448.4924 |  | 7448.4924
| 200 Buildings | [5 empty] | 993.75 | calc | 993.75 | 993.75
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 16568.552 | calc |  | 16568.552
|  | 320 | Pipe, Valves & Fitting labor |  |  | 68040 | 3947.6196 | calc |  | 789.5239 | 25264.7652
|  | 330 | Mechanical Subcontractor |  |  | 124686 | 7234.1695 | calc |  | 1446.8339 | 46298.6848
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 1800 | calc |  | 1800
[7 empty] | 29550.3411 |  | 29550.3411
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 5583.5 | calc |  | 5583.5
|  | 420 | Substation Equipment |  |  |  | 0 | calc |  | 0
|  | 430 | Plant Electrical Subcontractor |  |  | 149639.4 | 8681.9433 | calc |  | 1736.3887 | 55564.4372
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc |  | 0 | 0
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 1500 | calc |  | 1500
|  | 460 | Conduit, Cable & Wire Labor |  |  | 58320 | 3383.6739 | calc |  | 676.7348 | 21655.513
[7 empty] | 19149.1172 |  | 19149.1172
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 480 | calc |  | 480
|  | 530 | Instrumentation Subcontractor |  |  | 2268 | 131.5873 | calc |  |  | 1052.6986
[7 empty] | 611.5873 |  | 611.5873
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 905 | calc
|  | 620 | Telephone System |  |  |  | 20 | calc
|  | 630 | Public Address System |  |  |  | 20 | calc
|  | 640 | TV / Security |  |  |  | 20 | calc
[7 empty] | 965 |  | 965 | 965
700 Plant Erection
|  | 700 | Plant Erection |  |  | 104911.2 | 6086.8534 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 507864.6 | 6086.8534 |  | 6086.8534 | 1217.3707 | 38955.8618
| 800 Equipment Rental | [5 empty] | 5190 | calc | 5190 |  | 41520
| 900 Painting | [5 empty] | 575 | calc | 575 | 115 | 3680
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 1302.98 | calc |  | 1302.98
|  | 1002 | Ocean/Air Freight |  |  |  | 0 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 0 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 300 | plgd /1000 |  |  | 2400
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 100 | plgd /1000 |  |  | 800
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 1702.98 |  | 1702.98
| 1100 Site Costs | [5 empty] | 782.2 | calc | 782.2 |  | 6257.6
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 3980 | calc |  | 3980
|  | 1202 | Local Eng |  |  |  | 340 | calc |  |  | 2720
[7 empty] | 4320 |  | 4320
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 3980 | calc
|  | 1320 | Inspectors |  |  |  | 648 | calc
|  | 1390 | ProEnergy Labor |  |  |  | 1750
[7 empty] | 6378 |  | 6378 | 6378
| 1400 Travel & Perdiem | [5 empty] | 4190 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 4190 |  | 4190 | 4190
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 2 | 2200 | 6000 | plgd
|  | 1502 | Fire Water |  | 30 | 2500 | 75 | plgd
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd
|  | 1505 | Water Treatment |  | 20 | 2200 | 44 | plgd
|  | 1506 | Commission / S/U / Trng |  | 150 | 2000 | 300 | plgd
|  | 1507 | Controls Rep |  | 90 | 2000 | 180 | plgd
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd
|  | 1509 | LM6000 GTG tech Rep |  | 150 | 2000 | 300 | plgd
[7 empty] | 6899 |  | 6899 | 6899
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 100 | plgd /1000 |  |  | 800
|  | 1602 | Concrete |  |  |  | 125 | plgd /1000 |  |  | 1000
|  | 1603 | X Ray |  |  |  | 125 | plgd /1000 |  |  | 1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 250 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 100 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 700 |  | 700 | 700
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 800 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 800 |  | 800 | 800
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 2000 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 26897.052 | 1344.8526 | calc
|  | 2150 | Labor Contingency |  | 5% | 29465.847 | 1473.2924 | calc
[7 empty] | 4818.145 |  | 4818.145 | 4818.145
[5 empty] | BOP Cost |  |  |  | 101160.4664 | 64798.8774
[5 empty] | % Markup |  |  | 25% | 26000 | 26000
[5 empty] | BOP Sales Price |  |  |  | 127160.4664 | 90798.8774 | 293692.712
II. ProEnergy Substation Pricing | [6 empty] | US Dollars/1000
| Substation Equipment | [6 empty] | plgd | 11456 | 11456
| Substation Installation | [7 empty] | 840 | 420 | 3360
| Substation Total | [7 empty] | 12296 | 11876 | 3360
| Move 3 Transmission Lines | [6 empty] | plgd | 300 |  | 2400
| Total High Voltage Scope | [7 empty] | 12596 | 11876 | 5760
III. Total ProEnergy Scope | [5 empty] | BOP Sales Price |  |  | 139756.4664 | 102674.8774 | 299452.712
[6 empty] | Local Municipal & Social |  | 7.5% |  |  | 22458.9534
[6 empty] | IVA |  | 16% |  |  | 47912.4339
[6 empty] | Total ProEnergy Sales Price Incl. Taxes |  |  |  | 102674.8774 | 369824.0993
IV. Precomprimido Civil Subcontractor Bid
|  | Concrete Fence | [6 empty] | 1723 |  | 13784
|  | Site Prep,Terrace, Drainage, Access Road, Diversioin Channel for Creek | [6 empty] | 14003.25 |  | 112026
[6 empty] | Total Plant Sales Price |  |  | 155482.7164 | 102674.8774 | 495634.0993

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | Curapao Power Plant | [5 empty] | Date: |  | 2010-11-04
Customer: |  | PDVSA | [5 empty] | Quote No: |  | T 1035 - 4A
Location: |  | Curapao, Venn | [5 empty] | Est By: |  | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Clearing/Grubbing Area 1 |  |  | 1000 | 650 | 1 | 650000 | 24074.0741 | 12 | 288888.8889
2
3 | Clearing Area 2 |  |  | 500 | 300 | 1 | 150000 | 5555.5556 | 12 | 66666.6667
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Tank Dyke |  |  | 1500 | 6 | 6 | 54000 | 2000 | 15 | 30000
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
385.5556

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | Curapao Power Plant | [6 empty] | Date: |  | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: |  | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: |  | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
7 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
8 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
9 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
10 | [9 empty] | 12
11 | Main Plant Area 1 |  |  |  | 1000 | 650 | 1 | 650000 | 24074.0741 | 12 | 288888.8889
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 12 | 0
13 | Plant Area 2 |  |  |  | 500 | 300 | 1 | 150000 | 5555.5556 | 12 | 66666.6667
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 355.5556

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Curapao Power Plant | [7 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [7 empty] | Quote No: | T 1035 -3
Location: |  | Curapao, Venn | [7 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy
1 | POWER ISLAND | [8 empty] | 650
2 | LM 6000's |  |  | 2 | 60 | 20 | 4 | 9600 | 355.5556 | 750 | 266666.6667 | 1777.7778
3 | LM 6000 Exhaust Stack |  |  | 2 | 25 | 25 | 4 | 5000 | 185.1852 | 750 | 138888.8889 | 925.9259
4 | GE 7 EA's |  |  | 2 | 75 | 16 | 6 | 14400 | 533.3333 | 750 | 400000 | 2666.6667
5 | 7 EA Exhaust Stack |  |  | 2 | 35 | 35 | 6 | 14700 | 544.4444 | 750 | 408333.3333 | 2722.2222
6 | LM 6000 LO Cooling Tower |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 750 | 6250 | 41.6667
7 | 7 EA LO Fin Fans |  |  | 12 | 20 | 20 | 0.7 | 3360 | 124.4444 | 750 | 93333.3333 | 622.2222
8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
10 | Aux Skid(s) for GTG |  |  | 8 | 12 | 15 | 1 | 1440 | 53.3333 | 750 | 40000 | 266.6667
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | 0 | 18 | 8 | 1 | 0 | 0 | 650 | 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  | 0 | 25 | 6 | 1 | 0 | 0 | 650 | 0 | 0
17 | Fin Fan L O Coolers |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 650 | 0 | 0
18 | Gas Compressors |  |  | 0 | 45 | 15 | 4 | 0 | 0 | 650 | 0 | 0
19 | Fuel Gas Plant Metering Skid |  |  | 0 | 15 | 8 | 1 | 0 | 0 | 650 | 0 | 0
20 | Comp Fin Fans |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 650 | 0 | 0
21 | Waste Oil/Water Storage Tank |  |  | 2 | 15 | 12 | 1 | 360 | 13.3333 | 650 | 8666.6667 | 66.6667
22 | Oily Water Separator |  |  | 2 | 30 | 20 | 0.5 | 600 | 22.2222 | 650 | 14444.4444 | 111.1111
23 | Lubricant Storage Area |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 650 | 48750 | 375
24 | Instrument Air Comp Skid |  |  | 3 | 10 | 8 | 1 | 240 | 8.8889 | 650 | 5777.7778 | 44.4444
25 | Pipe Rack Stanchons |  |  | 50 | 2.5 | 2.5 | 6 | 1875 | 69.4444 | 650 | 45138.8889 | 347.2222
26 | 15KV Cable Tray Stanchons |  |  | 20 | 2.5 | 2.5 | 6 | 750 | 27.7778 | 650 | 18055.5556 | 138.8889
27 | Fire Water Pump Skid |  |  | 1 | 15 | 30 | 1 | 450 | 16.6667 | 650 | 10833.3333 | 83.3333
28 | Area Light Poles |  |  | 15 | 2.5 | 3 | 5 | 562.5 | 20.8333 | 650 | 13541.6667 | 104.1667
29 | Aux Trans fndns |  |  | 7 | 10 | 15 | 1.5 | 1575 | 58.3333 | 650 | 37916.6667 | 291.6667
30 | Cable Trenches see est |  |  | 4 | 250 | 12 | 0.6 | 7200 | 266.6667 | 650 | 173333.3333 | 1333.3333
31 | Water Treatment Plant |  |  | 1 | 75 | 65 | 1 | 4875 | 180.5556 | 650 | 117361.1111 | 902.7778
32 | DFO Raw 2000M Tank |  |  | 1 | 90 | 90 | 1 | 8100 | 300 | 650 | 195000 | 1500
33 | DFO Clean 1000M Tank |  |  | 1 | 75 | 75 | 1 | 5625 | 208.3333 | 650 | 135416.6667 | 1041.6667
34 | DFO Truck Unloading Shed |  |  | 5 | 60 | 20 | 1 | 6000 | 222.2222 | 650 | 144444.4444 | 1111.1111
35 | DFO Unlloading Pump Skid |  |  | 5 | 12 | 6 | 1 | 360 | 13.3333 | 650 | 8666.6667 | 66.6667
36 | DFO Forwarding Pump Skid |  |  | 1 | 8 | 6 | 1 | 48 | 1.7778 | 650 | 1155.5556 | 8.8889
37 | DFO Treatment Skid |  |  | 1 | 30 | 8 | 2 | 480 | 17.7778 | 650 | 11555.5556 | 88.8889
38 | Demin Water Pump skid |  |  | 2 | 8 | 6 | 1 | 96 | 3.5556 | 650 | 2311.1111 | 17.7778
39 | Demin Stg Tanks 500M Gal |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 650 | 48750 | 375
40 | Demin Forwarding Pumps |  |  | 2 | 8 | 6 | 1 | 96 | 3.5556 | 650 | 2311.1111 | 17.7778
41 | Chemical Injection Skid |  |  | 1 | 12 | 8 | 1 | 96 | 3.5556 | 650 | 2311.1111 | 17.7778
42 | Raw Water Tank Base 1 MM |  |  | 1 | 75 | 75 | 1 | 5625 | 208.3333 | 650 | 135416.6667 | 1041.6667
43 | Fire Water Tank base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
44 | Emer Generator Base |  |  | 1 | 30 | 20 | 2 | 1200 | 44.4444 | 650 | 28888.8889 | 222.2222
45
46 | BUILDINGS
47 | Control Bldg/Office |  |  | 1 | 140 | 60 | 0.5 | 4200 | 155.5556 | 650 | 101111.1111 | 777.7778
48 | Warehouse/Maintenance |  |  | 1 | 150 | 60 | 0.7 | 6300 | 233.3333 | 650 | 151666.6667 | 1166.6667
49 | Water Treatment Bldg |  |  | 1 | 120 | 75 | 0.7 | 6300 | 233.3333 | 650 | 151666.6667 | 1166.6667
50 | Gas Compressor Bldg |  |  | 0 | 120 | 45 | 1 | 0 | 0 | 650 | 0 | 0
51 | Electrical Bldg |  |  | 1 | 42 | 20 | 0.7 | 588 | 21.7778 | 650 | 14155.5556 | 108.8889
52 | Pwr Blk Utility Bldg's |  |  | 1 | 60 | 40 | 1 | 2400 | 88.8889 | 650 | 57777.7778 | 444.4444
53 | Substation Bldg |  |  | 1 | 15 | 12 | 0.7 | 126 | 4.6667 | 650 | 3033.3333 | 23.3333
54 | Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
55 | Liquid Fuel Unloading |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
56 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
57 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0
58
59 | SUBSTATION
60 | GSU Transformer |  |  | 4 | 35 | 35 | 3 | 14700 | 544.4444 | 650 | 353888.8889 | 2722.2222
61 | (___)KV SF6 Circuit Breaker |  |  | 8 | 15 | 15 | 1 | 1800 | 66.6667 | 650 | 43333.3333 | 333.3333
62 | (___)KV Disc Switch w/ Stand |  |  | 12 | 10 | 15 | 1 | 1800 | 66.6667 | 650 | 43333.3333 | 333.3333
63 | Dead End Tower |  |  | 7 | 15 | 10 | 3 | 3150 | 116.6667 | 650 | 75833.3333 | 583.3333
64 | Transmission Line Poles |  |  | 0 | 5 | 5 | 20 | 0 | 0 | 650 | 0 | 0
65 | Insulator Support Base |  |  | 45 | 3 | 3 | 4 | 1620 | 60 | 650 | 39000 | 300
66 | PT Support Base |  |  | 9 | 3 | 3 | 4 | 324 | 12 | 650 | 7800 | 60
67 | Static Pole Base |  |  | 4 | 3 | 3 | 6 | 216 | 8 | 650 | 5200 | 40
68
69
70 |  |  | Total Cost of Foundations | [5 empty] | 5278.2407 |  | 3611.3194 | 26391.2037
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | Curapao Power Plant | [7 empty] | Date: |  | 2010-11-04
Customer: |  | PDVSA | [7 empty] | Quote No: |  | T 1035 - 4A
Location: |  | Curapao, Venn | [7 empty] | Est By: |  | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description | [7 empty] | Cu | Price | Total
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls | [8 empty] | 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | Curapao Power Plant | [6 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
2 | Gen Removal Areas |  |  | 160 | 25 | 1 | 4000 | 148.1481 | 650 | 96296.2963
3 | Turbine Removal Areas |  |  | 120 | 25 | 0.7 | 2100 | 77.7778 | 650 | 50555.5556
4 | Entry Ways |  |  | 60 | 15 | 0.5 | 450 | 16.6667 | 650 | 10833.3333
5 | Walk ways |  |  | 220 | 6 | 0.5 | 660 | 24.4444 | 650 | 15888.8889
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 2400 | 20 | 0.7 | 33600 | 1244.4444 | 650 | 808888.8889
12 | Parking Lot |  |  | 250 | 150 | 0.7 | 26250 | 972.2222 | 650 | 631944.4444
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 1614.4074
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | Curapao Power Plant | [7 empty] | Date: |  | 2010-11-04
Customer: |  | PDVSA | [7 empty] | Quote No: |  | T 1035 - 4A
Location: |  | Curapao, Venn | [7 empty] | Est By: |  | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price
1
2 | Main Plant Area 1 |  |  | 1 | 1000 | 650 | 0.5 | 325000 | 12037.037 | 19981.4815 | 30 | 599444.4444
3
4 | Plant Area 2 |  |  | 1 | 500 | 300 | 0.5 | 75000 | 2777.7778 | 4611.1111 | 30 | 138333.3333
5
6 | Substation |  |  | 0 | 400 | 150 | 1 | 0 | 0 | 0 | 30 | 0
7
8 | Road ways |  |  | 1 | 2400 | 22 | 0.5 | 26400 | 977.7778 | 1623.1111 | 30 | 48693.3333
9
10 | Parking |  |  | 1 | 250 | 150 | 0.5 | 18750 | 694.4444 | 1152.7778 | 30 | 34583.3333
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | [8 empty] | 821.0544

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Curapao Power Plant | [5 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [5 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [5 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | # of | Qty | Price | Total
No. | [5 empty] | Lbs / Tons |  |  | Price
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 25 | 4500 | 112500
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [5 empty] | 12 | 4000 | 48000
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 4 | 20000 | 80000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 1 | 60000 | 60000
10
11 | Overhead Crane (Bldg) (__40__) Ton | [5 empty] | 1 | 75000 | 75000
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 1 | 10000 | 10000
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 5000 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 75000 | 75000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 460.5

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 2500 | 15 | 37500
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 4000 | 24 | 96000
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 650 | 24 | 15600
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 5 | 4000 | 20000
10 | Motor Operated Double Gate(s) |  |  |  |  | 2 | 7000 | 14000
11 | Personnel Gate(s) |  |  |  |  | 6 | 500 | 3000
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 2 | 7000 | 14000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 200.1

## 109 Architectual
ARCHITECTUAL TREATMENT
[5 empty] | (1,000's) |  |  | 109
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1
2 | Trees and/or Shrubs - Revegetation
3 | Boundry Road |  |  |  |  | 0 | 0 | 0
4 | Within site |  |  |  |  | 0 | 0 | 0
5 | [5 empty] | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39
40 |  |  | Total Cost of Arch Treatment |  |  |  |  | 0

## 110 Evap Pond
EVAPORATION POND
|  |  |  | (1,000's) | [5 empty] | 110
Project Name: |  | Curapao Power Plant | [6 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yard | cy | Price
1 | Storm Water Evap Pond |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7
8
9
10
11 | [8 empty] | Price
12 | [6 empty] | sf |  | sf
13 | Liner |  |  | 0 | 0 |  | 0 |  | 3 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 | [9 empty] | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Curapao Power Plant | [5 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [5 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [5 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price
1 | Fuel Gas Compressor Shed |  |  |  | 0 | 50 | 0 | 40 | 0
2 | Control/Office |  |  |  | 60 | 75 | 4500 | 55 | 247500
3 | Water Treatment |  |  |  | 120 | 60 | 7200 | 40 | 288000
4 | Electric Bldg |  |  |  | 60 | 40 | 2400 | 40 | 96000
5 | Warehouse/Maintenance |  |  |  | 120 | 75 | 9000 | 35 | 315000
6 | Substation Bldg |  |  |  | 20 | 20 | 400 | 0 | 0
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Treatment Shed |  |  |  | 45 | 25 | 1125 | 35 | 39375
9 | Pump Room |  |  |  | 0 | 0 | 0 | 0 | 0
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 15 | 15 | 225 | 35 | 7875
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 993.75

## 310, 320, 330 & 340 Mechanical
MECHANICAL
(1,000's)
310 & 330
Project Name: | Curapao Power Plant | [9 empty] | Date: | 40486 | 40486
Customer: | PDVSA | [9 empty] | Quote No: | T 1035 - 4A | T 1035 - 4A
Location: | Curapao, Venn | [9 empty] | Est By: | WTS/CD | WTS/CD
Bid Due Date: | 2010-11-04
|  |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
|  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
Tag Number | Prime Movers and Associated Equipment | Cost Code |  |  |  | 3% |  | 9
035GTG100 | Gas Turbine Generator 100, 200, 7 FA | 310.03 | 2 | 0 | 0 | 0 | 0 | 9 | 40 | 120 | 86400 | 58.0191 | 5012850.24
| Gas Turbine Genrator 300 400 LM 6000 | 310.04 | 2 | 0 | 0 | 0 | 0 | 9 | 24 | 35 | 15120 | 58.0191 | 877248.792
035DEG100 | Diesel Engine Generator 100, 200,300, … | 310.07 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CTLO100 | Emergency Generator 100, 200, … | 310.09 | 1 | 350000 | 350000 | 10500 | 10500 | 9 | 6 | 5 | 270 | 58.0191 | 15665.157
035FFLLO 100 | Exhaust Stack Generator 100,200 | 310.1'0 | 2 | 1500000 | 3000000 | 150000 | 300000 | 9 | 0 | 0 | 0 | 58.0191 | 0
035GRT100 | Exhaust Stack Generator 300, 400 | 310.11 | 2 | 220000 | 440000 | 25000 | 50000 | 9 | 0 | 0 | 0 | 58.0191 | 0
035LBO100 | Lube Oil Cooling Tower for LM 6000s | 310.12 | 1 | 45000 | 45000 | 5000 | 5000 | 9 | 0 | 0 | 0 | 58.0191 | 0
035GTT100 | Lube Oil Fin Fan Coolers for 7 FA s | 310.13 | 12 | 0 | 0 | 0 | 0 | 9 | 4 | 6 | 2592 | 58.0191 | 150385.5072
035AB100 | Grout Gen 100, 200, 300, … |  | 4 | 65000 | 260000 | 2500 | 10000 | 9 |  |  | 0 | 58.0191 | 0
| Lube Oil Gen 100, 200, 300 …. |  | 4 | 65000 | 260000 | 5000 | 20000 | 9 | 4 | 4 | 576 | 58.0191 | 33419.0016
| Gas Turbine Tools | 310.15 | 1 | 75000 | 75000 | 5000 | 5000 | 9 | 0 | 0 | 0 | 58.0191 | 0
035HRSG100 | Anchor Bolts Gen 100, 200, 300 … | 310.16 | 4 | 65000 | 260000 | 7800 | 31200 | 9 | 0 | 0 | 0 | 58.0191 | 0
035BDV100 | [7 empty] | 0 | 0 | 0 | 0 | 58.0191 | 0
| Water Wash Skid |  | 1 | 250000 | 250000 | 7500 | 7500 | 9 | 4 | 8 | 288 | 58.0191 | 16709.5008
| HRSG and Assoc Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| HRSG 100, 200, 300, … | 310.2'0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035SCR100 | By Pass Diverter Valve HRSG 100, 200, … | 310.21 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035NHT100 |  | 310.22 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PNH100 | SCR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| SCR100, 200,300 … |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Amonia Tank 100 | 310.25 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035STG100 | Amonia Pump 100 | 310.26 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CTSTG |  | 310.27 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CND100 | Steam Turbine Generator | 310.28 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035DEA100 | Steam Turbine Generator 100 | 310.29 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CHISTG100 | Cooling Tower Steam Turbine
| Condenser 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Dearator 100 | 310.31 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CH100 | Chemical Injection Skid STG Cooling Tower 100 | 310.32 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035EVP100 |  | 310.33 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035IFG100 | Inlet Air Conditioning Systems | 310.34 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CTCH100 | Inlet Air Chilling Package 100 | 310.35 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035GTCC100 | Gas Turbine Inlet Air Evap Cooling System | 310.36 | 2 | 150000 | 300000 | 9000 | 18000 | 9 | 4 | 8 | 576 | 58.0191 | 33419.0016
035CHICH100 | Inlet Air Fogging System 100 | [6 empty] | 9 |  |  |  |  | 0
| Cooling Tower Chiller Package 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Gas Turbine Inlet Air Cooling Coils 100,200,… | 310.'40 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CGF100,200 | Chemical Injection Skid Chiller Cooling Tower | 310.41 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CLOFF100 |  | 310.42 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035CLOCT100 | Fuel Gas System | 310.43 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035MFG100 | Compressor Fuel Gas 100, 200, … | 310.44 | 0 | 1800000 | 0 | 50000 | 0 | 9 | 6 | 15 | 0 | 58.0191 | 0
035ESD100 | Compressor Lube Oil Fin Fan 100, 200,… | 310.45 | 0 | 45000 | 0 | 7000 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0
035SFG100 | Compressor Lube Oil Cooling Tower 100 | 310.46 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Compressor Fuel Gas 300, 400 |  | 0 | 750000 | 0 | 30000 | 0 | 9 | 6 | 12 | 0 | 58.0191 | 0
| Compressor Fin Fan 300, 400 |  | 0 | 30000 | 0 | 5000 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0
035RGF100A/B | Meter Fuel Gas | 310.47 | 0 | 175000 | 0 | 4000 | 0 | 9 | 4 | 3 | 0 | 58.0191 | 0
035FGF100A/B | Emergency Shut Down Valve | 310.48 | 0 | 25000 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 58.0191 | 0
035HGF100 | Scrubber Fuel Gas |  | 0 | 35000 | 0 | 2500 | 0 | 9 | 3 | 4 | 0 | 58.0191 | 0
| Regulator Fuel Gas Skid (2 Regulators) |  | 0 | 145000 | 0 | 0 | 0 | 9 | 3 | 4 | 0 | 58.0191 | 0
| Fuel Gas Filter Skid (2 Filters) | 310.51 | 0 | 125000 | 0 | 0 | 0 | 9 | 3 | 4 | 0 | 58.0191 | 0
035SLF100 | Fuel Gas Heater Skid 7FA | 310.52 | 0 | 250000 | 0 | 0 | 0 | 9 | 6 | 18 | 0 | 58.0191 | 0
035MLF100 |  | 310.53 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035TLF | Liquid Fuel System | 310.54 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035FLF100A/B | Separator Liquid Fuel | 310.55 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035HLF100 | Meter Liquid Fuel |  | 1 | 190000 | 190000 | 3500 | 3500 | 9 | 3 | 4 | 108 | 58.0191 | 6266.0628
| Liquid Fuel Treatment Skid |  | 1 | 1300000 | 1300000 | 50000 | 50000 | 9 | 6 | 15 | 810 | 58.0191 | 46995.471
| Liquid Fuel Filter Skid ( 2 Filters) | 310.58 | 4 | 185000 | 740000 | 5000 | 20000 | 9 | 3 | 4 | 432 | 58.0191 | 25064.2512
035TRW100 | Liquid Fuel Heater Skid | 310.59 | 2 | 150000 | 300000 | 9000 | 18000 | 9 | 0 | 0 | 0 | 58.0191 | 0
035RWW100 |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Water System |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Water Treatment System (RO and EDI w/Filters) | 310.61 | 1 | 850000 | 850000 | 35000 | 35000 | 9 | 12 | 45 | 4860 | 58.0191 | 281972.826
035PLF100A/B | 6 inch pipeline to Ceuta Creek | 310.62 | 1800 | 25 | 45000 | 10000 | 10000 | 9 | 4 | 0.1 | 6480 | 58.0191 | 375963.768
035PLFF100A/B |  | 310.63 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PLFI100A/B | Pumps | 310.64 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PCW100A/B | Pump Liquid Fuel Unloading Skid (2 Pumps) | 310.65 | 6 | 18000 | 108000 | 750 | 4500 | 9 | 3 | 2 | 324 | 58.0191 | 18798.1884
035PCHW100A/B | Pump Liquid Fuel Forwarding Skid (2 Pumps) | 310.66 | 4 | 25000 | 100000 | 750 | 3000 | 9 | 3 | 3 | 324 | 58.0191 | 18798.1884
035PSPT100 | Pump Liquid Fuel Injection Skid (2 Pumps) | 310.67 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PWI100 | Pump Cooling Water Skid (2 Pumps) | 310.68 | 2 | 15000 | 30000 | 750 | 1500 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PDW100,200 | Pump Chilled Water Skid (2 Pumps) | 310.69 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035PEV100 | Demin Water Sprint Injection Pump | 310.'70 | 2 | 125000 | 250000 | 3500 | 7000 | 9 | 3 | 2 | 108 | 58.0191 | 6266.0628
035PIFG100 | Demin Water Injection Pump | 310.71 | 4 | 125000 | 500000 | 3000 | 12000 | 9 | 3 | 3 | 324 | 58.0191 | 18798.1884
035PWO100 | Demin Water Forwarding Pump 100, 200, … | 310.72 | 2 | 25000 | 50000 | 1500 | 3000 | 9 | 3 | 3 | 162 | 58.0191 | 9399.0942
035PWW100 | Pump Evap Cooling Water |  | 2 | 30000 | 60000 | 1500 | 3000 | 9 | 3 | 2 | 108 | 58.0191 | 6266.0628
| Pump Raw Creek Water Forward Pumps |  | 2 | 30000 | 60000 | 1000 | 2000 | 9 | 3 | 3 | 162 | 58.0191 | 9399.0942
| Pump Waste Oil | 310.75 | 2 | 10000 | 20000 | 600 | 1200 | 9 | 2 | 2 | 72 | 58.0191 | 4177.3752
035CIA300 | Pump Waste Water |  | 1 | 10000 | 10000 | 600 | 600 | 9 | 2 | 2 | 36 | 58.0191 | 2088.6876
| Pump Sludge |  | 2 | 18000 | 36000 | 1000 | 2000 | 9 | 2 | 3 | 108 | 58.0191 | 6266.0628
| Instrument and Service Air Compressor |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Instrument Air Compressor and Dryer | 310.78 | 3 | 75000 | 225000 | 6750 | 20250 | 9 | 4 | 5 | 540 | 58.0191 | 31330.314
035OWS |  | 310.79 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035TWO300 |  | 310.'80 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035TWW300 | Oily Water Drain System | 310.81 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Oily Water Separator | 310.82 | 2 | 55000 | 110000 | 5000 | 10000 | 9 | 6 | 5 | 540 | 58.0191 | 31330.314
| Waste Oil Tank | 310.83 | 2 | 10000 | 20000 | 1500 | 3000 | 9 | 4 | 4 | 288 | 58.0191 | 16709.5008
035TRW100 | Waste Water Tank | 310.84 | 2 | 10000 | 20000 | 1500 | 3000 | 9 | 4 | 4 | 288 | 58.0191 | 16709.5008
035TFW100 | Waste Sludge Tank | 310.85 | 1 | 25000 | 25000 | 5000 | 5000 | 9 | 4 | 4 | 144 | 58.0191 | 8354.7504
035TRFW100 | Tanks | 310.86 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035TDW100 | Tank Raw Water 1000 M Gal | 310.87 | 1 | 1100000 | 1100000 | 33000 | 33000 | 9 | 6 | 8 | 432 | 58.0191 | 25064.2512
035TROW100 | Tank Fire Water | 310.88 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
035TEVW100 | Tank Raw/Fire Water | [6 empty] | 9
| Tank Demin Water 500 M Gal |  | 1 | 700000 | 700000 | 15000 | 15000 | 0 | 4 | 6 | 0 | 58.0191 | 0
| Tank RO Water | 310.91 | 1 | 21000 | 21000 | 1500 | 1500 | 9 | 3 | 4 | 108 | 58.0191 | 6266.0628
035FWP100 | Tank Evap Water | 310.92 | 2 | 21000 | 42000 | 1500 | 3000 | 9 | 3 | 4 | 216 | 58.0191 | 12532.1256
| Raw DFO Tank 2,000 M Gal |  | 1 | 1800000 | 1800000 | 75000 | 75000 | 9 | 6 | 8 | 432 | 58.0191 | 25064.2512
| Clean DFO Tank 1,000M Gal |  | 1 | 1300000 | 1300000 | 45000 | 45000 | 9 | 6 | 9 | 486 | 58.0191 | 28197.2826
035FWF100 |  |  | 0 |  |  |  |  | 9 | 0 | 0 | 0 | 58.0191 | 0
| Fire Water System |  | 0 |  |  |  |  | 9 | 0 | 0 | 0 | 58.0191 | 0
| Fire Water Pump Skid |  | 1 | 1000000 | 1000000 | 30000 | 30000 | 9 | 6 | 8 | 432 | 58.0191 | 25064.2512
| Fire Water Foam Skid |  | 1 | 300000 | 300000 | 5000 | 5000 | 9 | 6 | 10 | 540 | 58.0191 | 31330.314
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 |  |  |  |  | 9 | 0 | 0 | 0
[8 empty] | 9 | 0 | 0 | 0
|  |  | 0 | 0 | 16552 | 0 | 882.25 | 9 | 0 | 0 | 0
|  | Totals |  |  | 16568.552 |  | 883.1322 | 9 |  |  | 124686 |  | 7234.1695
[8 empty] | Total Manhours |  |  | 0
[8 empty] | Times Prod Factor |  | 1.8 | 124686 | 58.0191 | 7234.1695
|  |  | 1 | 1800000 | 1800000 | 54000 | 54000 | 9 | 20 | 210 | 37800 | 58.0191 | 2193121.98
[5 empty] | 1800 |  | 54 |  |  |  | 37800 |  | 2193121.98
[8 empty] | Total Manhours |  |  | 37800
| Pipe Valve and fittings | [6 empty] | Times Prod Factor |  | 1.8 | 68040 | 58.0191 | 3947.6196
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 30
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 10.5
44.5
[7 empty] | Contr G&A 8% |  | 3.56
[7 empty] | Contr Mark up 15% |  | 6.675
54.735
[6 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on G137: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on J129: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL
(1,000's)
410 & 460
Project Name: |  | Curapao Power Plant | [8 empty] | Date: | 40486 | 2010-11-04
Customer: |  | PDVSA | [8 empty] | Quote No: | T 1035 - 4A | T 1035 - 4A
Location: |  | Curapao, Venn | [8 empty] | Est By: | WTS/CD | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  | Generators and Prime Systems |  |  |  |  | 3% |  | 9
2 | 035GTG 100, 200.. | Gas Turbine 100, 200, … | 410-01 | 2 | 0 | 0 | 0 | 0 | 9 | 30 | 120 | 64800 | 58.0191 | 3759637.68
|  | Gas Turbine 300, 400 |  | 2 |  |  |  |  | 9 | 12 | 35 | 7560 | 58.0191 | 438624.396
3 | 035DEG 100,200.. | Diesel Generator | 410-02 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
4 | 035EG 100 | Emergency Generator | 410-03 | 1 | 0 | 0 | 0 | 0 | 9 | 6 | 8 | 432 | 58.0191 | 25064.2512
5 | 035TLF | Liquid Fuel Treatment System | 410-04 | 1 | 0 | 0 | 0 | 0 | 9 | 6 | 8 | 432 | 58.0191 | 25064.2512
6 | 035TRW | Water Treatment System | 410-05 | 1 | 0 | 0 | 0 | 0 | 9 | 6 | 30 | 1620 | 58.0191 | 93990.942
7 |  |  | 410-06 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
8 |  |  | 410-07 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
9 | [11 empty] | 0 | 58.0191 | 0
10 |  | 15 KV Equipment | [10 empty] | 58.0191
11 | 035SWGR100 | GTG Breaker 18 KV | 410-'10 | 2 | 550000 | 1100000 | 20000 | 40000 | 9 | 6 | 8 | 864 | 58.0191 | 50128.5024
|  | GTG Breaker 13.8 KV |  | 2 | 150000 | 300000 | 20000 | 40000 | 9 | 4 | 3 | 216 | 58.0191 | 12532.1256
12 | 035SWB15-100 | 15 KV Switchboard | 410-11 | 2 | 100000 | 200000 | 6000 | 12000 | 9 | 3 | 4 | 216 | 58.0191 | 12532.1256
13 | 035SE15-100 | 15 KV Disconnect | 410-12 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
14 | 035FS-100 | Fused Switch | 410-13 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
15 | 035CB15-100 | Cable Bus | 410-14 | 2 | 200000 | 400000 | 12000 | 24000 | 9 | 4 | 6 | 432 | 58.0191 | 25064.2512
16 | 035DB15 | Bus Duct | 410-15 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
17 | 035ISOD18-100 | Iso Phase Bus | 410-16 | 2 | 750000 | 1500000 | 45000 | 90000 | 9 | 6 | 8 | 864 | 58.0191 | 50128.5024
18 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
19 |  | 5 KV Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
20 | 035B5D-100 | Breaker Distribution 5 KV | 410-'20 | 1 | 400000 | 400000 | 1500 | 1500 | 9 | 3 | 5 | 135 | 58.0191 | 7832.5785
21 | 035FS5-100 | Switchboard 5 KV w/ Sync | 410-21 | 1 | 175000 | 175000 | 1500 | 1500 | 9 | 3 | 5 | 135 | 58.0191 | 7832.5785
22 | 035WSB5-100 | Switchboard 5 KV | 410-22 | 1 | 75000 | 75000 | 750 | 750 | 9 | 3 | 2 | 54 | 58.0191 | 3133.0314
23 | 035MCC5-100 | Motor Control Center 5 KV | 410-23 | 0 | 30000 | 0 | 1500 | 0 | 9 | 2 | 3 | 0 | 58.0191
24 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
25 |  | 480 Volt Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
26 | 035DP-1 | Distribution Panel 480 V | 410-27 | 2 | 80000 | 160000 | 750 | 1500 | 9 | 3 | 4 | 216 | 58.0191 | 12532.1256
27 | 035MCC-1 | Motor Control Center 480 V | 410-28 | 3 | 25000 | 75000 | 1500 | 4500 | 9 | 3 | 4 | 324 | 58.0191 | 18798.1884
28 | 035MCCGTG1,2 | Motor Control Center 480 V GTG | 410-29 | 2 | 47000 | 94000 | 3000 | 6000 | 9 | 3 | 5 | 270 | 58.0191 | 15665.157
29 | 035LP-1,2, | 480/277 V Lighting Panel | 410-30 | 1 | 1500 | 1500 | 45 | 45 | 9 | 2 | 2 | 36 | 58.0191 | 2088.6876
30 | 035ALP - 1,2,3 | Area Lighting Pole | 410-31 | 15 | 1500 | 22500 | 150 | 2250 | 9 | 2 | 1 | 270 | 58.0191 | 15665.157
31 | 035AFL - 1… | Area Lighting Flood Light | 410-32 | 45 | 500 | 22500 | 675 | 30375 | 9 | 1 | 0.2 | 81 | 58.0191 | 4699.5471
32 | [12 empty] | 58.0191
33 |  | Aux Transformers |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
34 | 035AXT15/5-1 | Aux Transformer 15/5 KV | 410-36 | 2 | 200000 | 400000 | 12000 | 24000 | 9 | 4 | 4 | 288 | 58.0191 | 16709.5008
35 | 035AXT15/480-1 | Aux Transformer 15KV/480 Volt | 410-37 | 2 | 100000 | 200000 | 6000 | 12000 | 9 | 4 | 4 | 288 | 58.0191 | 16709.5008
36 | 035AXT5/480-1 | Aux Transformer 5KV/480 | 410-38 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
37 | 035AXT480/120-1 | Aux Transformer 480/120/208 Volt | 410-39 | 2 | 5000 | 10000 | 250 | 500 | 9 | 2 | 3 | 108 | 58.0191 | 6266.0628
38 | [12 empty] | 58.0191
39 |  | BOP 120/208 Volt Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
40 | 035LP120-1 | Lighting Panel 120/208 | 410-43 | 3 | 5000 | 15000 | 450 | 1350 | 9 | 2 | 2 | 108 | 58.0191 | 6266.0628
41 | 035LCT - 1 | Lighting Contactor | 410-44 | 2 | 500 | 1000 | 50 | 100 | 9 | 2 | 2 | 72 | 58.0191 | 4177.3752
42 | 035CATH - 100 | Cathodic Protection GTG 100 | 410-45 | 4 | 15000 | 60000 | 1800 | 7200 | 9 | 4 | 5 | 720 | 58.0191 | 41773.752
43 | 035LGT - 100 | Lightning Protection GTG 100 | 410-46 | 4 | 20000 | 80000 | 2400 | 9600 | 9 | 4 | 5 | 720 | 58.0191 | 41773.752
44 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
45 |  | DC Battery Chargers and Batteries |  | 0 | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
46 | 035CHG125-100 | 125 VDC Battery Charger | 410-50 | 2 | 18000 | 36000 | 1500 | 3000 | 9 | 2 | 4 | 144 | 58.0191 | 8354.7504
47 | 035BATT125-100 | 125 VDC Battery | 410-51 | 2 | 18000 | 36000 | 1080 | 2160 | 9 | 2 | 5 | 180 | 58.0191 | 10443.438
48 | 035CHG24-100 | 24 VDC Battery Charger | 410-52 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
49 | 035BATT24-100 | 24 VDC Battery | 410-53 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
50 | 035UPS-100 | UPS System | 410-54 | 2 | 5000 | 10000 | 300 | 600 | 9 | 2 | 3 | 108 | 58.0191 | 6266.0628
51 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
52 | Temporary Electrical |  |  | 1 | 60000 | 60000 | 1800 | 1800 | 9 | 2 | 60 | 1080 | 58.0191 | 62660.628
53 | Modular Control Building |  |  | 1 | 150000 | 150000 | 5000 | 5000 | 9 | 4 | 10 | 360 | 58.0191 | 20886.876
54 |  |  |  |  | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  | 5583500 |  | 321730 | 5583.5 |  | 321.73 |  |  |  | 83133 |  | 4823.3018
[13 empty] | Productivity | 1.8 | 149639.4 | 58.0191 | 8681.9433
56 | Cable Tray, Conduit, & Cable | [5 empty] | 1 | 1500000 | 1500000 | 45000 | 45000 | 9 | 20 | 180 | 32400 | 58.0191 | 1879818.84
57 | [8 empty] | 1500 |  | 45 |  |  |  | 32400 |  | 1879.8188
58 | [11 empty] | Total Manhours |  |  | 32400
59 | [11 empty] | Times Prod Factor |  | 1.8 | 58320 | 58.0191 | 3383.6739
Price per hour based with all labor burdens as follows:
[14 empty] | Local Hrly Cost |  | 30
[14 empty] | Fringes |  | 2.5
[14 empty] | Small Tools |  | 1.5
[14 empty] | Labor Burden 35% |  | 10.5
44.5
[14 empty] | Contr G&A 8% |  | 3.56
[14 empty] | Contr Mark up 15% |  | 6.675
54.735
[13 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[13 empty] | 45 | 50 | 60
[13 empty] | 1.06 | 1.1 | 1.17
Note on N89: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q81: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | Curapao Power Plant | [12 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [12 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [12 empty] | Est By:
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | [8 empty] | 3% |  | 9
2 | 035 GSU 1,2,.. |  | Generator Step Up Trans |  | 410.01 | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 10 | 0 | 58.0191 | 0
3 | 035 152 1,2,… |  | SF6 Breaker |  | 410.02 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 58.0191 | 0
4 | 035 1891,2,.. |  | HV Disconnect |  | 410.03 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 58.0191 | 0
5 | 035 DET 1,2, … |  | Dead End Tower |  | 410.04 | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.05 | 0 | 58.0191 | 0
6 | 035 SP 1,2,.. |  | Static Pole |  | 410.05 | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.5 | 0 | 58.0191 | 0
7 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.4 | 0 | 58.0191 | 0
8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 5 | 0 | 58.0191 | 0
9 | Alum Bus ______ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 58.0191 | 0
10 | Alum Bus Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 58.0191 | 0
11 | Alum Bus End Plugs _____ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.05 | 0 | 58.0191 | 0
12 | Alum Bus Support Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 58.0191 | 0
13 | Alum Bus "V" Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 58.0191 | 0
14 | Static Wire Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 58.0191 | 0
15 | Area Lighting Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 58.0191 | 0
16 | Flood Lights, ______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 58.0191 | 0
17 | #4/0 Grounding Conductor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.03 | 0 | 58.0191 | 0
18 | 3/4"x10'-0" Ground Rods & Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.04 | 0 | 58.0191 | 0
19 | #90 Cadweld Shots |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.3 | 0 | 58.0191 | 0
20 | Metering CT's & CPT's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 58.0191 | 0 | 0
21 | Station Metering w/ In & Out Capabilities |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 58.0191 | 0
22 | Station Protective Relay(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 58.0191 | 0
23 | Station RTU |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 58.0191 | 0
24 | 125V DC System |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 58.0191 | 0
25 | Transmission Line Poles |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 2 | 0 | 58.0191 | 0
26 | Transmission Line Strain Insulators |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 58.0191 | 0 | 0
27 | Cable Bus, Type _____, Size _____ |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 6 | 0 | 58.0191 | 0
28 | Main Power Transformer Oil, ______ Gal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 58.0191 | 0
29 | Main Power Transformer Dress Out & Test |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 58.0191 | 0
30 | Fiber Optic Cable w/ Messenger Cable |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0 | 0
31 | Fiber Optic Cable Fittings & Terminations |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 58.0191 | 0
32 | [10 empty] | 9 |  |  |  | 58.0191
33 | [10 empty] | 9 |  |  |  | 58.0191
34 | [10 empty] | 9 |  |  |  | 58.0191
35 | [10 empty] | 9 |  |  |  | 58.0191 | 0
36 |  |  | Total Cost of Substation Equipment |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
[12 empty] | Total Hours |  | 0
[12 empty] | Prod Factor | 1.8 | 0 | 58.0191 | 0
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 30
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 10.5
44.5
[13 empty] | Contr G&A 8% |  | 3.56
[13 empty] | Contr Mark up 15% |  | 6.675
54.735
[12 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N61: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q53: Insert Rate Here:

## 510 CEMS
CEM's
[5 empty] | (1,000's) |  |  | 510
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Cems | Cost | Cost
1
2 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 120000 | 0
3
4 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 130000 | 0
5
6 | Installation Support |  |  |  |  | 0 | 18000 | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of CEM's |  |  |  |  | 0

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Curapao Power Plant | [8 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [8 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [8 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | [6 empty] | 9
2 | Instrumentation for GTG |  |  | 4 | 100000 | 400000 | 9 | 2 | 10 | 720 | 58.0191 | 41773.752
3 | [6 empty] | 9 |  |  |  | 58.0191 | 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 58.0191 | 0
5 | [6 empty] | 9 |  |  |  | 58.0191
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 58.0191 | 0
7 | [6 empty] | 9 |  |  |  | 58.0191
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 60000 | 60000 | 9 | 2 | 20 | 360 | 58.0191 | 20886.876
9 | [6 empty] | 9 |  |  |  | 58.0191
10 | Instrumentation for Liquid Fuel Treatment |  |  | 1 | 20000 | 20000 | 9 | 2 | 10 | 180 | 58.0191 | 10443.438
11 | [6 empty] | 9 |  |  |  | 58.0191
12 | Instrumentation for gas compressors |  |  | 0 | 15000 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0
13 | [6 empty] | 9 |  |  |  | 58.0191
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0
15 | [6 empty] | 9 |  |  |  | 58.0191
16 | [6 empty] | 9 |  |  |  | 58.0191
17 | [6 empty] | 9 |  |  |  | 58.0191
18 | [6 empty] | 9 |  |  |  | 58.0191
19 | [6 empty] | 9 |  |  |  | 58.0191
20 | [6 empty] | 9 |  |  |  | 58.0191
21 | [6 empty] | 9 |  |  |  | 58.0191
22 | [6 empty] | 9 |  |  |  | 58.0191
23 |  |  | Total Cost of Plant Instrumentation |  |  | 480 |  |  |  | 1260 |  | 73.1041
[8 empty] | Total Hours |  | 1260
[8 empty] | Prod Factor | 1.8 | 2268 | 58.0191 | 131.5873
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 30
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 10.5
44.5
[9 empty] | Contr G&A 8% |  | 3.56
[9 empty] | Contr Mark up 15% |  | 6.675
54.735
[8 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [6 empty] | Cost | Cost
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 750000 | 750000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 4 | 20000 | 80000
5
6 | Documentation |  |  |  |  | 1 | 75000 | 75000
7
8 |  |  |  |  | Total DCS |  |  | 905
9
10 | PBX Communications System |  |  |  |  | 1 | 20000 | 20
11
12 | Loud Speaker System |  |  |  |  | 1 | 20000 | 20
13
14 | TV / Security System |  |  |  |  | 1 | 20000 | 20
15
16
17
[7 empty] | taxable | 830060

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Curapao Power Plant | [6 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  |  | 9
2 | GTG Erection LM 6000 |  |  | 2 | 9 | 24 | 30 | 12960 | 58.0191 | 751927.536
3 |  |  |  |  | 9 |  |  |  | 58.0191
4 | GTG 7 FA |  |  | 2 | 9 | 40 | 60 | 43200 | 58.0191 | 2506425.12
5 |  |  |  |  | 9 |  |  |  | 58.0191
6 | SCR Erection |  |  | 0 | 9 | 10 | 60 | 0 | 58.0191 | 0
7 |  |  |  |  | 9 |  |  |  | 58.0191
8 | Water Treatment and FW Systems |  |  | 1 | 9 | 8 | 20 | 1440 | 58.0191 | 83547.504
9 |  |  |  |  | 9 |  |  |  | 58.0191
10 | Waste Water Treatment System |  |  | 0 | 9 | 6 | 20 | 0 | 58.0191 | 0
11 |  |  |  |  | 9 |  |  |  | 58.0191
12 | BOP Equip Erection |  |  | 1 | 9 | 6 | 10 | 540 | 58.0191 | 31330.314
13 |  |  |  |  | 9 |  |  |  | 58.0191
14 | Gas Compressor Erection |  |  | 0 | 9 | 6 | 5 | 0 | 58.0191 | 0
15 |  |  |  |  | 9 |  |  |  | 58.0191
16 | Evap Cooling Erection |  |  | 0 | 9 | 4 | 4 | 0 | 58.0191 | 0
17 |  |  |  |  | 9 |  |  |  | 58.0191
18 | Fire Water Pump Skid |  |  | 1 | 9 | 4 | 4 | 144 | 58.0191 | 8354.7504
19 |  |  |  |  | 9 |  |  |  | 58.0191
20 | STG Erection |  |  | 0 | 9 | 12 | 36 | 0 | 58.0191 | 0
21 |  |  |  |  | 9 |  |  |  | 58.0191
22 | STG Cooling Tower |  |  | 0 | 9 | 8 | 8 | 0 | 58.0191 | 0
23 |  |  |  |  | 9 |  |  |  | 58.0191
24 |  |  |  |  | 9 |  |  |  | 58.0191
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 58284 |  | 3381.5852
[6 empty] | Total Hours |  | 58284
[6 empty] | Prod Factor | 1.8 | 104911.2 | 58.0191 | 6086.8534
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 30
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 10.5
44.5
[7 empty] | Contr G&A 8% |  | 3.56
[7 empty] | Contr Mark up 15% |  | 6.675
54.735
[6 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Curapao Power Plant | [6 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total
No. | [5 empty] | Units | Unit | Days | Per Day | Cost
1 | GTG Equip Rental per ea GTG
2 | 1 ea 450 Ton Crane w/ operator |  |  |  |  | 2 | 20 | 40 | 7500 | 300000
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 2 | 60 | 120 | 3200 | 384000
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
8 | 1 ea Man Lift |  |  |  |  | 0 | 0 | 0 | 80 | 0
9 | 2 ea Welders |  |  |  |  | 5 | 120 | 600 | 100 | 60000
10
11 | LM 6000
12 | 1 ea 450 Ton Crane w/ operator |  |  |  |  | 2 | 10 | 20 | 7500 | 150000
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 2 | 30 | 60 | 3200 | 192000
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 5 | 120 | 600 | 100 | 60000
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 1 | 240 | 240 | 2500 | 600000
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 2 | 240 | 480 | 2000 | 960000
51 | 2 ea Fork Lifts |  |  |  |  | 5 | 240 | 1200 | 550 | 660000
52 | 2 ea Sky Tracs |  |  |  |  | 3 | 240 | 720 | 550 | 396000
53 | 2 ea Pick ups |  |  |  |  | 8 | 240 | 1920 | 100 | 192000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 4 | 240 | 960 | 200 | 192000
55 | Welders |  |  |  |  | 20 | 240 | 4800 | 100 | 480000
56 | Substation Equip Rental
57 | 1 ea 450 Ton Crane w/ operator |  |  |  |  | 4 | 5 | 20 | 7500 | 150000
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 30 | 30 | 3200 | 96000
60 | 2 ea Fork Lifts |  |  |  |  | 2 | 30 | 550 | 80 | 44000
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 4 | 60 | 240 | 100 | 24000
63
64
65 | Mobilization and Demobilization |  |  |  |  | 1 |  |  |  | 250000
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 11810 |  | 5190

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Paint for GTG |  |  |  |  | 4 | 80000 | 320000
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 4 | 25000 | 100000
9
10 | Paint for BOP Equipment |  |  |  |  | 1 | 125000 | 125000
11
12 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0
13
14 | Paint for Water Treatment |  |  |  |  | 1 | 30000 | 30000
15
16 | Paint for Waste Water Treatment |  |  |  |  | 0 | 15000 | 0
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 575

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 882.25 | 882.25
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 321.73 | 321.73
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 0 | 0
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 54 | 54
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 45 | 45
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 1302.98

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | Curapao Power Plant | [6 empty] | Date: | 2010-11-04
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn | [6 empty] | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 6 | 18 | 900 | 97200
3 | Porta Potties |  |  |  |  | 8 | 18 | 150 | 21600
4 | Water and Ice |  |  |  |  | 8 | 18 | 500 | 72000
5 | Fed X |  |  |  |  | 1 | 18 | 300 | 5400
6 | Telephone |  |  |  |  | 1 | 18 | 2500 | 45000
7 | Office Supplies |  |  |  |  | 1 | 18 | 1000 | 18000
8
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 2 | 18 | 3000 | 108000
10 | Misc Items |  |  |  |  | 1 | 18 | 3000 | 54000
11 |  |  | Total Monthly Cost | [5 empty] | 421200
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 421200 |  | 421200
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 250000
21 | Cad Station | [8 empty] | 10000
22 | Computers | [8 empty] | 15000
23 | Telephone System and Satalite Dish | [8 empty] | 20000
24 | Plotter | [8 empty] | 6000
25 | Fax Machine and Printers | [8 empty] | 5000
26 | Misc equip | [8 empty] | 50000
27 | Signs | [8 empty] | 5000
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 782.2

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Conceptual Engineering |  |  |  |  | 1 | 45000 | 45000
3
4 | Detailed Engineering per GTG 7 FA |  |  |  |  | 2 | 1400000 | 2800000
5
6 | Detailed Engineering per LM 6000 |  |  |  |  | 2 | 350000 | 700000
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering for Liquid Fuel |  |  |  |  | 1 | 200000 | 200000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 1 | 35000 | 35000
13
14 | Detailed Engineering per Structural Steel/Civil |  |  |  |  | 1 | 200000 | 200000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 3980

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Resident Engineer |  |  |  |  | 10 | 10000 | 100000
3
4 | Civil Engineer |  |  |  |  | 4 | 10000 | 40000
5
6 | Mechanical Engineer |  |  |  |  | 10 | 10000 | 100000
7
8 | Electrical Engineer |  |  |  |  | 10 | 10000 | 100000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 340

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Mos | Per Mo | Cost
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 10 | 16000 | 160000
2 | Admin Mgr Months on Project |  |  |  |  | 10 | 10000 | 100000
3 | Scheduler |  |  |  |  | 16 | 10000 | 160000
4 | Purchasing Agent |  |  |  |  | 32 | 8000 | 256000
5 | Expediter |  |  |  |  | 6 | 8000 | 48000
6 | Home Office Logistic Coordinator |  |  |  |  | 8 | 10000 | 80000
7
8
9 | [6 empty] | 804000
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 30 | 5000 | 150000
18 | Construction Mngr |  |  |  |  | 10 | 15000 | 150000
19 | Contract Cost Admin |  |  |  |  | 10 | 5000 | 50000
20 | Scheduler |  |  |  |  | 10 | 9000 | 90000
21 | Mechanical Supervisor |  |  |  |  | 20 | 12000 | 240000
22 | Electrical Supervisor |  |  |  |  | 20 | 12000 | 240000
23 | Civil Supervisor |  |  |  |  | 20 | 12000 | 240000
24 | Clerks |  |  |  |  | 30 | 5000 | 150000
25 | Warehousemen |  |  |  |  | 20 | 6000 | 120000
26 | Draftsman |  |  |  |  | 2 | 8000 | 16000
27 | Security |  |  |  |  | 10 | 20000 | 200000
28 | Safety |  |  |  |  | 20 | 9000 | 180000
29 | QA/QC Mngr |  |  |  |  | 80 | 10000 | 800000
30
31
32 | [6 empty] | 2626000
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 20 | 15000 | 300000
35
36
37
38 | Training |  |  |  |  | 1 | 0 | 250000
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 3980
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 6 | 12000 | 72000
47 | Mechanical __ ea ___ mos |  |  |  |  | 16 | 12000 | 192000
48 | Electrical __ ea ___ mos |  |  |  |  | 16 | 12000 | 192000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 16 | 12000 | 192000
50
51 |  |  |  |  | Total Inspectors |  |  | 648000
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Units | Per Unit | Cost
1
2 | Project & Construciton Management
3 | R T Air Fares |  |  |  |  | 240 | 1500 | 360000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 300 | 5400 | 1620000
5 | Number of Months of Buses |  |  |  |  | 1200 | 100 | 120000
6 | Misc expenditures |  |  |  |  | 1 | 250000 | 250000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 300 | 5400 | 1620000
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 50 | 1500 | 75000
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 500 | 90 | 45000
16 | Auto Rental for Eng Days at Site |  |  |  |  | 500 | 100 | 50000
17 | Misc Travel Expentitures |  |  |  |  | 1 | 50000 | 50000
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 4190
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36

## 1900 Sales Tax
SALES TAXES
[5 empty] | (1,000's) |  |  | 1900
Project Name: |  | Curapao Power Plant |  |  |  |  | Date: | 2010-11-04
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1035 - 4A
Location: |  | Curapao, Venn |  |  |  |  | Est By: | WTS/CD
Bid Due Date: |  | 2010-11-04
Item |  | Description |  |  |  | Total | State | Total
No. | [5 empty] | Cost | Tax | Taxes
1
2 | Major Mechanical Equipment |  |  |  |  | 18352 | 0.085 | 1559.92
3
4 | Major Electrical Equipment |  |  |  |  | 7083.5 | 0 | 0
5
6 | Substation Equipment |  |  |  |  | 0 | 0 | 0
7
8 | DCS Eqipment |  |  |  |  | 830060 | 0 | 0
9
10 | Instrument |  |  |  |  | 480 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28 |  |  | Total Cost of Plant Sales Taxes |  |  |  |  | 0