**Site Address:**

CA.LA ELECTRICIDAD DE CARACAS (EDC)

Carretera Nacional Guarenas Guatire, Km 3

Deposito Eleggua, Electricidad de Caracas

**Contract Information:**

Pro Energy Services contracted by Derwick to execute EPC Contract

Derwick contracted by EDC: EDC is the End Client

Engineering services provided by EDGI, Tulsa, Oklahoma

Vepica contracted by EDC to provide QA/QC as eyes for EDC

Contract Signatory Date: 22MAR10

**Temperature & Site Conditions:** High 31/32; Low 22/24; 80 - 85% Humidity;

**Personal on Site:**

J D Robinson Project Manager 0424 232 0528

Roger Barr Construction Superintendent 0424 156 4962

Mike Shingle Civil Superintendent 0424 157 6067

Thabang Malebye Logistics / Warehouse Manager 0414 399 6192

Scott Blair Scheduler 0424 215 1508

Jose Isaya Logistics Assistant 0416 402 2202

Edwin Isea Resident Electrical Engineer 0412 238 0005

Eric Martin Administrative Assistant 0424 106 5474

Luis Nunez Logistics Assistant 0424 158 2387

Jesus Van Der Velde Resident Mechanical Engineer 0424 157 1237

Clayton Ely Quality Assurance / Quality Control 0424 157 7508

Nicole Martinez SHA Manager 0424 215 3087

Terry Henry Electrical Superintendent 0424 216 5507

Luis Garcia Administrative Assistant 0414 174 6245

**General Items:**

* Power Block, Site North Side and Fuel Block, Site South Side, Foundation Excavation and Forming
* National Guard quarters Refurbishment. Bathroom and roof work is on-going due to water leaks. Punch List items remain and being worked.
* Ship is in port and equipment is in customs. First truck containing our tool conex arrived and inventory has been completed and variances bring addressed.
* Warehouse and the EDC Material; All material has been relocated. Clean up of area has been started and on-going; to include sidewalks, cut back trees, painting of gutters, and pickup of left over material.
* Clean up and organization of EDC material in warehouse on-going.

**Action Items:**

* Pre tie forming of rebar for 2500 ready, waiting for extension of seal slab.
* Underground electrical duct banks on going.
* Unit Aux Transformer Foundation and coordinates required.
* Main Control room forms being installed and rebar being installed.
* Excavated Control Room/Warehouse footprint.

**Civil:**

* National Guard Quarters Refurbishment: Overall completion at 97%’.
* Inlet approach to site curbing curb painted and landscaping to begin.
* Center approach island poured. Small upper section to be knocked out and joined to curb.
* Side walk close to E wall has been poured and curb has been painted safety yellow.
* Demin tank and raw water tank painted and back filled.
* Cleaning of roadway began 2Aug and is on-going.
* Continued site grading due to heavy rain on 2Aug.

**Concrete/Foundations:**

* Unit 100 Mechanical Shed: Poured Slab on Grade.
* Unit 200 Mechanical Shed: Poured Slab on Grade
* Unit 300 and Unit 400 GSU: Poured Base
* Control room 200 footings poured, Pier rebar complete, forming on-going.
* Control room 100.footings poured, Pier rebar complete, forming on-going.
* Control room 300/400 footing poured, working rebar.
* Inlet approach at center island 6 ft of curb repaired.
* Installation of containment wall steel for transformers on-going.
* Pre-tying steel for main control warehouse.

**Mechanical:**

* Waiting on quote from tank fabrication vendor from site visit meeting.

**Electrical:**

* Excavation of duct bank on NE GSU corner.

**Scheduled Items:**

* National Guard side walk west side of building wall re-painted, delayed by rain again. Estimate completion by close of business 8-4-10
* Light pole on inlet approach is bent over and paper work sent to EDC to repair or replace pole.
* Compact and pour seal slab at Control Room/Warehouse.

**Critical Areas of Concerns;**

* **We need a schedule from EDC on when the services will be installed; these include the water pipe line, the gas pipe line and the 1.5 MWATT construction temp feeder for commissioning the plant.**
* Underground drawing’s still major concern.