**Site Address:**

CA.LA ELECTRICIDAD DE CARACAS (EDC)

Carretera Nacional Guarenas Guatire, Km 3

Deposito Eleggua, Electricidad de Caracas

**Contract Information:**

Pro Energy Services contracted by Derwick to execute EPC Contract

Derwick contracted by EDC: EDC is the End Client

Engineering services provided by EDGI, Tulsa, Oklahoma

Vepica contracted by EDC to provide QA/QC as eyes for EDC

Contract Signatory Date: 22MAR10

**Temperature & Site Conditions:** High 29 Low 27, 80 - 85% Humidity;

**Personal on Site:**

J D Robinson Project Manager 0424 232 0528

Roger Barr Construction Superintendent 0424 156 4962

Mike Shingle Civil Superintendent 0424 157 6067

Thabang Malebye Logistics / Warehouse Manager 0414 399 6192

Scott Blair Scheduler 0424 215 1508

Jose Isaya Logistics Assistant 0416 402 2202

Edwin Isea Resident Electrical Engineer 0412 238 0005

Eric Martin Administrative Assistant 0424 106 5474

Luis Nunez Logistics Assistant 0424 158 2387

Jesus Van Der Velde Resident Mechanical Engineer 0424 157 1237

Clayton Ely Quality Assurance / Quality Control 0424 157 7508

Nicole Martinez SHA Manager 0424 215 3087

Terry Henry Electrical Superintendent 0424 216 5507

Luis Garcia Administrative Assistant 0414 174 6245

**General Items:**

* National Guard quarters Refurbishment. Bathroom and roof work is on-going due to water leaks. Complete roof was re-tarred and ready for rain test, again.
* Ship is in port severe storm has delayed offload till 7 Aug.
* Warehouse and the EDC Material; All material has been relocated. Clean up of area has been started and on-going; to include sidewalks, cut back trees, painting of gutters, and pickup of left over material.
* Steve Fields arrived on site 2 Aug for the week.

**Action Items:**

Underground electrical duct banks on going.

* Unit Aux Transformer Foundation and coordinates required.
* Main Control room forms being installed and rebar being installed.

**Civil:**

* National Guard Quarters Refurbishment: Overall completion at 97%’.currently at stand still for completion of punch list, which includes rain test of roof.
* Inlet approach to site curbing curb painted and landscaping to begin.
* Center approach island completed..
* Demin tank and raw water tank painted and back filled.
* Cleaning of roadway began 2Aug and is on-going.
* De-water tanks due to late rain yesterday, 4 Aug.

**Concrete/Foundations:**

* Unit 300 and Unit 400 GSU: Poured Base
* Control room 200 footings poured, ready to pour Monday, 9 Aug.
* Control room 100.piers poured today.
* Control room 300/400 footing poured, working rebar.
* Inlet approach at center island completed and painted safety yellow.
* Installation of containment wall steel for transformers on-going, GSU # 100 is complete,
* Pre-tying steel for main control warehouse.

**Mechanical:**

* Waiting on quote from tank fabrication vendor from site visit meeting.

**Electrical:**

* Excavation of duct bank on NE GSU corner.

**Scheduled Items:**

* National Guard side walk west side of building wall re-painting completed. To start North wall 7 Aug.
* Light pole on inlet approach is bent over and paper work sent to EDC to repair or replace pole.
* Compact and pour seal slab at Control Room/Warehouse.
* GSU # 100 containment wall ready to pour 9 Aug, ( no concrete on Sat. or Sun. )

**Critical Areas of Concerns;**

* **We need a schedule from EDC on when the services will be installed; these include the water pipe line, the gas pipe line and the 1.5 MWATT construction temp feeder for commissioning the plant.**
* **Water Treatment module requires 320 GPM to function correctly.**
* Underground drawing’s still major concern.