**Site Address:**

CA.LA ELECTRICIDAD DE CARACAS (EDC)

Carretera Nacional Guarenas Guatire, Km 3

Deposito Eleggua, Electricidad de Caracas

**Contract Information:**

Pro Energy Services contracted by Derwick to execute EPC Contract

Derwick contracted by EDC: EDC is the End Client

Engineering services provided by EDGI, Tulsa, Oklahoma

Vepica contracted by EDC to provide QA/QC as eyes for EDC

Contract Signatory Date: 22MAR10

**Temperature & Site Conditions:** High 28 Low 22, 85 - 90% Humidity;

**Personal on Site:**

J D Robinson Project Manager 0424 232 0528

Roger Barr Construction Superintendent 0424 156 4962

Mike Shingle Civil Superintendent 0424 157 6067

Thabang Malebye Logistics / Warehouse Manager 0414 399 6192

Scott Blair Scheduler 0424 215 1508

Jose Isaya Logistics Assistant 0416 402 2202

Edwin Isea Resident Electrical Engineer 0412 238 0005

Eric Martin Administrative Assistant 0424 106 5474

Luis Nunez Logistics Assistant 0424 158 2387

Jesus Van Der Velde Resident Mechanical Engineer 0424 157 1237

Clayton Ely Quality Assurance / Quality Control 0424 157 7508

Nicole Martinez SHA Manager 0424 215 3087

Terry Henry Electrical Superintendent 0424 216 5507

Luis Garcia Administrative Assistant 0414 174 6245

**General Items:**

* National Guard quarters Refurbishment: Inspected all rooms after 2 nights of heavy rain, and could not find any wet floors, except Latrine and that is being caused by plumbing to toilet stools.
* Site curbs near trailers were power washed and painting completed.
* What was one trailer to arrive, turned out to be 11 trucks of which 9 needed to be unloaded on site due to weight limit of our forklift on warehouse site.
* Steve Fields departed site on 8 Aug 2010.
* Main Control Room formed, rebar being tied and show be complete by end of day.
* Dewatering of plant on Monday morning as result of rain. Thunder storms forcasted for rest of week.

**Action Items:**

* Unit Aux Transformer Foundation and coordinates required.
* Main Control room forms being installed and rebar being installed.
* Under ground duct bank work continues near unit 100.

**Civil:**

* National Guard Quarters Refurbishment: Overall completion at 97%’.currently at stand still for completion of punch list.
* Cleaning of roadway began 2Aug and is on-going.
* GSU 100 & 200 back fill complete.

**Concrete/Foundations:**

* Unit 300 and Unit 400 GSU: Poured Base
* Control room 200 footings poured; Concrete work cancelled due to rain.
* Control room 100.piers poure
* Installation of containment wall steel for transformers on-going, GSU # 100 is complete,
* Pre-tying steel for main control warehouse.

**Mechanical:**

* Waiting on quote from tank fabrication vendor from site visit meeting.

**Electrical:**

* Excavation of duct bank from NE GSU corner south to unit 100 continues.

**Scheduled Items:**

* National Guard North wall painting complete and kitchen tile is complete.
* Light pole on inlet approach is bent over and paper work sent to EDC to repair or replace pole, 2 weeks now and still no action taken.
* GSU # 100 containment wall ready to pour 9 Aug: pouring cancelled due to rain. Rescheduled 10 Aug.
* GSU # 200 containment wall to pour 10 Aug, Rescheduled 11 Aug.
* GSU # 300 containment wall to pour 11 Aug, rescheduled 12 Aug.

**Critical Areas of Concerns;**

* **We need a schedule from EDC on when the services will be installed; these include the water pipe line, the gas pipe line and the 1.5 MWATT construction temp feeder for commissioning the plant.**
* **Water Treatment module requires 320 GPM to function correctly.**
* Underground drawing’s still major concern.
* Began receiving truck loads of equipment from the ship. One truck of cargo damaged. The damage will be evaluated today and pictures taken for record.