## Summary
ProEnergy EPC
Proj. Descript: |  |  | 2 x LM6000 + 2 x LM2500+ + LFO treat & storage + Water treat & storage + Gas Compressors + Black Start
Project Name: |  |  | Guarenas | [5 empty] | Status Date: |  | 2010-09-16
Customer: |  |  | Derwick | [5 empty] | Project No: |  | 10-T 1009 | [10 empty] | VARIANCE = USD ONLY
Location: |  |  | Guatire, Venn | [17 empty] | FORECASTED | CURRENT BUDGET -
[15 empty] | EQUIV. USD TOTAL | VZ BsF ONLY TOTAL | USD ONLY TOTAL | EQUIV. USD TOTAL |  |  | USD ONLY COST | FORECAST USD ONLY
| COST ITEM DESCRIPTION | [5 empty] | ORIGINAL BUDGET |  | CO #1 |  | CO #2 |  | CO #3 |  | CURRENT BUDGET | COST TO DATE | COST TO DATE | COST TO DATE |  |  | AT COMPLETION | AT COMPLETION
[9 empty] | 2nd 6000+LFO |  | Gas |  | Black Start |  |  |  |  | BsF/1.0 Equiv. USD =
|  |  |  | All Construction |  |  |  |  | +WT+HV |  | Compressors |  | Capability |  |  |  |  | 6 | All Construction
| 100 Civil Structural |  |  | 17834000 | 35.02% | [13 empty] | 4576227.5 | 28.21%
| 190 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 95285 | 95285 | 25.66% |  | 280250 | -280250
| 101 | Site Preparation |  |  |  |  | 236000 |  | 178000 |  | 26000 |  | 2000 |  | 442000 | 5662488 | 0 | 943748 |  |  | 0 | na
| 102 | Excavation - Fill |  |  |  |  | 236000 |  | 178000 |  | 7000 |  | 0 |  | 421000 | 2324677 | 0 | 387446.1667 |  |  | 0 | na
| 103 | Concrete Foundations |  |  |  |  | 1160000 |  | 698000 |  | 557000 |  | 35000 |  | 2450000 | 1369449 | 11441 | 239682.5 |  |  | 33650 | -33650
| 104 | Concrete Pilings |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 817735 | 0 | 136289.1667 |  |  | 0 | na
| 105 | Paving Asphalt - Concrete |  |  |  |  | 290000 |  | 210000 |  | 0 |  | 0 |  | 500000 | 669036 | 0 | 111506 |  |  | 0 | na
| 106 | Gravel - Sand |  |  |  |  | 71000 |  | 69000 |  | 8000 |  | 2000 |  | 150000 | 6720 | 0 | 1120 |  |  | 0 | na
| 107 | Structual Steel |  |  |  |  | 166000 |  | 70000 |  | 35000 |  | 4000 |  | 275000 | 1002272 | 0 | 167045.3333 |  |  | 0 | na
| 108 | Fencing |  |  |  |  | 96000 |  | 0 |  | 0 |  | 0 |  | 96000 | 242431 | 0 | 40405.1667 |  |  | 0 | na
| 109 | Architectual Treatment |  |  |  |  | 50000 |  | 0 |  | 0 |  | 0 |  | 50000 | 0 | 0 | 0 |  |  | 0 | na
| 110 | Evaporation Pond |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | na
[7 empty] | 2305000 |  | 1403000 |  | 633000 |  | 43000 |  | 4384000 | 12094808 | 106726 | 2122527.3333 |  |  | 313900 | -313900
| 200 Buildings | [5 empty] | 540000 |  | 239000 |  | 180000 |  | 45000 |  | 1004000 | 0 | 369977 | 369977 |  |  | 500000 | 504000
[7 empty] | 540000 |  | 239000 |  | 180000 |  | 45000 |  | 1004000 | 0 | 369977 | 369977 |  |  | 500000 | 504000
|  |  |  | All Procure/Trans/Reps | [14 empty] | All Procure/Trans/Reps
| 300 Mechanical |  |  | 29168778 | 57.28% | [13 empty] | 10165753.65 | 62.66%
| 390 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 43712 | 43712 | 34.85% |  | 128564.7059 | -128564.7059
| 315 | Fire Water System |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 31345 | 31345 |  |  | 100000 | -100000
| 310 | Major Mechanical Equipment |  |  |  |  | 1115000 |  | 1543000 | 4465000 | 20000 | 4465000 | 256000 |  | 2934000 | 911190 | 1368709 | 1520574 |  |  | 2500000 | 434000 | 7230000
| 310.03 | Exhaust Stacks |  |  |  |  | 660000 |  | 0 |  | 0 |  | 0 |  | 660000 | 0 | 0 | 0 |  |  | 500000 | 160000
| 310.38 | Fuel Gas Compressors w/ Fin Fans |  |  |  |  | 0 |  | 0 |  | 2300000 |  | 0 |  | 2300000 | 0 | 1322620 | 1322620 |  |  | 1600000 | 700000
| 310.39 | Fuel Gas Check Metering/Regulator Skid |  |  |  |  | 0 |  | 0 |  | 175000 |  | 0 |  | 175000 | 0 | 0 | 0 |  |  | 0 | 175000
| 310.45 | LF Unloading Pumps Skid |  |  |  |  | 30000 |  | 30000 |  | 0 |  | 0 |  | 60000 | 0 | 0 | 0 |  |  | 100000 | -40000
| 310.46 | LF Metering Skid |  |  |  |  | 145000 |  | 0 |  | 0 |  | 0 |  | 145000 | 0 | 0 | 0 |  |  | 0 | 145000
| 310.47 | LF Forwarding Pumps Skids |  |  |  |  | 25000 |  | 50000 |  | 0 |  | 0 |  | 75000 | 0 | 53183 | 53183 |  |  | 120000 | -45000
| 310.5 | LF Filter Skids |  |  |  |  | 120000 |  | 0 |  | 0 |  | 0 |  | 120000 | 0 | 0 | 0 |  |  | 160000 | -40000
| 310.51 | LF Centrifuge Skid |  |  |  |  | 300000 |  | 0 |  | 0 |  | 0 |  | 300000 | 0 | 390500 | 390500 |  |  | 450000 | -150000
| 310.53 | Raw LF Storage Tank |  |  |  |  | 700000 |  | 300000 |  | 0 |  | 0 |  | 1000000 | 0 | 0 | 0 |  |  | 1200000 | -200000
| 310.54 | Treated LF Storage Tank |  |  |  |  | 250000 |  | 0 |  | 0 |  | 0 |  | 250000 | 0 | 2060 | 2060 |  |  | 300000 | -50000
| 310.57 | Raw/Fire Water Storage Tank |  |  |  |  | 250000 |  | 650000 |  | 0 |  | 0 |  | 900000 | 0 | 5404 | 5404 |  |  | 1100000 | -200000
| 310.63 | Water Injection Skids |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 167900 | 167900 |  |  | 220000 | -220000
| 310.64 | Demin Treatment System |  |  |  |  | 150000 |  | 150000 |  | 0 |  | 0 |  | 300000 | 0 | 365155 | 365155 |  |  | 420000 | -120000
| 310.65 | Demin Water SS Tank |  |  |  |  | 0 |  | 300000 |  | 0 |  | 0 |  | 300000 | 0 | 2060 | 2060 |  |  | 400000 | -100000
| 310.68 | Water Injection Filters Skids |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 91572 | 91572 |  |  | 200000 | -200000
| 310.78 | Fire Water Pump Skid |  |  |  |  | 650000 |  | 0 |  | 0 |  | 0 |  | 650000 | 0 | 337400 | 337400 |  |  | 400000 | 250000
| 310.87 | Instrument Air Compressor Pkg |  |  |  |  | 70000 |  | 0 |  | 0 |  | 0 |  | 70000 | 0 | 48310 | 48310 |  |  | 60000 | 10000
| 320 | Pipe, Valves & Fitting labor | [6 empty] | 140000 |  | 0 |  | 22000 |  | 162000 | 0 | 0 | 0 |  |  | 0 | na
| 330 | Mechanical Subcontractor |  |  |  |  | 1154000 |  | 596000 |  | 153000 |  | 9000 |  | 1912000 | 0 | 0 | 0 |  |  | 0 | na
| 340 | Pipe, Valves & Fitting Material |  |  |  |  | 600000 |  | 425000 |  | 320000 |  | 22000 |  | 1367000 | 0 | 18560 | 18560 |  |  | 1200000 | 167000
[7 empty] | 6219000 |  | 4184000 |  | 2968000 |  | 309000 |  | 13680000 | 911190 | 4248490 | 4400355 |  |  | 11158564.7059 | 447435.2941
400 Electrical
| 490 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 34457 | 34457 |  |  | 101344.1176 | -101344.1176
| 410 | Major Electrical Equipment |  |  |  |  | 898000 |  | 376000 | 1253000 | 165000 | 1253000 | 110000 | 1253000 | 1549000 | 0 | -748573 | -748573 |  |  | 1000000 | 549000 | 1230000
| 410.11 | Generator Breaker(s) |  |  |  |  | 135000 |  | 135000 |  | 0 |  | 0 |  | 270000 | 0 | 604504 | 604504 |  |  | 750000 | -480000
| 410.12 | Distribution Breaker(s) |  |  |  |  | 0 |  | 0 |  | 360000 |  | 0 |  | 360000 | 0 | 155159 | 155159 |  |  | 200000 | 160000
| 410.2 | 5kV MCCs |  |  |  |  | 0 |  | 0 |  | 125000 |  | 0 |  | 125000 | 0 | 56000 | 56000 |  |  | 80000 | 45000
| 410.33 | Aux Transformers, 15kV/5kV |  |  |  |  | 0 |  | 0 |  | 95000 |  | 0 |  | 95000 | 0 | 106808 | 106808 |  |  | 120000 | -25000
| 410.34 | Aux Transformers, 15kV/600V |  |  |  |  | 220000 |  | 48000 |  | 55000 |  | 0 |  | 323000 | 0 | 50728 | 50728 |  |  | 80000 | 243000
| 420 | Substation Equipment |  |  |  |  | 540000 |  | 239778 | 2240000 | 0 | 2240000 | 0 | 2240000 | 779778 | 0 | 379760 | 379760 |  |  | 900000 | -120222 | 2025000
| 420.02 | Generator Stepup Transformers |  |  |  |  | 1400000 |  | 450000 |  | 0 |  | 0 |  | 1850000 | 0 | 1355900 | 1355900 |  |  | 1600000 | 250000
| 420.03 | SF6 Circuit Breakers |  |  |  |  | 110000 |  | 52500 |  | 0 |  | 0 |  | 162500 | 0 | 249500 | 249500 |  |  | 300000 | -137500
| 420.04 | Disconnect Switches |  |  |  |  | 90000 |  | 7500 |  | 0 |  | 0 |  | 97500 | 0 | 0 | 0 |  |  | 0 | 97500
| 420.08 | Dead End Towers |  |  |  |  | 100000 |  | 30000 |  | 0 |  | 0 |  | 130000 | 0 | 102584 | 102584 |  |  | 125000 | 5000
| 430 | Plant Electrical Subcontractor |  |  |  |  | 1279000 |  | 540000 |  | 284000 |  | 7000 |  | 2110000 | 1045598 | 0 | 174266.3333 |  |  | 0 | na
| 440 | Substation Subcontractor |  |  |  |  | 561000 |  | 500000 |  | 0 |  | 0 |  | 1061000 | 0 | 14600 | 14600 |  |  | 60000 | -60000
| 450 | Conduit, Cable & Wire Material |  |  |  |  | 700000 |  | 445000 |  | 290000 |  | 15000 |  | 1450000 | 0 | 666709 | 666709 |  |  | 1200000 | 250000
| 460 | Conduit, Cable & Wire Labor |  |  |  |  | 943000 |  | 608000 |  | 419000 |  | 24000 |  | 1994000 | 0 | 0 | 0 |  |  | 0 | na
[7 empty] | 6976000 |  | 3431778 |  | 1793000 |  | 156000 |  | 12356778 | 1045598 | 3028136 | 3202402.3333 |  |  | 6516344.1176 | 675433.8824
500 Instrumentation
| 590 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 62364 | 62364 |  |  | 183423.5294 | -183423.5294
| 510 | CEMS | [12 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 520 | Plant Instrumentation |  |  |  |  | 110000 |  | 80000 |  | 75000 |  | 15000 |  | 280000 | 0 | 87379 | 87379 |  |  | 300000 | -20000
| 530 | Instrumentation Subcontractor |  |  |  |  | 112000 |  | 65000 |  | 70000 |  | 7000 |  | 254000 | 0 | 0 | 0 |  |  | 0 | na
[7 empty] | 222000 |  | 145000 |  | 145000 |  | 22000 |  | 534000 | 0 | 149743 | 149743 |  |  | 483423.5294 | -203423.5294
600 DCS System / Communications
| 690 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 2942 | 2942 |  |  | 8652.9412 | -8652.9412
| 610 | Hardware / Software |  |  |  |  | 345000 |  | 95000 |  | 80000 |  | 0 |  | 520000 | 73346.9 | 36961 | 49185.4833 |  |  | 800000 | -280000
| 620 | Telephone System |  |  |  |  | 15000 |  | 0 |  | 0 |  | 0 |  | 15000 | 0 | 0 | 0 |  |  | 0 | 15000
| 630 | Public Address System |  |  |  |  | 15000 |  | 0 |  | 0 |  | 0 |  | 15000 | 0 | 0 | 0 |  |  | 0 | 15000
| 640 | TV / Security | [12 empty] | 0 | 184915 | 0 | 30819.1667 |  |  | 0 | na
[7 empty] | 375000 |  | 95000 |  | 80000 |  | 0 |  | 550000 | 258261.9 | 39903 | 82946.65 |  |  | 808652.9412 | -258652.9412
700 Plant Erection
| 790 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 88280 | 88280 |  |  | 259647.0588 | -259647.0588
| 700 | Plant Erection |  |  |  |  | 1406000 |  | 405000 |  | 140000 |  | 19000 |  | 1970000 | 0 | 0 | 0 |  |  | 0 | na
| 750 | Plant Dismantling | [12 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 755 | Plant Dismantling Labor | [12 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0
[7 empty] | 1406000 |  | 405000 |  | 140000 |  | 19000 |  | 1970000 | 0 | 88280 | 88280 |  |  | 259647.0588 | -259647.0588
| 800 Equipment Rental | [5 empty] | 1048000 |  | 256000 |  | 32000 |  | 19000 |  | 1355000 | 1439357 | 93264 | 333156.8333 |  |  | 274305.8824 | -274305.8824
[7 empty] | 1048000 |  | 256000 |  | 32000 |  | 19000 |  | 1355000 | 1439357 | 93264 | 333156.8333 |  |  | 274305.8824 | -274305.8824
| 900 Painting | [5 empty] | 340000 |  | 155000 |  | 25000 |  | 5000 |  | 525000 | 48731 | 3303 | 11424.8333 |  |  | 9714.7059 | -9714.7059
[7 empty] | 340000 |  | 155000 |  | 25000 |  | 5000 |  | 525000 | 48731 | 3303 | 11424.8333 |  |  | 9714.7059 | -9714.7059
1000 Transportation
| 1090 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 12452 | 12452 |  |  | 36623.5294 | -36623.5294
| 1010 | Export Crating |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 125276 | 125276 |  |  | 500000 | -500000
| 1001 | US Inland Transportation |  |  |  |  | 614000 |  | 230000 |  | 187000 |  | 3000 |  | 1034000 | 384454 | 114660 | 178735.6667 |  |  | 800000 | 34000
| 1002 | Ocean/Air Freight |  |  |  |  | 1800000 |  | 2034000 |  | 350000 |  | 40000 |  | 4224000 | 0 | 973534 | 973534 |  |  | 3500000 | 724000
| 1003 | Destination Inland Freight |  |  |  |  | 900000 |  | 642000 |  | 250000 |  | 40000 |  | 1832000 | 10192 | 661675 | 663373.6667 |  |  | 2400000 | -568000
| 1004 | Customs / Duties (plant equip & mat'l) |  |  |  |  | 50000 |  | 32000 |  | 0 |  | 0 |  | 82000 | 0 | 0 | 0 |  |  | 0 | 82000
| 1005 | Unload & Receive Mat'l at Site | [12 empty] | 0 | 665908 | 0 | 110984.6667 |  |  | 0 | na
| 1006 | Receive, Inspect, Inventory | [12 empty] | 0 | 0 | 6492 | 6492 |  |  | 30000 | -30000
| 1007 | Storage | [12 empty] | 0 | 0 | 5023 | 5023 |  |  | 20000 | -20000
| 1008 | Local Registrations Fees, License, Etc. | [12 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1009 | Transport of Damaged Goods for Repair | [12 empty] | 0 | 0 | 1800 | 1800 |  |  | 50000 | -50000
[7 empty] | 3364000 |  | 2938000 |  | 787000 |  | 83000 |  | 7172000 | 1060554 | 1900912 | 2077671 |  |  | 7336623.5294 | -364623.5294
| 1100 Site Costs | [5 empty] | 329000 |  | 74000 |  | 106000 |  | 0 |  | 509000 | 591400 | 1530850 | 1629416.6667 |  |  | 3000000 | -2891000
[7 empty] | 329000 |  | 74000 |  | 106000 |  | 0 |  | 509000 | 591400 | 1530850 | 1629416.6667 |  |  | 3000000 | -2891000
|  |  |  | Engineering & PM | [14 empty] | Engineering & PM
| 1200 Engineering |  |  | 3921000 | 7.7% | [13 empty] | 1482322.8333 | 9.136%
| 1290 | Engineering Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 13835 | 13835 | 37.8% |  | 40691.1765 | -40691.1765
| 1201 | EPC Eng Labor |  |  |  |  | 615000 |  | 450000 |  | 120000 |  | 50000 |  | 1235000 | 0 | 903119 | 903119 |  |  | 1500000 | -265000
| 1202 | Local Eng |  |  |  |  | 225000 |  | 60000 |  | 0 |  | 0 |  | 285000 | 47945 | 0 | 7990.8333 |  |  | 0 | na
[7 empty] | 840000 |  | 510000 |  | 120000 |  | 50000 |  | 1520000 | 47945 | 916954 | 924944.8333 |  |  | 1540691.1765 | -305691.1765
1300 Project Management
| 1390 | ProEnergy Labor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 324879 | 324879 |  |  | 955526.4706 | -955526.4706
|  | Subcontractor |  |  |  |  | incl below |  | incl below |  | incl below |  | incl below |  | incl below | 0 | 89837 | 89837 |  |  | 264226.4706 | -264226.4706
| 1310 | Project & Construction |  |  |  |  | 1282000 |  | 625000 |  | 160000 |  | 0 |  | 2067000 | 0 | 135053 | 135053 |  |  | 600000 | 1467000
| 1320 | Inspectors |  |  |  |  | 276000 |  | 0 |  | 58000 |  | 0 |  | 334000 | 45654 | 0 | 7609 |  |  | 0 | na
[7 empty] | 1558000 |  | 625000 |  | 218000 |  | 0 |  | 2401000 | 45654 | 549769 | 557378 |  |  | 1819752.9412 | 247247.0588
| 1400 Travel & Perdiem | [5 empty] | 916000 |  | 211000 |  | 127000 |  | 0 |  | 1254000 | 887445 | 54648 | 202555.5 |  |  | 160729.4118 | -160729.4118
| 1410 |  | Project Meal Expense |  |  |  | 25000 |  | 0 |  | 0 |  | 0 |  | 25000 | 0 | 0 | 0 |  |  | 0 | na
[7 empty] | 941000 |  | 211000 |  | 127000 |  | 0 |  | 1279000 | 887445 | 54648 | 202555.5 |  |  | 160729.4118 | -160729.4118
1500 Technical Reps
| 1501 | GTG Tech Rep |  |  |  |  | 450000 |  | 225000 |  | 0 |  | 0 |  | 675000 | 0 | 0 | 0 |  |  | 300000 | 375000
| 1502 | Fire Water |  |  |  |  | 30000 |  | 0 |  | 0 |  | 0 |  | 30000 | 0 | 0 | 0 |  |  | 30000 | 0
| 1503 | Gas Compressor |  |  |  |  | 0 |  | 0 |  | 60000 |  | 0 |  | 60000 | 0 | 0 | 0 |  |  | 60000 | 0
| 1504 | Chiller |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1505 | Water Treatment |  |  |  |  | 60000 |  | 60000 |  | 0 |  | 0 |  | 120000 | 0 | 0 | 0 |  |  | 120000 | 0
| 1506 | Commission / S/U / Trng |  |  |  |  | 240000 |  | 0 |  | 0 |  | 0 |  | 240000 | 0 | 12282 | 12282 |  |  | 120000 | 120000
| 1507 | Controls Rep |  |  |  |  | 180000 |  | 0 |  | 0 |  | 0 |  | 180000 | 0 | 2454 | 2454 |  |  | 90000 | 90000
| 1508 | Evap Cooler |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1509 | SCR | [12 empty] | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 1510 | Black Start Generator | [10 empty] | 30000 |  | 30000 | 0 | 0 | 0 |  |  | 30000 | 0
[7 empty] | 960000 |  | 285000 |  | 60000 |  | 30000 |  | 1335000 | 0 | 14736 | 14736 |  |  | 720000 | 585000
1600 Project Tests
| 1601 | Soil Boring / Compaction |  |  |  |  | 15000 |  | 0 |  | 10000 |  | 1000 |  | 26000 | 0 | 0 | 0 |  |  | 0 | na
| 1602 | Concrete |  |  |  |  | 50000 |  | 15000 |  | 15000 |  | 2000 |  | 82000 | 0 | 0 | 0 |  |  | 0 | na
| 1603 | X Ray |  |  |  |  | 50000 |  | 15000 |  | 15000 |  | 1000 |  | 81000 | 0 | 0 | 0 |  |  | 0 | na
| 1604 | Plant Performance and Reliability |  |  |  |  | 100000 |  | 0 |  | 0 |  | 0 |  | 100000 | 0 | 0 | 0 |  |  | 0 | na
| 1605 | Emission Tests |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | na
| 1606 | Protective Relays |  |  |  |  | 20000 |  | 10000 |  | 0 |  | 0 |  | 30000 | 0 | 0 | 0 |  |  | 0 | na
| 1607 | Acoustics / Noise Test |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | na
[7 empty] | 235000 |  | 40000 |  | 40000 |  | 4000 |  | 319000 | 0 | 0 | 0 |  |  | 0 | 0
| 1700 Legal | [5 empty] | 30000 |  | 0 |  | 0 |  | 0 |  | 30000 | 340716 | 0 | 56786 |  |  | 0 | na
[7 empty] | 30000 |  | 0 |  | 0 |  | 0 |  | 30000 | 340716 | 0 | 56786 |  |  | 0 | na
1800 Insurance / Securities
| 1810 | Bonds |  |  |  |  | 300000 |  | 190000 |  | 0 |  | 0 |  | 490000 | 0 | 0 | 0 |  |  | 0 | 490000
| 1820 | Buildiers All Risk |  |  |  |  | 300000 |  | 190000 |  | 0 |  | 0 |  | 490000 | 0 | 0 | 0 |  |  | 0 | 490000
| 1830 | Marine / Cargo |  |  |  |  | 300000 |  | 190000 |  | 0 |  | 0 |  | 490000 | 0 | 0 | 0 |  |  | 0 | 490000
| 1840 | Professional |  |  |  |  | 75000 |  | 45000 |  | 0 |  | 0 |  | 120000 | 17640 | 0 | 2940 |  |  | 0 | na
[7 empty] | 975000 |  | 615000 |  | 0 |  | 0 |  | 1590000 | 17640 | 0 | 2940 |  |  | 0 | 1470000
| 1900 Taxes | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2000 Commissions | [5 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
[7 empty] | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
2100 Project Contingency / Risk
| 2110 | Project Contingency |  |  |  |  | 400000 |  | 260000 |  | 200000 |  | 30000 |  | 890000 | 0 | 0 | 0 |  |  | 0 | 890000
| 2120 | GT Performance |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2130 | Schedule LD |  |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 |  |  | 0 | 0
| 2140 | Material Escalation |  |  |  |  | 487000 |  | 297000 |  | 88000 |  | 20000 |  | 892000 | 0 | 0 | 0 |  |  | 0 | 892000
| 2150 | Labor Contingency |  |  |  |  | 273000 |  | 173000 |  | 53000 |  | 20000 |  | 519000 | 0 | 0 | 0 |  |  | 0 | 519000
[7 empty] | 1160000 |  | 730000 |  | 341000 |  | 70000 |  | 2301000 | 0 | 0 | 0 |  |  | 0 | 2301000
| Total Budget - Equivalent USD | [5 empty] | 29823000 |  | 16341778 |  | 7795000 |  | 855000 |  | 54814778 | 18789299.9 | 13095691 | 16227243.9833 |  |  | 34917350 | 1188428
| Budget - BsF | [5 empty] | 41684710 |  | 42546516 |  | 22577909 |  | 1861884 |  | 108671019
| BsF Budget - Equiv. USD@6.0 ER | [5 empty] | 6947451.6667 |  | na |  | na |  | na |  | na
| Budget - USD only | [5 empty] | 22875548.3333 |  | 8976778 |  | 5392000 |  | 667000 |  | 37911326.3333
| Construction % Complete = |  |  |  | 34%
| Forecasted BsF Cost at Completion = | [5 empty] | 55262646.7647 |  | USE ======> |  | 90000000
| Forecasted BsF Cost Below / (Above) Budget = | [5 empty] | 53408372.2353
| Project Fin % Compl. |  |  | 31.86% | 41.92% |  | <====use
E=55%;P=45%;C=34%
| Forecasted USD Only Cost at Completion = | [5 empty] | 34917350
| Forecasted USD Only Cost Below / (Above) Budget = | [7 empty] | 2993976.3333
| Estimated Revenue as of 01 May 2010 | [5 empty] | 12719181 | + | 1816653 |  | BsF
[6 empty] | = | 13021956.5 |  | Equiv. USD
| Estimated Cost of Money APR | [5 empty] | 6% |  | Note: 15,661,077 BsF invoiced but not paid as of 12 July 2010
| Estimated Cost of Money APR weekly rate | [5 empty] | 0.1154%
| Minimum Cash Position Since 03 Aug 2010 | [5 empty] | 9890406.5167
| Estimated Value of Cash Position Since 01 May | [5 empty] | 41126.569
| Estimated USD Only Budget Surplus + Cash Position Value = | [7 empty] | 3035102.9023