## Recap
ProEnergy EPC
Job Description: |  |  | "Cost Estimate for adding gas compression Guarenas"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  |  | 2010-06-12
I. Balance of Plant
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 14.8148 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 20.7407 | calc
|  | 103 | Concrete Foundations |  |  | 4452.5463 | 756.9329 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 0 | calc
|  | 106 | Gravel - Sand |  |  |  | 7.5315 | calc
|  | 107 | Structual Steel |  |  |  | 35 | calc
|  | 108 | Fencing |  |  |  | 0 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 835.0199 |  | 835.0199
| 200 Buildings | [5 empty] | 252 | calc | 252
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 195 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 10800 |  | calc
|  | 330 | Mechanical Subcontractor |  |  | 2620 | 152.5144 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 320 | calc
[7 empty] | 667.5144 |  | 667.5144
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 800 | calc
|  | 420 | Substation Equipment |  |  |  | 0 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 4880 | 284.0726 | calc
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 290 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 7200 | 419.1235 | calc
[7 empty] | 1793.1961 |  | 1793.1961
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 75 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 1200 | 69.8539 | calc
[7 empty] | 144.8539 |  | 144.8539
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 80 | calc
|  | 620 | Telephone System |  |  |  | 0 | calc
|  | 630 | Public Address System |  |  |  | 0 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 80 |  | 80
700 Plant Erection
|  | 700 | Plant Erection |  |  | 2400 | 139.7078 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 29100 | 139.7078 |  | 139.7078
| 800 Equipment Rental | [5 empty] | 32 | calc | 32
| 900 Painting | [5 empty] | 25 | calc | 25
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 187.4 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 250 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 200 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 637.4 |  | 637.4
| 1100 Site Costs | [5 empty] | 105.55 | calc | 105.55
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 120 | calc
|  | 1202 | Local Eng |  |  |  | 0 | calc
[7 empty] | 120 |  | 120
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 160 | calc
|  | 1320 | Inspectors |  |  |  | 57.5 | calc
[7 empty] | 217.5 |  | 217.5
| 1400 Travel & Perdiem | [5 empty] | 126.75 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 126.75 |  | 126.75
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 0 | 2500 | 0 | plgd /1000
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 45 | 2200 | 99 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 0 | 2000 | 0 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 0 | 2000 | 0 | plgd /1000
|  | 1507 | Controls Rep |  | 0 | 3000 | 0 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 99 |  | 99
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 10 | plgd /1000
|  | 1602 | Concrete |  |  |  | 15 | plgd /1000
|  | 1603 | X Ray |  |  |  | 15 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 0 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 0 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 40 |  | 40
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 0 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 0 |  | 0
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 150 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 1760 | 88 | calc
|  | 2150 | Labor Contingency |  | 5% | 1065.2722 | 53.2636 | calc
[7 empty] | 291.2636 |  | 291.2636
[5 empty] | BOP Cost |  |  |  | 5606.7557
[5 empty] | % Markup |  |  | 40% | 2242.7023
[5 empty] | BOP Sales Price |  |  |  | 7849.458
Note The price does not include the following:
1.0 Taxes or Imprort Duties
II. | Gas Compressors
| 1 | LM 600 Gas Compressors |  |  | 3 | 550 | 1650
| 2 | LM 2500 Gas Compressors |  |  | 2 | 400 | 800
2450
|  |  |  | Mark Up |  | 25% | 612.5
|  |  |  | Compression Price |  |  | 3062.5 |  | 3062.5
|  |  |  | Total Compression Plant Price |  |  |  |  | 10911.958

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | Guarenas Gas Compression | [5 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [5 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [5 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Clearing/Grubbing |  |  | 200 | 80 | 1 | 16000 | 592.5926 | 25 | 14814.8148
2
3 | Demolition
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Containment Systems
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
14.8148

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | Guarenas Gas Compression | [6 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [6 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 140 | 80 | 2 | 22400 | 829.6296 | 25 | 20740.7407
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | O/W Sep and Oil tank |  |  |  | 0 | 20 | 15 | 0 | 0 | 30 | 0
8 | GAS Turbine Hall |  |  |  | 0 | 130 | 1 | 0 | 0 | 18 | 0
9 | Liquid Fuel Under ground tank |  |  |  | 0 | 50 | 18 | 0 | 0 | 30 | 0
10
11 | Main Plant Area |  |  |  | 0 | 250 | 1 | 0 | 0 | 30 | 0
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 20.7407

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Guarenas Gas Compression | [7 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [7 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5 | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy | E=Est
1 | POWER ISLAND |  |  | Price: 850
2 | GT Generators LM 2500+ |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
| GT Generator LM 6000 |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
3 | Exhaust Stack |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
4 | HRSG |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
5 | SCR |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
6 | STG |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
7 | STG Cooling Tower |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
8 | STG Inlet Chillers |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
9 | Gen LO Pump Skid |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
10 | Aux Skid(s) for GTG |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
17 | Fin Fan L O Coolers |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
18 | Gas Compressors |  |  | 5 | 35 | 15 | 4 | 10500 | 388.8889 | 850 | 330555.5556 | 1944.4444
19 | Fuel Gas Plant Metering Skid |  |  | 0 |  |  |  | 0 | 0 | 850 | 0 | 0
20 | Comp Fin Fans |  |  | 5 | 15 | 15 | 1 | 1125 | 41.6667 | 850 | 35416.6667 | 208.3333
21 | Waste Oil/Water Storage Tank |  |  | 0 |  |  |  | 0 | 0 | 850 | 0 | 0
22 | Oily Water Separator |  |  | 0 |  |  |  | 0 | 0 | 850 | 0 | 0
23 | Lubricant Storage Area |  |  | 0 |  |  |  | 0 | 0 | 850 | 0 | 0
24 | Instrument Air Comp Skid |  |  | 0 |  |  |  | 0 | 0 | 850 | 0 | 0
25 | Pipe Rack Stanchons |  |  | 15 | 2.5 | 2.5 | 5 | 468.75 | 17.3611 | 850 | 14756.9444 | 86.8056
26 | 15KV Cable Tray Stanchons |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
27 | Fire Water Pump Skid |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
28 | Area Light Poles |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
29 | Aux Trans fndns |  |  | 2 | 10 | 15 | 1.5 | 450 | 16.6667 | 850 | 14166.6667 | 83.3333
30 | Cable Trenches see est |  |  | 1 | 300 | 15 | 1 | 4500 | 166.6667 | 850 | 141666.6667 | 833.3333
31 | Water Treatment Plant |  |  | Cubic: 0; Price: 850; Total: 0 | 0
32 | Condenser Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
33 | Deaerator Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
34 | BFW Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
35 | Demin Water Pump skid |  |  | Cubic: 0; Price: 850; Total: 0 | 0
36 | Demin Stg Tanks _200 M_ Gal |  |  | Cubic: 0; Price: 850; Total: 0 | 0
37 | Demin Forwarding Pumps |  |  | Cubic: 0; Price: 850; Total: 0 | 0
38 | Chemical Injection Skid |  |  | Cubic: 0; Price: 850; Total: 0 | 0
39 | Raw Water Tank Base |  |  | Cubic: 0; Price: 850; Total: 0 | 0
40 | Fire Water Tank base |  |  | Cubic: 0; Price: 850; Total: 0 | 0
41 | Emer Generator Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
42
43 | BUILDINGS
44 | Control Bldg/Office |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
45 | Warehouse/Maintenance |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
46 | Water Treatment Bldg |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
47 | Gas Compressor Shed |  |  | 1 | 140 | 50 | 1 | 7000 | 259.2593 | 850 | 220370.3704 | 1296.2963
48 | DFO Treatment Shed |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
49 | Pwr Blk Utility Bldg's |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
50 | Substation Bldg |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
51 | Gas Turbine Hall |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
52 | Liquid Fuel Unloading |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
53 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
54 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
55
56 | SUBSTATION
57 | GSU Transformer |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
58 | (___)KV SF6 Circuit Breaker |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
59 | (___)KV Disc Switch w/ Stand |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
60 | Dead End Tower |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
61 | Transmission Line Poles |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
62 | Insulator Support Base |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
63 | PT Support Base |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
64 | Static Pole Base |  |  | Cubic: 0; Cubic: 0; Price: 850; Total: 0 | 0
65
66
67 |  |  | Total Cost of Foundations | Cubic: 890.5093; Total: 756.9329 | 4452.5463
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | Guarenas Gas Compression | [7 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description | [7 empty] | Cu | Price | Total | Q=Quote
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price | E=Est
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls |  | Total Price: 0

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | Guarenas Gas Compression | [7 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price | E=Est
1
2 | Compression Area |  |  | 1 | 140 | 50 | 0.5 | 3500 | 129.6296 | 215.1852 | 35 | 7531.4815
3
4 | Cooling Tower Area |  |  | Cubic: 0; Cubic: 0; Tons: 0; Price: 35; Total: 0
5
6 | Substation |  |  | Cubic: 0; Cubic: 0; Tons: 0; Price: 35; Total: 0
7
8 | Road ways |  |  | Cubic: 0; Cubic: 0; Tons: 0; Price: 35; Total: 0
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | Total: 7.5315

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Guarenas Gas Compression | [5 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | # of | Qty | Price | Total | Q=Quote
No. | [5 empty] | Lbs / Tons |  |  | Price | E=Est
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 10 | 2000 | 20000
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [7 empty] | 0
6 | [8 empty] | 0
7 | GTG walkways and stairs | [7 empty] | 0
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [7 empty] | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [7 empty] | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 15000 | 15000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 35

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Guarenas Gas Compression | [5 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price | E=Est
1 | Office/Control/Warehouse | [7 empty] | 0
2 | Water Treatment | [7 empty] | 0
3 | Gas Compr Shed |  |  |  | 140 | 45 | 6300 | 40 | 252000
4 | DFO Treatment Shed | [7 empty] | 0
5 |  |  |  |  | 0 |  | 0 |  | 0
6 |  |  |  |  | 0 |  | 0 |  | 0
7 |  |  |  |  | 0 |  | 0 |  | 0
8 |  |  |  |  | 0 | 0 | 0 | 0 | 0
9 |  |  |  |  | 0 | 0 | 0 | 0 | 0
10 |  |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House | [7 empty] | 0
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 252

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | Guarenas Gas Compression | [9 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [9 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [9 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
[15 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
| GTG |  |  | Unit: 3%; Hours: 10
1 | GTG Type 2ea GE LM 2500 + 1ea LM 6000 |  |  |  |  | 0 | 0 | 0 | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
2 | Lube oils and Chemicals |  |  |  |  | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
3 | Exhaust Stack |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | Project Grouting |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | GTG Tools |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | Anchor Bolts |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
31 | Inlet Evap Cooling System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 18 | 0 | 58.2116 | 0 |  | E
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
33 | Cooling Water Circulation Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 5 | 0 | 0 | 25000 | 125000 | 10 | 4 | 6 | 1200 | 58.2116 | 69853.914 |  | E
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 1 | 175000 | 175000 | 5250 | 5250 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
40 | Fuel Gas Turbine Metering Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 0 | 125000 | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
42 | ESD Valve, ___" ___# |  |  | 1 | 20000 | 20000 | 600 | 600 | 10 | 2 | 1 | 20 | 58.2116 | 1164.2319 |  | E
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  |  |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
46 | Metering Skid |  |  |  |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
47 | Forwarding Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
48 | Transfer Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
49 | Fuel Heating |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
50 | Filter Skids |  |  |  |  | 0 |  | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
51 | Centrifuge |  |  |  |  | 0 |  | 0 | 10 | 4 | 8 | 0 | 58.2116 | 0 |  | E
52 | Injection Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
53 | Storage Tank 500000 gal |  |  |  |  | 0 |  | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
54 | Day Tank 200000 gal |  |  |  |  | 0 |  | 0 | 10 | 4 | 6 | 0 | 58.2116 | 0 |  | E
55
56 | Water Supply System
57 | Raw/Fire Water Storage Tank 450 M gal | [5 empty] | 0 | 0 | 10 | 4 | 6 | 0 | 58.2116 | 0 |  | E
58 | Raw Water Supply Pumps | [5 empty] | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
59 | Raw Water Forwarding Pumps | [5 empty] | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
64 | Demin Treatment System 115 M gal/day |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 8 | 0 | 58.2116 | 0 |  | E
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
66 | Demin water fiberglass tank |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
67 | Demin forwarding pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
68 | Demin Filter Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
69 | Demin Water Tank, SS 200M gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
73 | Oily Waste Tank 10000 gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
74 | Waste Water Tank 10000 gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
79 | Fire Water Foam System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
80 | [15 empty] | E
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
89 | Anti-Icing Ducting |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
90 | Sanitary Sewer |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
91 |  |  |  | Hours: 10
92
93 |  |  | Total Cost | Total: 195; Frt: 130.85; Qty: 1310
94 |  |  |  | Total: 76.2572
[9 empty] | Total Manhours |  |  | 1310
[9 empty] | Times Prod Factor |  | 2 | 2620 | 58.2116 | 152.5144
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 320000 | 320000 | 9600 | 9600 | 10 | 6 | 90 | 5400 | 58.2116 | 314342.613 |  | E
96 |  |  | Total Cost | Total: 320; Frt: 9.6; Qty: 5400; Total: 314342.613
97
98 |  |  |  | Hours: Total Manhours; Qty: 5400
99 |  |  |  | Hours: Times Prod Factor; Qty: 2; Qty: 10800; Rate: 58.2116
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 27
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 9.45
40.45
[8 empty] | Contr G&A 8% |  | 3.236
[8 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[7 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | Guarenas Gas Compression | [11 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [11 empty] | Quote No: |  | T 1009 - B
Location: |  | Guatire, Venn | [11 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | Power Island Equipment | [7 empty] | 3% |  | 10
2 | Gas Turbine Generator LM 2500 & LM 6000 |  |  |  |  | 0 |  |  | 0 |  | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | STG Cooling Tower |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7 | Chiller Package |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
8 | Water Treatment Package |  |  |  |  | 0 |  |  | 0 |  | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
9 | [13 empty] | 0 | 58.2116 | 0
10 | 15KV | [13 empty] | 58.2116
11 | Generator Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
12 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
13 | Aux Breakers |  |  |  |  | 6 | 60000 | 360000 | 750 | 4500 | 10 | 3 | 3 | 540 | 58.2116 | 31434.2613 |  | E
14 | Bus Duct |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
17 | 5KV | [13 empty] | 58.2116
18 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
19 | Fused Disconnect(s) |  |  |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0 |  | E
20 | MCC's |  |  |  |  | 5 | 25000 | 125000 | 3750 | 18750 | 10 | 3 | 3 | 450 | 58.2116 | 26195.2177 |  | E
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0
23 | 600V | [13 empty] | 58.2116
24 | Distribution Panel Add'n |  |  |  |  | 1 | 85000 | 85000 | 2550 | 2550 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
25 | GTG MCC(s) LM 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
| LM 2500 Plus MCCs |  |  |  |  | 0 | 0 | 0 | 0 |  | 10 | 2 | 5 | 0 | 58.2116 | 0
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
28 | BOP MCC for Compression |  |  |  |  | 1 | 25000 | 25000 | 1500 | 1500 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
29 | Water Treatment MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0
32 | Aux Transformer(s) | [13 empty] | 58.2116
33 | 15/5KV ____5___ MVA |  |  |  |  | 1 | 95000 | 95000 | 5000 | 5000 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
34 | 15/600V _750_ KVA |  |  |  |  | 1 | 55000 | 55000 | 2500 | 2500 | 10 | 3 | 5 | 150 | 58.2116 | 8731.7393 |  | E
35 | 600/120/208V ________ KVA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
38 | Area Lighting | [13 empty] | 58.2116
39 | Poles _______ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
40 | Floodlights _______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.5 | 0 | 58.2116 | 0 |  | E
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 58.2116 | 0
43 | Other Systems | [13 empty] | 58.2116
44 | UPS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
45 | DC |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
46 | Cathodic Protection |  |  |  |  | 3 | 10000 | 30000 | 900 | 2700 | 10 | 2 | 5 | 300 | 58.2116 | 17463.4785 |  | E
47 | Lightning Protection |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
48 | [11 empty] | 0 | 0 | 0 | 58.2116 | 0
49 | [14 empty] | 58.2116
50 | Temporary Electric |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 2 | 35 | 700 | 58.2116 | 40748.1165 |  | E
51 | Electrical Control Module LM 2500+ |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
52 | Electrical Control Module LM 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 800 |  | 38.25 |  |  |  | 2440 |  | 142.0363
[12 empty] | Productivity | 2 | 4880 | 58.2116 | 284.0726
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 290000 | 290000 | 8700 | 8700 | 10 | 6 | 60 | 3600 | 58.2116 | 209561.742 |  | E
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 290 |  | 8.7 |  |  |  | 3600 |  | 209.5617
58 | [10 empty] | Total Manhours |  |  | 3600
59 | [10 empty] | Times Prod Factor |  | 2 | 7200 | 58.2116 | 419.1235
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 27
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 9.45
40.45
[13 empty] | Contr G&A 8% |  | 3.236
[13 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[12 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N88: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q80: Insert Rate Here:

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Guarenas Gas Compression | [8 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [8 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [8 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
[13 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 |  |  |  | Hours: 10
2 | Instrumentation for GTG |  |  | 0 | 0 | 0 | 10 | 2 | 10 | 0 | 58.2116 | 0 |  | E
3 |  |  |  | Hours: 10; Rate: 58.2116; Total: 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
5 |  |  |  | Hours: 10; Rate: 58.2116
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
7 |  |  |  | Hours: 10; Rate: 58.2116
8 | Instrumentation for Injection Water Treatment |  |  | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0 |  | E
9 |  |  |  | Hours: 10; Rate: 58.2116
10 | Instrumentation for DFO Centrifuges |  |  | 0 | 0 | 0 | 10 | 2 | 10 | 0 | 58.2116 | 0 |  | E
11 |  |  |  | Hours: 10; Rate: 58.2116
12 | Instrumentation for gas compressors |  |  | 5 | 15000 | 75000 | 10 | 4 | 3 | 600 | 58.2116 | 34926.957 |  | E
13 |  |  |  | Hours: 10; Rate: 58.2116
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
15 |  |  |  | Hours: 10; Rate: 58.2116
16 |  |  |  | Hours: 10; Rate: 58.2116
17 |  |  |  | Hours: 10; Rate: 58.2116
18 |  |  |  | Hours: 10; Rate: 58.2116
19 |  |  |  | Hours: 10; Rate: 58.2116
20 |  |  |  | Hours: 10; Rate: 58.2116
21 |  |  |  | Hours: 10; Rate: 58.2116
22 |  |  |  | Hours: 10; Rate: 58.2116
23 |  |  | Total Cost of Plant Instrumentation | Total: 75; Qty: 600; Total: 34.927
[8 empty] | Total Hours |  | 600
[8 empty] | Prod Factor | 2 | 1200 | 58.2116 | 69.8539
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 27
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 9.45
40.45
[9 empty] | Contr G&A 8% |  | 3.236
[9 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[8 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [6 empty] | Cost | Cost | E=Est
1
2 | DCS Hardware / Software add'n |  |  |  |  | 1 | 50000 | 50000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 1 | 15000 | 15000
5
6 | Documentation |  |  |  |  | 1 | 15000 | 15000
7
8 |  |  |  |  | Total DCS |  |  | 80
9
10 | PBX Communications System |  |  |  |  | 0 | 0 | 0
11
12 | Loud Speaker System |  |  |  |  | 0 | 0 | 0
13
14 | TV / Security System |  |  |  |  | 0 | 0 | 0
15
16
17
[7 empty] | taxable | 65000

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Guarenas Gas Compression | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est
1 |  |  |  |  | 10
2 | GTG Erection |  |  | 0 | 10 | 12 | 30 | 0 | 58.2116 | 0 | E
3 |  |  |  |  | 10 |  |  |  | 58.2116
4 | HRSG Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
5 |  |  |  |  | 10 |  |  |  | 58.2116
6 | SCR Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
7 |  |  |  |  | 10 |  |  |  | 58.2116
8 | Water Treatment and FW Systems |  |  | 0 | 10 | 4 | 8 | 0 | 58.2116 | 0 | E
9 |  |  |  |  | 10 |  |  |  | 58.2116
10 | DFO Treatment System |  |  | 0 | 10 | 4 | 10 | 0 | 58.2116 | 0 | E
11 |  |  |  |  | 10 |  |  |  | 58.2116
12 | BOP Equip Erection |  |  | 0 | 10 | 6 | 10 | 0 | 58.2116 | 0 | E
13 |  |  |  |  | 10 |  |  |  | 58.2116
14 | Gas Compressor Erection |  |  | 5 | 10 | 6 | 4 | 1200 | 58.2116 | 69853.914 | E
15 |  |  |  |  | 10 |  |  |  | 58.2116
16 | Evap Cooling Erection |  |  | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 | E
17 |  |  |  |  | 10 |  |  |  | 58.2116
18 | Fire Water Pump Skid |  |  | 0 | 10 | 4 | 3 | 0 | 58.2116 | 0 | E
19 |  |  |  |  | 10 |  |  |  | 58.2116
20 | STG Erection |  |  | 0 | 10 | 12 | 36 | 0 | 58.2116 | 0 | E
21 |  |  |  |  | 10 |  |  |  | 58.2116
22 | STG Cooling Tower |  |  | 0 | 10 | 8 | 8 | 0 | 58.2116 | 0 | E
23 |  |  |  |  | 10 |  |  |  | 58.2116
24 |  |  |  |  | 10 |  |  |  | 58.2116
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 1200 |  | 69.8539
[6 empty] | Total Hours |  | 1200
[6 empty] | Prod Factor | 2 | 2400 | 58.2116 | 139.7078
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 27
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 9.45
40.45
[7 empty] | Contr G&A 8% |  | 3.236
[7 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[6 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Guarenas Gas Compression | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total | Q=Quote
No. | [5 empty] | Units | Unit | Days | Per Day | Cost | E=Est
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 10000 | 0
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3800 | 0
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 100 | 0
8 | 1 ea Man Lift |  |  |  |  | 0 | 0 | 0 | 80 | 0
9 | 2 ea Welders |  |  |  |  | 0 | 0 | 0 | 60 | 0
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 5 | 4 | 20 | 1500 | 30000
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
51 | 2 ea Fork Lifts |  |  |  |  | 1 | 20 | 20 | 100 | 2000
52 | Welders |  |  |  |  | 0 | 0 | 0 | 70 | 0
53 | 2 ea Pick ups |  |  |  |  | 0 | 0 | 0 | 30 | 0
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 0 | 0 | 0 | 70 | 0
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
60 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 40 |  | 32

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Paint for GTG |  |  |  |  | 0 | 45000 | 0 | E
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0 | E
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0 | E
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 0 | 40000 | 0 | E
9
10 | Paint for BOP Equipment |  |  |  |  | 0 | 50000 | 0 | E
11
12 | Paint for Gas Compressor |  |  |  |  | 1 | 25000 | 25000 | E
13
14 | Paint for Water Treatment |  |  |  |  | 0 | 15000 | 0 | E
15
16 | Paint for DFO Treatment |  |  |  |  | 0 | 15000 | 0 | E
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0 | E
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 25

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 130.85 | 130.85 | E
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 38.25 | 38.25 | E
5
6 | Transportation Substation Equip |  |  |  |  | 0 | 0 | 0 | E
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 9.6 | 9.6 | E
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 8.7 | 8.7 | E
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 187.4

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | Guarenas Gas Compression | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - B
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total | Q=Quote
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost | E=Est
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 1 | 3 | 2000 | 6000 |  | E
3 | Porta Potties |  |  |  |  | 1 | 3 | 350 | 1050 |  | E
4 | Water and Ice |  |  |  |  | 2 | 3 | 250 | 1500 |  | E
5 | Fed X |  |  |  |  | 1 | 3 | 500 | 1500 |  | E
6 | Telephone |  |  |  |  | 1 | 3 | 2500 | 7500 |  | E
7 | Office Supplies |  |  |  |  | 1 | 3 | 1000 | 3000 |  | E
8 | [6 empty] | 0
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 2 | 3500 | 7000 |  | E
10 | Misc Items |  |  |  |  | 1 | 2 | 1500 | 3000 |  | E
11 |  |  | Total Monthly Cost | [5 empty] | 30550
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 30550 |  | 30550
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 50000 | E
21 | Cad Station | [8 empty] | 0 | E
22 | Computers | [8 empty] | 5000 | E
23 | Telephone System and Satalite Dish | [8 empty] | 0 | E
24 | Plotter | [8 empty] | 0 | E
25 | Fax Machine and Printers | [8 empty] | 0 | E
26 | Misc equip | [8 empty] | 20000 | E
27 | Signs | [8 empty] | 0 | E
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 105.55

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Conceptual Engineering |  |  |  |  | 0 | 0 | 0 | E
3
4 | Detailed Engineering per GTG |  |  |  |  | 0 | 0 | 0
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 1 | 75000 | 75000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 0 | 0 | 0
13
14 | Detailed Engineering for civil/structural/bldg |  |  |  |  | 1 | 45000 | 45000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 120

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | No. | Cost | Total | Q=Quote
No. | [5 empty] | Mos | Per Mo | Cost | E=Est
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 2 | 16000 | 32000 | E
2 | Admin Mgr Months on Project |  |  |  |  | 0 | 8000 | 0 | E
3 | Scheduler |  |  |  |  | 0 | 8000 | 0 | E
4 | Purchasing Agent |  |  |  |  | 0 | 8000 | 0 | E
5 | Expediter |  |  |  |  | 0 | 5000 | 0 | E
6 | Home Office Logistic Coordinator |  |  |  |  | 0 | 9000 | 0 | E
7
8
9 | [6 empty] | 32000 |  | E
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 0 | 4000 | 0 | E
18 | Construction Mngr |  |  |  |  | 3 | 16000 | 48000 | E
19 | Contract Cost Admin |  |  |  |  | 0 | 12000 | 0 | E
20 | Scheduler |  |  |  |  | 0 | 10000 | 0 | E
21 | Mechanical Supervisor |  |  |  |  | 2 | 20000 | 40000 | E
22 | Electrical Supervisor |  |  |  |  | 2 | 20000 | 40000 | E
23 | Civil Supervisor |  |  |  |  | 0 | 20000 | 0 | E
24 | Clerks |  |  |  |  | 0 | 5000 | 0 | E
25 | Warehousemen |  |  |  |  | 0 | 5000 | 0 | E
26 | Draftsman |  |  |  |  | 0 | 7000 | 0 | E
27 | Security |  |  |  |  | 0 | 15000 | 0 | E
28 | Safety |  |  |  |  | 0 | 20000 | 0 | E
29 | QA/QC Mngr |  |  |  |  | 0 | 20000 | 0 | E
30
31
32 | [6 empty] | 128000 |  | E
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 0 | 12000 | 0 | E
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0 | E
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 160
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
47 | Mechanical __ ea ___ mos |  |  |  |  | 3 | 11500 | 34500
48 | Electrical __ ea ___ mos |  |  |  |  | 2 | 11500 | 23000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 0 | 11500 | 0
50
51 |  |  |  |  | Total Inspectors |  |  | 57.5
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | Guarenas Gas Compression |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - B
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | No. | Cost | Total |  | Q=Quote
No. | [5 empty] | Units | Per Unit | Cost |  | E=Est
1
2 | Project & Construciton Management
3 | R T Air Fares (6 traveling regularly) |  |  |  |  | 8 | 3000 | 24000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 12 | 5000 | 60000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 0 | 5000 | 0
6 | Misc expenditures |  |  |  |  | 1 | 20000 | 20000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 350 | 65 | 22750
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 0 | 0 | 0 |  | E
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 0 | 0 | 0 |  | E
16 | Auto Rental for Eng Days at Site |  |  |  |  | 0 | 0 | 0 |  | E
17 | Misc Travel Expentitures |  |  |  |  | 0 | 0 | 0 |  | E
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 126.75
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 0 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 0 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36