Note: The Owner has purchased one (1) additional dual fueled GE LM 6000 PC Sprint Gas Turbine Generator package with associated facilities for this project.  The unit and associated equipment are identified in the Table Below:

- Gas Turbine Generator Sets Scope of Supply

  - LM 6000 PC Gas Turbine Generator

Owner will supply One (1) dual fueled GE LM 6000 PC Sprint gas turbine generator set including the following scope of supply:

- LM 6000 Duel fuel engine with water injection for NOx control

- Water injection for Sprint Performance

- Duel ventilation fans

- Electric hydraulic start skid

- Generator Lube Oil skid

- Liquid fuel pressurization skid

- Water injection pressurization pump skid

- Lube oil cooler/exchanger

- Free standing GTG Control Panel.  Note:  Contractor will supply modular control Building w/MCC, Batteries and Chargers.

Contractor will provide Turnkey EPC Services to purchase and install (1) the required Balance of Plant identified below and (2) to install Owner’s provided equipment described above.

2.2 Scope of Supply and Detailed Division of Responsibility

| Material/Responsibility | Qty | Description |  |
| --- | --- | --- | --- |
| Owner: |  |  |  |
|  | 1 Lot | Natural Gas at Gas Compression Header |  |
|  | 1 Lot | Natural Gas for commissioning / start-up |  |
|  | 1 Lot | Liquid Fuel for Commissioning / Start-up that meets GE Fuel Specifications |  |
|  | 1 Lot | Treated Water at water treatment plant |  |
|  | 1 Lot | Waste Water and Waste Oil Truck Removal |  |
|  | 1 Lot | Permits for Environmental, Transportation, Building, Operations, etc. to allow plant construction and commercial operations |  |
|  | 1 Lot | Construction & Commissioning Water and 480V three phase power |  |
|  | 1 Lot | Access Roads to site |  |
|  | 1 Lot | Import Duties and Taxes |  |
|  | 1 lot | Right of Way, easements, etc. to allow proposed interconnects as required |  |
| OWNER Provide /CONTRACTOR Install | 1 | New GE LM 6000 PC Sprint (60Hz) Gas Turbine Generator with Associated Equipment |  |
|  | 1 | -Turbine Control Panel |  |
|  | 1 | -Generator Control Panel and Protection Panel |  |
|  | 1 set | - 24 VDC Batteries and Chargers |  |
| OWNER Will Provide |  |  |  |
|  | 1 Lot | Project Site free and clear of rock and ground water |  |
|  | 1 Lot | Industrial Water for Commissioning and Startup |  |
|  | 1 Lot | Diesel Fuel Supply for Commissioning and Startup |  |
|  | 1 Lot | Electrical Back Feed for Commissioning and Startup |  |
|  | 1 Lot | Waste Oil Disposal |  |
|  | 1 Lot | Waste Water Disposal |  |
| Contractor will Provide and Install |  |  |  |
| Civil, Engineering & Construction: | 1 Lot | Design Engineering and Construction Management of Contracted Labor including Safety, QA/QC, Project Schedule Management, Technical management, start-up, commissioning, systems turnover and performance testing. |  |
|  | 1 Lot | Civil earthwork, leveling, foundations, roadways, plant gravel, and paving |  |
| Mechanical: | 1 set | GTG Tools |  |
|  | 1 | LM 6000 GTG Exhaust Stack with Silencer |  |
|  | 1 Lot | Mechanical pipe, valves, and material including installation with contract labor |  |
|  | 1 Lot | Connection to Duplex 185 scfm Plant Service and Instrument Air Compressor |  |
|  | 1 Lot | Connection to 2000 gallon Underground Oily Water Separator System |  |
|  | 1 Lot | Connection to Firewater HDPE underground distribution system with hydrants, monitors, controls and foaming system. |  |
|  | 1 | Raw Water supply pump |  |
|  | 1 | Raw Water Forwarding pump |  |
|  | 1 | LO Cooling Tower |  |
|  | 1 | Demin. Water Forwarding Pump |  |
|  | 1 | DFO Filter Skid |  |
| Electrical |  |  |  |
|  | 1 | 13.8KV 3000 Amp Generator Breaker NEMA 3R |  |
|  | 1 Lot | Electrical wire, conduit, and cable including installation with contract labor |  |
|  | 1 | 13.8 KV Aux Breaker |  |
|  | 1 | 480 V Distribution Panel |  |
|  | 1 | LM 6000 Control Building with 480V MCC, Batteries and Chargers |  |
|  | 1 | BOP 480V MCC |  |
|  | 1 | 480V 750 KVA expansion of existing Aux. Transformer |  |
|  | 1 | 480V/120V/208V Aux Transformers |  |
|  | 2 | Area Lighting Poles each with (2) lights |  |
|  | 1 Lot | Cathodic Protection System |  |
|  | 1 Lot | Lightning Protection |  |
|  | 1 | Plant UPS System |  |
| Instrumentation: |  |  |  |
|  | 1 Lot | Plant Instrumentation- addition |  |
|  | 1 Lot | Interconnect to Plant DCS System |  |
|  | 1 | PBX Communications System - addition |  |
|  | 1 | Loud Speaker System – addition |  |
|  | 1 Lot | Fiber Optic Cables, Fittings & Terminators - expansion |  |