Guarenas-Guatire Project Payment Schedule

Payment Milestones                                                                         US Dollars        Bolivars

| Down Payment Due Upon Signing |  | 35% | 25% |
| --- | --- | --- | --- |
| Milestone 1 |  | 10% | 10% |
| Civil works |  |  |  |
|  | Site Preparation Complete |  |  |
|  | Gas Turbine Foundations Poured for Equipment |  |  |
| Milestone 2 |  | 10% | 15% |
| Gas Turbine 1 Erection Complete |  |  |  |
|  | Assembly of Major Gas Turbine Modules Complete |  |  |
|  | Exhaust Stack Erected |  |  |
| Milestone 3 |  | 10% | 15% |
| Gas Turbine Unit 2 Erection Complete |  |  |  |
|  | Assembly of Major Gas Turbine Modules Complete |  |  |
|  | Exhaust Stacks Erected |  |  |
| Milestone 4 |  | 10% | 10% |
| Mechanical |  |  |  |
|  | Gas Turbine Unit 3 Erection Complete |  |  |
|  | Gas Turbine Auxiliary Equipment Set |  |  |
|  | Interconnect Piping Installed |  |  |
| Electrical |  |  |  |
|  | All Major Electrical Equipment Set and Installed |  |  |
| Milestone 5 |  | 10% | 10% |
| Mechanical |  |  |  |
|  | Water treatment System Installed |  |  |
|  | Interconnect Piping Installed |  |  |
| Electrical Completion |  |  |  |
|  | All Electrical Interconnect Cabling Installed Units 1 & 2 |  |  |
| Precommissioning Complete on Units 1 & 2 |  |  |  |
|  | All Mechanical Equipment Flushed and Checked |  |  |
|  | All Hydrostatic Testing Complete |  |  |
|  | All Pumps Rotated and Tested |  |  |
|  | All Mechanical Systems Ready for Startup |  |  |
|  | All Electrical Equipment Statically Tested |  |  |
|  | All Electrical Systems Ready for Startup |  |  |
| Milestone 6 |  | 5% | 5% |
| Unit 1 & 2 Commissioning and Testing Complete |  |  |  |
|  | Unit 1 & 2 Tested and Ready for Commercial Operation |  |  |
|  | All Mechanical Auxiliary Ready for Commercial Operation |  |  |
|  | All Electrical Auxiliary Equipment Tested and Ready for Commercial Operation |  |  |
| Milestone 7 |  | 5% | 5% |
| Mechanical |  |  |  |
|  | All Plant Fuel and Water Tanks Complete |  |  |
|  | All Plant Fuel and Water Piping Complete |  |  |
| Electrical |  |  |  |
|  | All Electrical Balance of Plant Complete |  |  |
|  | All Plant Interconnect Cabling Complete |  |  |
| Precommissioning Complete on Unit 3 |  |  |  |
|  | All Mechanical Equipment Flushed and Checked |  |  |
|  | All Hydrostatic Testing Complete |  |  |
|  | All Pumps Rotated and Tested |  |  |
|  | All Mechanical Systems Ready for Startup |  |  |
|  | All Electrical Equipment Statically Tested |  |  |
|  | All Electrical Systems Ready for Startup |  |  |
| Milestone 8 |  | 5% | 5% |
| Plant Commissioning and Testing Complete |  |  |  |
|  | GT Unit 3 Ready to be Tested and Ready for Commercial Operation |  |  |
|  | All Mechanical Auxiliary and Balance of Plant Equipment Ready for Commercial Operation |  |  |
|  | All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation |  |  |
|  | All Buildings Finished and Complete |  |  |
|  | All Driveways and Finish Grading Complete |  |  |
| Total |  | 100% | 100% |