## Recap
ProEnergy EPC
Job Description: |  |  | " 2ea LM 2500 Plus & 1ea LM 6000 S.C. Cost Estimate"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  |  | 2010-03-07
I. Balance of Plant
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 236.1111 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 236.1111 | calc
|  | 103 | Concrete Foundations |  |  | 7735.0926 | 1160.2639 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 290.0926 | calc
|  | 106 | Gravel - Sand |  |  |  | 70.5807 | calc
|  | 107 | Structual Steel |  |  |  | 166 | calc
|  | 108 | Fencing |  |  |  | 96.1 | calc
|  | 109 | Architectual Treatment |  |  |  | 50 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 2305.2594 |  | 2305.2594
| 200 Buildings | [5 empty] | 539.875 | calc | 539.875
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 4465 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 27000 |  | calc
|  | 330 | Mechanical Subcontractor |  |  | 19820 | 1153.7538 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 600 | calc
[7 empty] | 6218.7538 |  | 6218.7538
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 1253 | calc
|  | 420 | Substation Equipment |  |  |  | 2240.3 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 21980 | 1279.4909 | calc
|  | 440 | Substation Subcontractor |  |  | 9632 | 560.6941 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 700 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 16200 | 943.0278 | calc
[7 empty] | 6976.5128 |  | 6976.5128
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 110 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 1920 | 111.7663 | calc
[7 empty] | 221.7663 |  | 221.7663
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 345 | calc
|  | 620 | Telephone System |  |  |  | 15 | calc
|  | 630 | Public Address System |  |  |  | 15 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 375 |  | 375
700 Plant Erection
|  | 700 | Plant Erection |  |  | 24160 | 1406.3921 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 120712 | 1406.3921 |  | 1406.3921
| 800 Equipment Rental | [5 empty] | 1048.2 | calc | 1048.2
| 900 Painting | [5 empty] | 340 | calc | 340
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 614.204 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 1800 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 900 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 50 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 3364.204 |  | 3364.204
| 1100 Site Costs | [5 empty] | 328.7 | calc | 328.7
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 615 | calc
|  | 1202 | Local Eng |  |  |  | 225 | calc
[7 empty] | 840 |  | 840
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 1282 | calc
|  | 1320 | Inspectors |  |  |  | 276 | calc
[7 empty] | 1558 |  | 1558
| 1400 Travel & Perdiem | [5 empty] | 916 | calc
|  | 1410 | Project Meal Expense |  |  |  | 25 | calc
[7 empty] | 941 |  | 941
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 180 | 2500 | 450 | plgd /1000
|  | 1502 | Fire Water |  | 15 | 2000 | 30 | plgd /1000
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 30 | 2000 | 60 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 120 | 2000 | 240 | plgd /1000
|  | 1507 | Controls Rep |  | 60 | 3000 | 180 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 960 |  | 960
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 15 | plgd /1000
|  | 1602 | Concrete |  |  |  | 50 | plgd /1000
|  | 1603 | X Ray |  |  |  | 50 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 100 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 20 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 235 |  | 235
| 1700 Legal | [5 empty] | 30 | plgd /1000 | 30
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 300 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 300 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 300 | plgd /1000
|  | 1840 | Professional |  |  |  | 75 | plgd /1000
[7 empty] | 975 |  | 975
| 1900 Taxes | [6 empty] | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 400 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 9743.3 | 487.165 | calc
|  | 2150 | Labor Contingency |  | 5% | 5455.125 | 272.7562 | calc
[7 empty] | 1159.9212 |  | 1159.9212
[5 empty] | BOP Cost |  |  |  | 29823.5847
[5 empty] | % Markup |  |  | 40% | 11929.4339
[5 empty] | BOP Sales Price |  |  |  | 41753.0186
Note The price does not include the following:
1.0 Dual Fuel - Liquid Fuel only with centriguges and 5 days storage
2.0 Water injection for Nox
3.0 Changes to the existing 69 KV Substation
4.0 Taxes or Imprort Duties
The price does include the following:
1.0 Small Office/Control/Warehouse Building
2.0 Small DCS System
3.0 Potable water treatment system
4.0 Small Demin water treatment system 32,000 GPD for LM 6000 Sprint and Centrifuge
5.0 Two 69 KV GSU Transformers (1ea for 2 - LM 2500s and 1ea for LM 6000)
6.0 Two short transmission lines to existing 69 KV Substation - includes feed into the
existing substion with SF6 Breaker and Disconnect on each transmission line, but no
changes to the existing substation.
7.0 Two 100% Centrifuges w/ 500,000 gal Raw DFO and 200,000 gal treated DFO
8.0 Use 2ea PEEC Modular Control Buildings w/ MCCs located in Sedalia for LM 2500s - New Modular
Control Building with new MCC for LM 6000
9.0 New exhaust stacks for all three Gas Turbines
10.0 Ocean Freight at $1,800,000 and Inland Venn Freight at $900,000
11.0 Fire Water System with Foam on tanks

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | Elegua Site Power Plant | [5 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [5 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [5 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Clearing/Grubbing |  |  | 850 | 250 | 1 | 212500 | 7870.3704 | 30 | 236111.1111
2
3 | Demolition
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Containment Systems
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
236.1111

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | O/W Sep and Oil tank |  |  |  | 0 | 20 | 15 | 0 | 0 | 30 | 0
8 | GAS Turbine Hall |  |  |  | 0 | 130 | 1 | 0 | 0 | 18 | 0
9 | Liquid Fuel Under ground tank |  |  |  | 0 | 50 | 18 | 0 | 0 | 30 | 0
10
11 | Main Plant Area |  |  |  | 850 | 250 | 1 | 212500 | 7870.3704 | 30 | 236111.1111
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 236.1111

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Elegua Site Power Plant | [7 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [7 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [7 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5 | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy | E=Est
1 | POWER ISLAND | [8 empty] | 750
2 | GT Generators LM 2500+ |  |  | 2 | 65 | 18 | 4 | 9360 | 346.6667 | 750 | 260000 | 1733.3333
| GT Generator LM 6000 |  |  | 1 | 55 | 18 | 4 | 3960 | 146.6667 | 750 | 110000 | 733.3333
3 | Exhaust Stack |  |  | 3 | 25 | 25 | 3 | 5625 | 208.3333 | 750 | 156250 | 1041.6667
4 | HRSG |  |  | 0 | 75 | 16 | 4 | 0 | 0 | 750 | 0 | 0
5 | SCR |  |  | 0 | 52 | 16 | 4 | 0 | 0 | 750 | 0 | 0
6 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
7 | STG Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
8 | STG Inlet Chillers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
9 | Gen LO Pump Skid |  |  | 2 | 6 | 6 | 1 | 72 | 2.6667 | 750 | 2000 | 13.3333
10 | Aux Skid(s) for GTG |  |  | 3 | 10 | 8 | 1 | 240 | 8.8889 | 750 | 6666.6667 | 44.4444
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | 0 | 12 | 6 | 1 | 0 | 0 | 750 | 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  | 0 | 18 | 6 | 1 | 0 | 0 | 750 | 0 | 0
17 | Fin Fan L O Coolers |  |  | 3 | 15 | 15 | 2 | 1350 | 50 | 750 | 37500 | 250
18 | Gas Compressors |  |  | 0 | 30 | 15 | 3 | 0 | 0 | 750 | 0 | 0
19 | Fuel Gas Plant Metering Skid |  |  | 0 | 15 | 8 | 1 | 0 | 0 | 750 | 0 | 0
20 | Comp Fin Fans |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 750 | 0 | 0
21 | Waste Oil/Water Storage Tank |  |  | 1 | 30 | 22 | 1 | 660 | 24.4444 | 750 | 18333.3333 | 122.2222
22 | Oily Water Separator |  |  | 1 | 30 | 22 | 0.5 | 330 | 12.2222 | 750 | 9166.6667 | 61.1111
23 | Lubricant Storage Area |  |  | 0 | 45 | 30 | 1 | 0 | 0 | 750 | 0 | 0
24 | Instrument Air Comp Skid |  |  | 2 | 10 | 8 | 1 | 160 | 5.9259 | 750 | 4444.4444 | 29.6296
25 | Pipe Rack Stanchons |  |  | 30 | 2.5 | 2.5 | 6 | 1125 | 41.6667 | 750 | 31250 | 208.3333
26 | 15KV Cable Tray Stanchons |  |  | 9 | 2.5 | 2.5 | 6 | 337.5 | 12.5 | 750 | 9375 | 62.5
27 | Fire Water Pump Skid |  |  | 1 | 15 | 30 | 1 | 450 | 16.6667 | 750 | 12500 | 83.3333
28 | Area Light Poles |  |  | 6 | 2.5 | 3 | 5 | 225 | 8.3333 | 750 | 6250 | 41.6667
29 | Aux Trans fndns |  |  | 4 | 10 | 15 | 1.5 | 900 | 33.3333 | 750 | 25000 | 166.6667
30 | Cable Trenches see est |  |  | 1 | 200 | 15 | 1 | 3000 | 111.1111 | 750 | 83333.3333 | 555.5556
31 | Water Treatment Plant |  |  | 0 | 30 | 40 | 0 | 0 | 0 | 750 | 0 | 0
32 | Condenser Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
33 | Deaerator Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
34 | BFW Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
35 | Demin Water Pump skid |  |  | 0 | 8 | 6 | 1 | 0 | 0 | 750 | 0 | 0
36 | Demin Stg Tanks _20 M_ Gal |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 750 | 0 | 0
37 | Demin Forwarding Pumps |  |  | 0 | 8 | 6 | 1 | 0 | 0 | 750 | 0 | 0
38 | Chemical Injection Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
39 | Raw Water Tank Base |  |  | 1 | 45 | 45 | 1 | 2025 | 75 | 750 | 56250 | 375
40 | Fire Water Tank base |  |  | 0 | 35 | 20 | 1 | 0 | 0 | 750 | 0 | 0
41 | Emer Generator Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
42
43 | BUILDINGS
44 | Control Bldg/Office |  |  | 1 | 90 | 60 | 0.5 | 2700 | 100 | 750 | 75000 | 500
45 | Warehouse/Maintenance |  |  | 0 | 90 | 30 | 0.7 | 0 | 0 | 750 | 0 | 0
46 | Water Treatment Bldg |  |  | 0 | 60 | 50 | 0.7 | 0 | 0 | 750 | 0 | 0
47 | Gas Compressor Bldg |  |  | 0 | 60 | 40 | 1 | 0 | 0 | 750 | 0 | 0
48 | DFO Treatment Shed |  |  | 0 | 42 | 20 | 1 | 0 | 0 | 750 | 0 | 0
49 | Pwr Blk Utility Bldg's |  |  | 0 | 30 | 20 | 1 | 0 | 0 | 750 | 0 | 0
50 | Substation Bldg |  |  | 0 | 15 | 12 | 1 | 0 | 0 | 750 | 0 | 0
51 | Gas Turbine Hall |  |  | 0 | 120 | 50 | 0.7 | 0 | 0 | 750 | 0 | 0
52 | Liquid Fuel Unloading |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
53 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
54 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
55
56 | SUBSTATION
57 | GSU Transformer |  |  | 2 | 30 | 30 | 3 | 5400 | 200 | 750 | 150000 | 1000
58 | (___)KV SF6 Circuit Breaker |  |  | 2 | 15 | 15 | 1 | 450 | 16.6667 | 750 | 12500 | 83.3333
59 | (___)KV Disc Switch w/ Stand |  |  | 6 | 10 | 15 | 1 | 900 | 33.3333 | 750 | 25000 | 166.6667
60 | Dead End Tower |  |  | 0 | 15 | 10 | 3 | 0 | 0 | 750 | 0 | 0
61 | Transmission Line Poles |  |  | 5 | 5 | 5 | 20 | 2500 | 92.5926 | 750 | 69444.4444 | 462.963
62 | Insulator Support Base |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
63 | PT Support Base |  |  | 6 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
64 | Static Pole Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
65
66
67 |  |  | Total Cost of Foundations | [5 empty] | 1547.0185 |  | 1160.2639 | 7735.0926
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | Elegua Site Power Plant | [7 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description | [7 empty] | Cu | Price | Total | Q=Quote
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price | E=Est
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls | [8 empty] | 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
2 | Gen Removal Areas |  |  | 60 | 20 | 1 | 1200 | 44.4444 | 650 | 28888.8889
3 | Turbine Removal Areas |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
4 | Entry Ways |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
5 | Walk ways |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 650 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 400 | 20 | 0.7 | 5600 | 207.4074 | 650 | 134814.8148
12 | Parking Lot |  |  | 150 | 50 | 0.7 | 5250 | 194.4444 | 650 | 126388.8889
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 290.0926
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | Elegua Site Power Plant | [7 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price | E=Est
1
2 | Main Plant Area (less substa) |  |  | 1 | 240 | 220 | 0.5 | 26400 | 977.7778 | 1623.1111 | 35 | 56808.8889
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 35 | 0
5
6 | Substation |  |  | 0 | 400 | 150 | 1 | 0 | 0 | 0 | 35 | 0
7
8 | Road ways |  |  | 1 | 400 | 20 | 0.8 | 6400 | 237.037 | 393.4815 | 35 | 13771.8519
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | [8 empty] | 70.5807

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Elegua Site Power Plant | [5 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | # of | Qty | Price | Total | Q=Quote
No. | [5 empty] | Lbs / Tons |  |  | Price | E=Est
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 15 | 2500 | 37500
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [5 empty] | 11 | 3500 | 38500
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 5 | 15000 | 75000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 0 | 0 | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 0 | 15000 | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 15000 | 15000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 166

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | or Ftg | Price | Price | E=Est
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 1000 | 15 | 15000
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 2600 | 21 | 54600
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 0 | 0 | 0
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 3 | 4000 | 12000
10 | Motor Operated Double Gate(s) |  |  |  |  | 1 | 7500 | 7500
11 | Personnel Gate(s) |  |  |  |  | 4 | 500 | 2000
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 1 | 5000 | 5000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 96.1

## 109 Architectual
ARCHITECTUAL TREATMENT
[5 empty] | (1,000's) |  |  | 109
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | or Ftg | Price | Price | E=Est
1
2 | Trees and/or Shrubs - Revegetation
3 | Boundry Road |  |  |  |  | 0 | 0 | 0
4 | Within site |  |  |  |  | 1 | 50000 | 50000
5 | [5 empty] | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39
40 |  |  | Total Cost of Arch Treatment |  |  |  |  | 50

## 110 Evap Pond
EVAPORATION POND
|  |  |  | (1,000's) | [5 empty] | 110
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yard | cy | Price | E=Est
1 | Storm Water Evap Pond |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7
8
9
10
11 | [8 empty] | Price
12 | [6 empty] | sf |  | sf
13 | Liner |  |  | 0 | 0 |  | 0 |  | 3 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 | [9 empty] | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Elegua Site Power Plant | [5 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price | E=Est
1 | Office/Control/Warehouse |  |  |  | 90 | 60 | 5400 | 60 | 324000
2 | Water Treatment |  |  |  | 50 | 50 | 2500 | 55 | 137500
3 | Gas Compr Shed |  |  |  | 0 | 35 | 0 | 55 | 0
4 | DFO Treatment Shed |  |  |  | 40 | 30 | 1200 | 55 | 66000
5 |  |  |  |  | 0 |  | 0 |  | 0
6 |  |  |  |  | 0 |  | 0 |  | 0
7 |  |  |  |  | 0 |  | 0 |  | 0
8 |  |  |  |  | 0 | 0 | 0 | 0 | 0
9 |  |  |  |  | 0 | 0 | 0 | 0 | 0
10 |  |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 15 | 15 | 225 | 55 | 12375
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 539.875

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | Elegua Site Power Plant | [9 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [9 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [9 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
[15 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
| GTG | [5 empty] | 3% |  | 10
1 | GTG Type 2ea GE LM 2500 + 1ea LM 6000 |  |  | 3 | 0 | 0 | 0 | 0 | 10 | 6 | 35 | 6300 | 58.2116 | 366733.0485 |  | E
2 | Lube oils and Chemicals |  |  | 3 | 40000 | 120000 | 3600 | 10800 | 10 | 2 | 3 | 180 | 58.2116 | 10478.0871 |  | E
3 | Exhaust Stack |  |  | 3 | 220000 | 660000 | 40000 | 120000 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | Project Grouting |  |  | 3 | 50000 | 150000 | 4500 | 13500 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | GTG Tools |  |  | 1 | 50000 | 50000 | 1500 | 1500 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | Anchor Bolts |  |  | 3 | 45000 | 135000 | 4050 | 12150 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
31 | Inlet Evap Cooling System |  |  | 0 | 185000 | 0 | 10000 | 0 | 10 | 4 | 18 | 0 | 58.2116 | 0 |  | E
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
33 | Cooling Water Circulation Pumps |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 0 | 400000 | 0 | 25000 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 0 | 175000 | 0 | 0 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
40 | Fuel Gas Turbine Metering Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 0 | 125000 | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
42 | ESD Valve, ___" ___# |  |  | 0 | 20000 | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  | 1 | 30000 | 30000 | 900 | 900 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
46 | Metering Skid |  |  | 1 | 145000 | 145000 | 4350 | 4350 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
47 | Forwarding Pump Skid |  |  | 1 | 25000 | 25000 | 2000 | 2000 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
48 | Transfer Pump Skid |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
49 | Fuel Heating |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
50 | Filter Skids |  |  | 3 | 40000 | 120000 | 3600 | 10800 | 10 | 3 | 4 | 360 | 58.2116 | 20956.1742 |  | E
51 | Centrifuge |  |  | 2 | 300000 | 600000 | 18000 | 36000 | 10 | 4 | 8 | 640 | 58.2116 | 37255.4208 |  | E
52 | Injection Pump Skid |  |  | 0 | 150000 | 0 | 0 | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
53 | Storage Tank 500000 gal |  |  | 1 | 700000 | 700000 | 50000 | 50000 | 10 | 3 | 6 | 180 | 58.2116 | 10478.0871 |  | E
54 | Day Tank 200000 gal |  |  | 1 | 250000 | 250000 | 15000 | 15000 | 10 | 4 | 6 | 240 | 58.2116 | 13970.7828 |  | E
55
56 | Water Supply System
57 | Raw/Fire Water Storage Tank 250 M gal |  |  | 1 | 250000 | 250000 | 15000 | 15000 | 10 | 4 | 6 | 240 | 58.2116 | 13970.7828 |  | E
58 | Raw Water Supply Pumps |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 10 | 3 | 2 | 120 | 58.2116 | 6985.3914 |  | E
59 | Raw Water Forwarding Pumps |  |  | 2 | 15000 | 30000 | 900 | 1800 | 10 | 3 | 2 | 120 | 58.2116 | 6985.3914 |  | E
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
64 | Demin Treatment System 35 M gal/day |  |  | 1 | 150000 | 150000 | 7000 | 7000 | 10 | 4 | 8 | 320 | 58.2116 | 18627.7104 |  | E
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
66 | Demin water fiberglass tank |  |  | 2 | 25000 | 50000 | 1500 | 3000 | 10 | 3 | 4 | 240 | 58.2116 | 13970.7828 |  | E
67 | Demin forwarding pumps |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 10 | 3 | 2 | 120 | 58.2116 | 6985.3914 |  | E
68 | Demin Filter Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
69 | Demin Water Tank, SS 300M gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 1 | 50000 | 50000 | 5000 | 5000 | 10 | 3 | 6 | 180 | 58.2116 | 10478.0871 |  | E
73 | Oily Waste Tank 10000 gal |  |  | 1 | 10000 | 10000 | 300 | 300 | 10 | 2 | 3 | 60 | 58.2116 | 3492.6957 |  | E
74 | Waste Water Tank 10000 gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 1 | 15000 | 15000 | 450 | 450 | 10 | 2 | 2 | 40 | 58.2116 | 2328.4638 |  | E
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 1 | 650000 | 650000 | 15000 | 15000 | 10 | 3 | 6 | 180 | 58.2116 | 10478.0871 |  | E
79 | Fire Water System, valves, hydrants, monitors |  |  | 1 | 80000 | 80000 | 2400 | 2400 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
80 | [15 empty] | E
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 1 | 70000 | 70000 | 3000 | 3000 | 10 | 3 | 4 | 120 | 58.2116 | 6985.3914 |  | E
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
89 | Anti-Icing Ducting |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
90 | Sanitary Sewer |  |  | 1 | 20000 | 20000 | 600 | 600 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
91 | [8 empty] | 10
92
93 |  |  | Total Cost |  |  | 4465 |  | 336.1 |  |  |  | 9910
94 | [13 empty] | 576.8769
[9 empty] | Total Manhours |  |  | 9910
[9 empty] | Times Prod Factor |  | 2 | 19820 | 58.2116 | 1153.7538
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 600000 | 600000 | 18000 | 18000 | 10 | 15 | 90 | 13500 | 58.2116 | 785856.5325 |  | E
96 |  |  | Total Cost |  |  | 600 |  | 18 |  |  |  | 13500 |  | 785856.5325
97
98 | [8 empty] | Total Manhours |  |  | 13500
99 | [8 empty] | Times Prod Factor |  | 2 | 27000 | 58.2116
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 27
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 9.45
40.45
[8 empty] | Contr G&A 8% |  | 3.236
[8 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[7 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | Elegua Site Power Plant | [11 empty] | Date: |  | 2010-03-06
Customer: |  | Derwick | [11 empty] | Quote No: |  | T 1009
Location: |  | Guatire, Venn | [11 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-03-07
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | Power Island Equipment | [7 empty] | 3% |  | 10
2 | Gas Turbine Generator LM 2500 & LM 6000 |  |  |  |  | 3 |  |  | 0 |  | 10 | 6 | 35 | 6300 | 58.2116 | 366733.0485 |  | E
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | STG Cooling Tower |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7 | Chiller Package |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
8 | Water Treatment Package |  |  |  |  | 1 |  |  | 0 |  | 10 | 4 | 5 | 200 | 58.2116 | 11642.319 |  | E
9 | [13 empty] | 0 | 58.2116 | 0
10 | 15KV | [13 empty] | 58.2116
11 | Generator Breaker(s) |  |  |  |  | 3 | 135000 | 405000 | 12150 | 36450 | 10 | 4 | 5 | 600 | 58.2116 | 34926.957 |  | E
12 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
13 | Fused Disconnect(s) |  |  |  |  | 5 | 20000 | 100000 | 750 | 3750 | 10 | 3 | 3 | 450 | 58.2116 | 26195.2177 |  | E
14 | Bus Duct |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
17 | 5KV | [13 empty] | 58.2116
18 | Distribution Breaker(s) |  |  |  |  | 0 | 40000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
19 | Fused Disconnect(s) |  |  |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0 |  | E
20 | MCC's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 1 | 0 | 58.2116 | 0 |  | E
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0
23 | 600V | [13 empty] | 58.2116
24 | Distribution Panel(s) |  |  |  |  | 1 | 85000 | 85000 | 2550 | 2550 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
25 | GTG MCC(s) LM 6000 |  |  |  |  | 1 | 48000 | 48000 | 1500 | 1500 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
28 | BOP MCC(s) |  |  |  |  | 1 | 15000 | 15000 | 450 | 450 | 10 | 2 | 3 | 60 | 58.2116 | 3492.6957 |  | E
29 | Water Treatment MCC(s) |  |  |  |  | 0 | 12000 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0
32 | Aux Transformer(s) | [13 empty] | 58.2116
33 | 15/5KV ___________ MVA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
34 | 15/600V _750_ KVA |  |  |  |  | 4 | 55000 | 220000 | 2500 | 10000 | 10 | 3 | 5 | 600 | 58.2116 | 34926.957 |  | E
35 | 600/120/208V ________ KVA |  |  |  |  | 2 | 5000 | 10000 | 300 | 600 | 10 | 3 | 6 | 360 | 58.2116 | 20956.1742 |  | E
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
38 | Area Lighting | [13 empty] | 58.2116
39 | Poles _______ High |  |  |  |  | 6 | 1500 | 9000 | 270 | 1620 | 10 | 2 | 1 | 120 | 58.2116 | 6985.3914 |  | E
40 | Floodlights _______ Watts |  |  |  |  | 12 | 500 | 6000 | 50 | 600 | 10 | 1 | 0.5 | 60 | 58.2116 | 3492.6957 |  | E
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 58.2116 | 0
43 | Other Systems | [13 empty] | 58.2116
44 | UPS |  |  |  |  | 1 | 5000 | 5000 | 150 | 150 | 10 | 2 | 3 | 60 | 58.2116 | 3492.6957 |  | E
45 | DC |  |  |  |  | 1 | 35000 | 35000 | 1500 | 1500 | 10 | 2 | 4 | 80 | 58.2116 | 4656.9276 |  | E
46 | Cathodic Protection |  |  |  |  | 3 | 15000 | 45000 | 1350 | 4050 | 10 | 2 | 5 | 300 | 58.2116 | 17463.4785 |  | E
47 | Lightning Protection |  |  |  |  | 3 | 15000 | 45000 | 1350 | 4050 | 10 | 2 | 5 | 300 | 58.2116 | 17463.4785 |  | E
48 | [11 empty] | 0 | 0 | 0 | 58.2116 | 0
49 | [14 empty] | 58.2116
50 | Temporary Electric |  |  |  |  | 1 | 35000 | 35000 | 1050 | 1050 | 10 | 2 | 35 | 700 | 58.2116 | 40748.1165 |  | E
51 | Electrical Control Module LM 2500+ |  |  |  |  | 2 | 50000 | 100000 | 5000 | 10000 | 10 | 4 | 5 | 400 | 58.2116 | 23284.638 |  | E
52 | Electrical Control Module LM 6000 |  |  |  |  | 1 | 90000 | 90000 | 5000 | 5000 | 10 | 4 | 5 | 200 | 58.2116 | 11642.319
53 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 1253 |  | 83.32 |  |  |  | 10990 |  | 639.7454
[12 empty] | Productivity | 2 | 21980 | 58.2116 | 1279.4909
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 700000 | 700000 | 21000 | 21000 | 10 | 9 | 90 | 8100 | 58.2116 | 471513.9195 |  | E
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 700 |  | 21 |  |  |  | 8100 |  | 471.5139
58 | [10 empty] | Total Manhours |  |  | 8100
59 | [10 empty] | Times Prod Factor |  | 2 | 16200 | 58.2116 | 943.0278
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 27
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 9.45
40.45
[13 empty] | Contr G&A 8% |  | 3.236
[13 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[12 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N87: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q79: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | Elegua Site Power Plant | [12 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [12 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [12 empty] | Est By:
Bid Due Date: |  | 2010-03-07
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | [8 empty] | 3% |  | 10
2 | Main Power Transformer 11.5/33 KV, _35_ MVA |  |  |  |  | 2 | 700000 | 1400000 | 50000 | 100000 | 10 | 4 | 10 | 800 | 58.2116 | 46569.276 |  | E
3 | SF6 Circuit Breaker(s) ____ KV |  |  |  |  | 2 | 55000 | 110000 | 5000 | 10000 | 10 | 2 | 6 | 240 | 58.2116 | 13970.7828 |  | E
4 | Disconnect Switches ______ KV |  |  |  |  | 5 | 18000 | 90000 | 1500 | 7500 | 10 | 2 | 3 | 300 | 58.2116 | 17463.4785 |  | E
5 | Station Post Insulators ____ KV |  |  |  |  | 6 | 550 | 3300 | 99 | 594 | 10 | 2 | 0.05 | 6 | 58.2116 | 349.2696 |  | E
6 | Insulator Stanchons ______ High |  |  |  |  | 6 | 500 | 3000 | 90 | 540 | 10 | 1 | 0.5 | 30 | 58.2116 | 1746.3479 |  | E
7 | Insulator Stanchons ______ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.4 | 0 | 58.2116 | 0 |  | E
8 | Dead End Tower(s) |  |  |  |  | 4 | 25000 | 100000 | 3000 | 12000 | 10 | 6 | 3 | 720 | 58.2116 | 41912.3484 |  | E
9 | Alum Bus ______ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.08 | 0 | 58.2116 | 0 |  | E
10 | Alum Bus Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 58.2116 | 0 |  | E
11 | Alum Bus End Plugs _____ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.05 | 0 | 58.2116 | 0 |  | E
12 | Alum Bus Support Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 58.2116 | 0 |  | E
13 | Alum Bus "V" Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.08 | 0 | 58.2116 | 0 |  | E
14 | Static Wire Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 58.2116 | 0 |  | E
15 | Area Lighting Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 58.2116 | 0 |  | E
16 | Flood Lights, ______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
17 | #4/0 Grounding Conductor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0.03 | 0 | 58.2116 | 0 |  | E
18 | 3/4"x10'-0" Ground Rods & Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.04 | 0 | 58.2116 | 0 |  | E
19 | #90 Cadweld Shots |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0.3 | 0 | 58.2116 | 0 |  | E
20 | Metering CT's & CPT's |  |  |  |  | 2 | 35000 | 70000 | 2100 | 4200 | 10 | 2 | 5 | 200 | 58.2116 | 11642.319 |  | E | 0
21 | Station Metering w/ In & Out Capabilities |  |  |  |  | 1 | 40000 | 40000 | 1200 | 1200 | 10 | 2 | 6 | 120 | 58.2116 | 6985.3914 |  | E
22 | Station Protective Relay(s) |  |  |  |  | 2 | 40000 | 80000 | 2400 | 4800 | 10 | 2 | 6 | 240 | 58.2116 | 13970.7828 |  | E
23 | Station RTU |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
24 | 125V DC System |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
25 | Transmission Line Poles |  |  |  |  | 5 | 5000 | 25000 | 750 | 3750 | 10 | 4 | 2 | 400 | 58.2116 | 23284.638 |  | E
26 | Transmission Line Strain Insulators |  |  |  |  | 42 | 500 | 21000 | 100 | 4200 | 10 | 1 | 1 | 420 | 58.2116 | 24448.8699 |  | E | 0
27 | Cable Bus, Type _____, Size _____ |  |  |  |  | 6000 | 18 | 108000 | 2000 | 2000 | 10 | 1 | 0.02 | 1200 | 58.2116 | 69853.914 |  | E
28 | Main Power Transformer Oil, ______ Gal |  |  |  |  | 2 | 45000 | 90000 | 2500 | 5000 | 10 | 2 | 2 | 80 | 58.2116 | 4656.9276 |  | E
29 | Main Power Transformer Dress Out & Test |  |  |  |  | 2 | 50000 | 100000 | 0 | 0 | 10 | 2 | 3 | 60 | 58.2116 | 3492.6957 |  | E
30 | Fiber Optic Cable w/ Messenger Cable |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E | 0
31 | Fiber Optic Cable Fittings & Terminations |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
32 | [10 empty] | 10 |  |  |  | 58.2116
33 | [10 empty] | 10 |  |  |  | 58.2116
34 | [10 empty] | 10 |  |  |  | 58.2116
35 | [10 empty] | 10 |  |  |  | 58.2116 | 0
36 |  |  | Total Cost of Substation Equipment |  |  |  |  | 2240.3 |  | 155.784 |  |  |  | 4816 |  | 280.347
[12 empty] | Total Hours |  | 4816
[12 empty] | Prod Factor | 2 | 9632 | 58.2116 | 560.6941
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 27
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 9.45
40.45
[13 empty] | Contr G&A 8% |  | 3.236
[13 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[12 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N61: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q53: Insert Rate Here:

## 510 CEMS
CEM's
[5 empty] | (1,000's) |  |  | 510
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Cems | Cost | Cost | E=Est
1
2 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 120000 | 0
3
4 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 180000 | 0
5
6 | Installation Support |  |  |  |  | 0 | 18000 | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of CEM's |  |  |  |  | 0

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Elegua Site Power Plant | [8 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [8 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [8 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
[13 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | [6 empty] | 10
2 | Instrumentation for GTG |  |  | 3 | 25000 | 75000 | 10 | 2 | 10 | 600 | 58.2116 | 34926.957 |  | E
3 | [6 empty] | 10 |  |  |  | 58.2116 | 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
5 | [6 empty] | 10 |  |  |  | 58.2116
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
7 | [6 empty] | 10 |  |  |  | 58.2116
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 15000 | 15000 | 10 | 2 | 8 | 160 | 58.2116 | 9313.8552 |  | E
9 | [6 empty] | 10 |  |  |  | 58.2116
10 | Instrumentation for DFO Centrifuges |  |  | 1 | 20000 | 20000 | 10 | 2 | 10 | 200 | 58.2116 | 11642.319 |  | E
11 | [6 empty] | 10 |  |  |  | 58.2116
12 | Instrumentation for gas compressors |  |  | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
13 | [6 empty] | 10 |  |  |  | 58.2116
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
15 | [6 empty] | 10 |  |  |  | 58.2116
16 | [6 empty] | 10 |  |  |  | 58.2116
17 | [6 empty] | 10 |  |  |  | 58.2116
18 | [6 empty] | 10 |  |  |  | 58.2116
19 | [6 empty] | 10 |  |  |  | 58.2116
20 | [6 empty] | 10 |  |  |  | 58.2116
21 | [6 empty] | 10 |  |  |  | 58.2116
22 | [6 empty] | 10 |  |  |  | 58.2116
23 |  |  | Total Cost of Plant Instrumentation |  |  | 110 |  |  |  | 960 |  | 55.8831
[8 empty] | Total Hours |  | 960
[8 empty] | Prod Factor | 2 | 1920 | 58.2116 | 111.7663
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 27
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 9.45
40.45
[9 empty] | Contr G&A 8% |  | 3.236
[9 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[8 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [6 empty] | Cost | Cost | E=Est
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 300000 | 300000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 1 | 15000 | 15000
5
6 | Documentation |  |  |  |  | 1 | 30000 | 30000
7
8 |  |  |  |  | Total DCS |  |  | 345
9
10 | PBX Communications System |  |  |  |  | 1 | 15000 | 15
11
12 | Loud Speaker System |  |  |  |  | 1 | 15000 | 15
13
14 | TV / Security System |  |  |  |  | 0 | 20000 | 0
15
16
17
[7 empty] | taxable | 315030

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est
1 |  |  |  |  | 10
2 | GTG Erection |  |  | 3 | 10 | 12 | 30 | 10800 | 58.2116 | 628685.226 | E
3 |  |  |  |  | 10 |  |  |  | 58.2116
4 | HRSG Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
5 |  |  |  |  | 10 |  |  |  | 58.2116
6 | SCR Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
7 |  |  |  |  | 10 |  |  |  | 58.2116
8 | Water Treatment and FW Systems |  |  | 1 | 10 | 4 | 4 | 160 | 58.2116 | 9313.8552 | E
9 |  |  |  |  | 10 |  |  |  | 58.2116
10 | DFO Treatment System |  |  | 1 | 10 | 4 | 10 | 400 | 58.2116 | 23284.638 | E
11 |  |  |  |  | 10 |  |  |  | 58.2116
12 | BOP Equip Erection |  |  | 1 | 10 | 6 | 10 | 600 | 58.2116 | 34926.957 | E
13 |  |  |  |  | 10 |  |  |  | 58.2116
14 | Gas Compressor Erection |  |  | 0 | 10 | 6 | 5 | 0 | 58.2116 | 0 | E
15 |  |  |  |  | 10 |  |  |  | 58.2116
16 | Evap Cooling Erection |  |  | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 | E
17 |  |  |  |  | 10 |  |  |  | 58.2116
18 | Fire Water Pump Skid |  |  | 1 | 10 | 4 | 3 | 120 | 58.2116 | 6985.3914 | E
19 |  |  |  |  | 10 |  |  |  | 58.2116
20 | STG Erection |  |  | 0 | 10 | 12 | 36 | 0 | 58.2116 | 0 | E
21 |  |  |  |  | 10 |  |  |  | 58.2116
22 | STG Cooling Tower |  |  | 0 | 10 | 8 | 8 | 0 | 58.2116 | 0 | E
23 |  |  |  |  | 10 |  |  |  | 58.2116
24 |  |  |  |  | 10 |  |  |  | 58.2116
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 12080 |  | 703.1961
[6 empty] | Total Hours |  | 12080
[6 empty] | Prod Factor | 2 | 24160 | 58.2116 | 1406.3921
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 27
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 9.45
40.45
[7 empty] | Contr G&A 8% |  | 3.236
[7 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[6 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total | Q=Quote
No. | [5 empty] | Units | Unit | Days | Per Day | Cost | E=Est
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 3 | 6 | 18 | 7000 | 126000
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 3 | 50 | 150 | 3000 | 450000
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 1 | 50 | 50 | 100 | 5000
8 | 1 ea Man Lift |  |  |  |  | 0 | 0 | 0 | 80 | 0
9 | 2 ea Welders |  |  |  |  | 5 | 50 | 250 | 60 | 15000
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 100 | 100 | 3000 | 300000
51 | 2 ea Fork Lifts |  |  |  |  | 2 | 100 | 200 | 70 | 14000
52 | Welders |  |  |  |  | 5 | 60 | 300 | 70 | 21000
53 | 2 ea Pick ups |  |  |  |  | 2 | 100 | 200 | 30 | 6000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 0 | 0 | 0 | 70 | 0
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 2 | 6 | 12 | 4000 | 48000
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 40 | 40 | 1500 | 60000
60 | 2 ea Man Lifts |  |  |  |  | 1 | 40 | 40 | 80 | 3200
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 1320 |  | 1048.2

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Paint for GTG |  |  |  |  | 4 | 45000 | 180000 | E
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0 | E
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0 | E
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 0 | 40000 | 0 | E
9
10 | Paint for BOP Equipment |  |  |  |  | 2 | 50000 | 100000 | E
11
12 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0 | E
13
14 | Paint for Water Treatment |  |  |  |  | 2 | 15000 | 30000 | E
15
16 | Paint for DFO Treatment |  |  |  |  | 2 | 15000 | 30000 | E
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0 | E
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 340

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 336.1 | 336.1 | E
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 83.32 | 83.32 | E
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 155.784 | 155.784 | E
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 18 | 18 | E
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 21 | 21 | E
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 614.204

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | Elegua Site Power Plant | [6 empty] | Date: | 2010-03-06
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total | Q=Quote
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost | E=Est
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 4 | 6 | 2000 | 48000 |  | E
3 | Porta Potties |  |  |  |  | 2 | 6 | 350 | 4200 |  | E
4 | Water and Ice |  |  |  |  | 2 | 6 | 250 | 3000 |  | E
5 | Fed X |  |  |  |  | 1 | 6 | 500 | 3000 |  | E
6 | Telephone |  |  |  |  | 1 | 6 | 2500 | 15000 |  | E
7 | Office Supplies |  |  |  |  | 1 | 6 | 1000 | 6000 |  | E
8 | [6 empty] | 6
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 6 | 3500 | 21000 |  | E
10 | Misc Items |  |  |  |  | 1 | 6 | 3000 | 18000 |  | E
11 |  |  | Total Monthly Cost | [5 empty] | 118200
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 118200 |  | 118200
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 125000 | E
21 | Cad Station | [8 empty] | 5000 | E
22 | Computers | [8 empty] | 5000 | E
23 | Telephone System and Satalite Dish | [8 empty] | 15000 | E
24 | Plotter | [8 empty] | 7500 | E
25 | Fax Machine and Printers | [8 empty] | 3000 | E
26 | Misc equip | [8 empty] | 50000 | E
27 | Signs | [8 empty] | 0 | E
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 328.7

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Conceptual Engineering WGPS |  |  |  |  | 1 | 15000 | 15000 | E
3
4 | Detailed Engineering per GTG |  |  |  |  | 3 | 180000 | 540000
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 0 | 0 | 0
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 0 | 10000 | 0
13
14 | Detailed Engineering for civil/structural/bldg |  |  |  |  | 1 | 60000 | 60000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 615

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Soils & Environmental Eng |  |  |  |  | 0 | 45000 | 0
3
4 | Civil Engineer |  |  |  |  | 3 | 25000 | 75000
5
6 | Mechanical Engineer |  |  |  |  | 3 | 25000 | 75000
7
8 | Electrical Engineer |  |  |  |  | 3 | 25000 | 75000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 225

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | No. | Cost | Total | Q=Quote
No. | [5 empty] | Mos | Per Mo | Cost | E=Est
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 5 | 25000 | 125000 | E
2 | Admin Mgr Months on Project |  |  |  |  | 5 | 8000 | 40000 | E
3 | Scheduler |  |  |  |  | 5 | 8000 | 40000 | E
4 | Purchasing Agent |  |  |  |  | 5 | 8000 | 40000 | E
5 | Expediter |  |  |  |  | 5 | 5000 | 25000 | E
6 | Home Office Logistic Coordinator |  |  |  |  | 5 | 9000 | 45000 | E
7
8
9 | [6 empty] | 315000 |  | E
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 6 | 4000 | 24000 | E
18 | Construction Mngr |  |  |  |  | 6 | 20000 | 120000 | E
19 | Contract Cost Admin |  |  |  |  | 3 | 12000 | 36000 | E
20 | Scheduler |  |  |  |  | 5 | 10000 | 50000 | E
21 | Mechanical Supervisor |  |  |  |  | 5 | 20000 | 100000 | E
22 | Electrical Supervisor |  |  |  |  | 5 | 20000 | 100000 | E
23 | Civil Supervisor |  |  |  |  | 5 | 20000 | 100000 | E
24 | Clerks |  |  |  |  | 5 | 5000 | 25000 | E
25 | Warehousemen |  |  |  |  | 6 | 5000 | 30000 | E
26 | Draftsman |  |  |  |  | 5 | 7000 | 35000 | E
27 | Security |  |  |  |  | 5 | 15000 | 75000 | E
28 | Safety |  |  |  |  | 5 | 20000 | 100000 | E
29 | QA/QC Mngr |  |  |  |  | 5 | 20000 | 100000 | E
30
31
32 | [6 empty] | 895000 |  | E
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 6 | 12000 | 72000 | E
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0 | E
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 1282
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 6 | 11500 | 69000
47 | Mechanical __ ea ___ mos |  |  |  |  | 6 | 11500 | 69000
48 | Electrical __ ea ___ mos |  |  |  |  | 6 | 11500 | 69000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 6 | 11500 | 69000
50
51 |  |  |  |  | Total Inspectors |  |  | 276
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | No. | Cost | Total |  | Q=Quote
No. | [5 empty] | Units | Per Unit | Cost |  | E=Est
1
2 | Project & Construciton Management
3 | R T Air Fares (6 traveling regularly) |  |  |  |  | 48 | 3000 | 144000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 60 | 5000 | 300000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 15 | 5000 | 75000
6 | Misc expenditures |  |  |  |  | 2 | 50000 | 100000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 1600 | 65 | 104000
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 18 | 3000 | 54000 |  | E
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 180 | 300 | 54000 |  | E
16 | Auto Rental for Eng Days at Site |  |  |  |  | 180 | 250 | 45000 |  | E
17 | Misc Travel Expentitures |  |  |  |  | 1 | 40000 | 40000 |  | E
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 916
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 250 | 50 | 12500 | 625000
25
26 | Project Mgt Meal Expense |  |  |  |  | 250 | 50 | 12500 | 625000
27
28 |  |  |  |  | Total Meal Expense |  |  | 25
29
30
31
32
33
34
35
36

## 1900 Sales Tax
SALES TAXES
[5 empty] | (1,000's) |  |  | 1900
Project Name: |  | Elegua Site Power Plant |  |  |  |  | Date: | 2010-03-06
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-03-07
Item |  | Description |  |  |  | Total | State | Total
No. | [5 empty] | Cost | Tax | Taxes
1
2 | Major Mechanical Equipment |  |  |  |  | 5065 | 0.085 | 430.525
3
4 | Major Electrical Equipment |  |  |  |  | 1953 | 0 | 0
5
6 | Substation Equipment |  |  |  |  | 2240.3 | 0 | 0
7
8 | DCS Eqipment |  |  |  |  | 315030 | 0 | 0
9
10 | Instrument |  |  |  |  | 110 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28 |  |  | Total Cost of Plant Sales Taxes