## Recap
ProEnergy EPC
Job Description: |  |  | " Add'l Water Treatment for add'l LM 6000 PC"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  |  | 2010-05-11
I. Balance of Plant
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 0 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 0 | calc
|  | 103 | Concrete Foundations |  |  | 164.4444 | 24.6667 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 0 | calc
|  | 106 | Gravel - Sand |  |  |  | 0 | calc
|  | 107 | Structual Steel |  |  |  | 5 | calc
|  | 108 | Fencing |  |  |  | 0 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 29.6667 |  | 29.6667
| 200 Buildings | [5 empty] | 33 | calc | 33
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 515 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 2400 | 139.7078 | calc
|  | 330 | Mechanical Subcontractor |  |  | 2380 | 138.5436 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 50 | calc
[7 empty] | 843.2514 |  | 843.2514
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 33 | calc
|  | 420 | Substation Equipment |  |  |  | 0 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 680 | 39.5839 | calc
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 75 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 2000 | 116.4232 | calc
[7 empty] | 264.0071 |  | 264.0071
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 15 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 320 | 18.6277 | calc
[7 empty] | 33.6277 |  | 33.6277
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 0 | calc
|  | 620 | Telephone System |  |  |  | 0 | calc
|  | 630 | Public Address System |  |  |  | 0 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 0 |  | 0
700 Plant Erection
|  | 700 | Plant Erection |  |  | 640 | 37.2554 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 8420 | 37.2554 |  | 37.2554
| 800 Equipment Rental | [5 empty] | 35 | calc | 35
| 900 Painting | [5 empty] | 15 | calc | 15
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 49.69 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 1800 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 900 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 50 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 2799.69 |  | 2799.69
| 1100 Site Costs | [5 empty] | 0 | calc | 0
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 15 | calc
|  | 1202 | Local Eng |  |  |  | 0 | calc
[7 empty] | 15 |  | 15
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 32 | calc
|  | 1320 | Inspectors |  |  |  | 0 | calc
[7 empty] | 32 |  | 32
| 1400 Travel & Perdiem | [5 empty] | 32 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 32 |  | 32
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  |  | 2500 | 0 | plgd /1000
|  | 1502 | Fire Water |  |  | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 15 | 2000 | 30 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 0 | 2000 | 0 | plgd /1000
|  | 1507 | Controls Rep |  | 0 | 3000 | 0 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 30 |  | 30
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  |  | plgd /1000
|  | 1602 | Concrete |  |  |  |  | plgd /1000
|  | 1603 | X Ray |  |  |  |  | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  |  | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  |  | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 0 |  | 0
| 1700 Legal | [6 empty] | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  |  | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  |  | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  |  | plgd /1000
|  | 1840 | Professional |  |  |  |  | plgd /1000
[7 empty] | 0 |  | 0
| 1900 Taxes | [6 empty] | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 100 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 688 | 34.4 | calc
|  | 2150 | Labor Contingency |  | 5% | 490.1416 | 24.5071 | calc
[7 empty] | 158.9071 |  | 158.9071
[5 empty] | BOP Cost |  |  |  | 4358.4054
[5 empty] | % Markup |  |  | 40% | 1743.3622
[5 empty] | BOP Sales Price for Add'l Water Treatment |  |  |  | 6101.7675
Note The price does include the following:
1.0 Water Injection for Nox and Sprint
2.0 Water Treatment with add'l RO and EDI for 70M GPD
3.0 Additional Raw and Treated Water Tankage
4.0 Additional Space in the Water Treatment Building
The price does not include the following:
1.0 Taxes or Import Duties

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [7 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [7 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [7 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5 | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy | E=Est
1 | POWER ISLAND |  |  | Price: 750
2 | GT Generators LM 2500+ |  |  |  | 65 | 18 | 4 | 0 | 0 | 750 | 0 | 0
| GT Generator LM 6000 |  |  |  | 55 | 18 | 4 | 0 | 0 | 750 | 0 | 0
3 | Exhaust Stack |  |  |  | 25 | 25 | 3 | 0 | 0 | 750 | 0 | 0
4 | HRSG |  |  |  | 75 | 16 | 4 | 0 | 0 | 750 | 0 | 0
5 | SCR |  |  |  | 52 | 16 | 4 | 0 | 0 | 750 | 0 | 0
6 | STG |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
7 | STG Cooling Tower |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
8 | STG Inlet Chillers |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
9 | Gen LO Pump Skid |  |  |  | 6 | 6 | 1 | 0 | 0 | 750 | 0 | 0
10 | Aux Skid(s) for GTG |  |  |  | 10 | 8 | 1 | 0 | 0 | 750 | 0 | 0
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  |  | 12 | 6 | 1 | 0 | 0 | 750 | 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  |  | 18 | 6 | 1 | 0 | 0 | 750 | 0 | 0
17 | Fin Fan L O Coolers |  |  |  | 15 | 15 | 2 | 0 | 0 | 750 | 0 | 0
18 | Gas Compressors |  |  |  | 30 | 15 | 3 | 0 | 0 | 750 | 0 | 0
19 | Fuel Gas Plant Metering Skid |  |  |  | 15 | 8 | 1 | 0 | 0 | 750 | 0 | 0
20 | Comp Fin Fans |  |  |  | 15 | 15 | 1 | 0 | 0 | 750 | 0 | 0
21 | Waste Oil/Water Storage Tank |  |  |  | 30 | 22 | 1 | 0 | 0 | 750 | 0 | 0
22 | Oily Water Separator |  |  |  | 30 | 22 | 0.5 | 0 | 0 | 750 | 0 | 0
23 | Lubricant Storage Area |  |  |  | 45 | 30 | 1 | 0 | 0 | 750 | 0 | 0
24 | Instrument Air Comp Skid |  |  |  | 10 | 8 | 1 | 0 | 0 | 750 | 0 | 0
25 | Pipe Rack Stanchons |  |  |  | 2.5 | 2.5 | 6 | 0 | 0 | 750 | 0 | 0
26 | 15KV Cable Tray Stanchons |  |  |  | 2.5 | 2.5 | 6 | 0 | 0 | 750 | 0 | 0
27 | Fire Water Pump Skid |  |  |  | 15 | 30 | 1 | 0 | 0 | 750 | 0 | 0
28 | Area Light Poles |  |  |  | 2.5 | 3 | 5 | 0 | 0 | 750 | 0 | 0
29 | Aux Trans fndns |  |  |  | 10 | 15 | 1.5 | 0 | 0 | 750 | 0 | 0
30 | Cable Trenches see est |  |  |  | 300 | 15 | 1 | 0 | 0 | 750 | 0 | 0
31 | Water Treatment Plant |  |  | 1 | 30 | 20 | 0.7 | 420 | 15.5556 | 750 | 11666.6667 | 77.7778
32 | Condenser Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
33 | Deaerator Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
34 | BFW Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
35 | Demin Water Pump skid |  |  | 1 | 8 | 6 | 1 | 48 | 1.7778 | 750 | 1333.3333 | 8.8889
36 | Demin Stg Tanks _200 M_ Gal |  |  | 0 | 25 | 25 | 1 | 0 | 0 | 750 | 0 | 0
37 | Demin Forwarding Pumps |  |  | 0 | 8 | 6 | 1 | 0 | 0 | 750 | 0 | 0
38 | Chemical Injection Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
39 | Raw Water Tank Base |  |  | 0 | 45 | 45 | 1 | 0 | 0 | 750 | 0 | 0
40 | Fire Water Tank base |  |  | 0 | 35 | 20 | 1 | 0 | 0 | 750 | 0 | 0
41 | Emer Generator Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
42
43 | BUILDINGS
44 | Control Bldg/Office |  |  |  | 90 | 60 | 0.5 | 0 | 0 | 750 | 0 | 0
45 | Warehouse/Maintenance |  |  |  | 90 | 30 | 0.7 | 0 | 0 | 750 | 0 | 0
46 | Water Treatment Bldg |  |  | 1 | 30 | 20 | 0.7 | 420 | 15.5556 | 750 | 11666.6667 | 77.7778
47 | Gas Compressor Bldg |  |  | 0 | 60 | 40 | 1 | 0 | 0 | 750 | 0 | 0
48 | DFO Treatment Shed |  |  |  | 30 | 20 | 1 | 0 | 0 | 750 | 0 | 0
49 | Pwr Blk Utility Bldg's |  |  |  | 30 | 20 | 1 | 0 | 0 | 750 | 0 | 0
50 | Substation Bldg |  |  |  | 15 | 12 | 1 | 0 | 0 | 750 | 0 | 0
51 | Gas Turbine Hall |  |  |  | 120 | 50 | 0.7 | 0 | 0 | 750 | 0 | 0
52 | Liquid Fuel Unloading |  |  |  | 60 | 23 | 1 | 0 | 0 | 750 | 0 | 0
53 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
54 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
55
56 | SUBSTATION
57 | GSU Transformer |  |  |  | 30 | 30 | 3 | 0 | 0 | 750 | 0 | 0
58 | (___)KV SF6 Circuit Breaker |  |  |  | 15 | 15 | 1 | 0 | 0 | 750 | 0 | 0
59 | (___)KV Disc Switch w/ Stand |  |  |  | 10 | 15 | 1 | 0 | 0 | 750 | 0 | 0
60 | Dead End Tower |  |  |  | 15 | 10 | 3 | 0 | 0 | 750 | 0 | 0
61 | Transmission Line Poles |  |  |  | 5 | 5 | 20 | 0 | 0 | 750 | 0 | 0
62 | Insulator Support Base |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
63 | PT Support Base |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
64 | Static Pole Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0
65
66
67 |  |  | Total Cost of Foundations | Cubic: 32.8889; Total: 24.6667 | 164.4444
Note on K12: Insert Rate Here:

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [5 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | # of | Qty | Price | Total | Q=Quote
No. | [5 empty] | Lbs / Tons |  |  | Price | E=Est
1
2
3 | Misc Pipe Rack supports etc. | [6 empty] | 2500 | 0
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [6 empty] | 3500 | 0
6 | [8 empty] | 0
7 | GTG walkways and stairs | [6 empty] | 15000 | 0
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [6 empty] | 0 | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [6 empty] | 15000 | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 5000 | 5000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 5

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [5 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price | E=Est
1 | Office/Control/Warehouse |  |  |  | 0 | 60 | 0 | 60 | 0
2 | Water Treatment |  |  |  | 30 | 20 | 600 | 55 | 33000
3 | Gas Compr Shed |  |  |  | 0 | 35 | 0 | 55 | 0
4 | DFO Treatment Shed |  |  |  |  | 30 | 0 | 55 | 0
5 | [6 empty] | 0 |  | 0
6 | [6 empty] | 0 |  | 0
7 | [6 empty] | 0 |  | 0
8 | [5 empty] | 0 | 0 | 0 | 0
9 | [5 empty] | 0 | 0 | 0 | 0
10 | [5 empty] | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  |  | 15 | 0 | 55 | 0
12 | [5 empty] | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 33

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [9 empty] | Date: |  | 2010-05-08
Customer: |  | Derwick | [9 empty] | Quote No: |  | T 1009B - 1
Location: |  | Guatire, Venn | [9 empty] | Est By: |  | WTS/JC
Bid Due Date: |  | 2010-05-11
[15 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
| GTG |  |  | Unit: 3%; Hours: 10
1 | GTG Type 2ea GE LM 2500 + 1ea LM 6000 |  |  |  | 0 | 0 | 0 | 0 | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
2 | Lube oils and Chemicals |  |  |  |  | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
3 | Exhaust Stack |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | Project Grouting |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | GTG Tools |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | Anchor Bolts |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
31 | Inlet Evap Cooling System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 18 | 0 | 58.2116 | 0 |  | E
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
33 | Cooling Water Circulation Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  |  |  | 0 |  | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
39 | Fuel Gas Check Metering/Regulator Skid |  |  |  |  | 0 |  | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
40 | Fuel Gas Turbine Metering Skid |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  |  |  | 0 |  | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
42 | ESD Valve, ___" ___# |  |  |  |  | 0 |  | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
46 | Metering Skid |  |  |  |  | 0 |  | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
47 | Forwarding Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
48 | Transfer Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
49 | Fuel Heating |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
50 | Filter Skids |  |  |  |  | 0 |  | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
51 | Centrifuge |  |  |  |  | 0 |  | 0 | 10 | 4 | 8 | 0 | 58.2116 | 0 |  | E
52 | Injection Pump Skid |  |  |  |  | 0 |  | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
53 | Storage Tank 500000 gal |  |  |  |  | 0 |  | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
54 | Day Tank 200000 gal |  |  |  |  | 0 |  | 0 | 10 | 4 | 6 | 0 | 58.2116 | 0 |  | E
55
56 | Water Supply System
57 | Raw/Fire Water Storage Tank Addition 50M GaL |  |  | 1 | 50000 | 50000 | 15000 | 15000 | 10 | 4 | 6 | 240 | 58.2116 | 13970.7828 |  | E
58 | Raw Water Supply Pumps |  |  | 2 | 15000 | 30000 | 900 | 1800 | 10 | 3 | 2 | 120 | 58.2116 | 6985.3914 |  | E
59 | Raw Water Forwarding Pumps |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
64 | Demin Treatment System Add'n 70 M GPD |  |  | 1 | 150000 | 150000 | 7000 | 7000 | 10 | 4 | 8 | 320 | 58.2116 | 18627.7104 |  | E
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
66 | Demin water fiberglass tank |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 3 | 4 | 120 | 58.2116 | 6985.3914 |  | E
67 | Demin forwarding pumps |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 10 | 3 | 2 | 120 | 58.2116 | 6985.3914 |  | E
68 | Demin Filter Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
69 | Demin Water Tank, SS Add'n 75 M GPD |  |  | 1 | 150000 | 150000 | 15000 | 15000 | 10 | 3 | 5 | 150 | 58.2116 | 8731.7393 |  | E
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 0 | 50000 | 0 | 5000 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
73 | Oily Waste Tank 10000 gal |  |  | 0 | 10000 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
74 | Waste Water Tank 10000 gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 0 | 650000 | 0 | 15000 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
79 | Fire Water Foam System |  |  | 0 | 120000 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
80 | [15 empty] | E
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 1 | 70000 | 70000 | 3000 | 3000 | 10 | 3 | 4 | 120 | 58.2116 | 6985.3914 |  | E
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
89 | Anti-Icing Ducting |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
90 | Sanitary Sewer |  |  | 0 | 20000 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
91 |  |  |  | Hours: 10
92
93 |  |  | Total Cost | Total: 515; Frt: 44.95; Qty: 1190
94 |  |  |  | Total: 69.2718
[9 empty] | Total Manhours |  |  | 1190
[9 empty] | Times Prod Factor |  | 2 | 2380 | 58.2116 | 138.5436
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 50000 | 50000 | 1500 | 1500 | 10 | 4 | 30 | 1200 | 58.2116 | 69853.914 |  | E
96 |  |  | Total Cost | Total: 50; Frt: 1.5; Qty: 1200; Total: 69853.914
97
98 |  |  |  | Hours: Total Manhours; Qty: 1200
99 |  |  |  | Hours: Times Prod Factor; Qty: 2; Qty: 2400; Rate: 58.2116; Total: 139707.828
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 27
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 9.45
40.45
[8 empty] | Contr G&A 8% |  | 3.236
[8 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[7 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [11 empty] | Date: |  | 2010-05-08
Customer: |  | Derwick | [11 empty] | Quote No: |  | T 1009B - 1
Location: |  | Guatire, Venn | [11 empty] | Est By: |  | WTS/JC
Bid Due Date: |  | 2010-05-11
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | Power Island Equipment | [7 empty] | 3% |  | 10
2 | Gas Turbine Generator LM 2500 & LM 6000 |  |  |  |  | 0 |  |  | 0 |  | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | STG Cooling Tower |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7 | Chiller Package |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
8 | Water Treatment Package |  |  |  |  | 1 |  |  | 0 |  | 10 | 4 | 5 | 200 | 58.2116 | 11642.319 |  | E
9 | [13 empty] | 0 | 58.2116 | 0
10 | 15KV | [13 empty] | 58.2116
11 | Generator Breaker(s) |  |  |  |  | 0 | 135000 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
12 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
13 | Fused Disconnect(s) |  |  |  |  | 0 | 20000 | 0 | 750 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
14 | Bus Duct |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
17 | 5KV | [13 empty] | 58.2116
18 | Distribution Breaker(s) |  |  |  |  | 0 | 40000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
19 | Fused Disconnect(s) |  |  |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0 |  | E
20 | MCC's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 1 | 0 | 58.2116 | 0 |  | E
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0
23 | 600V | [13 empty] | 58.2116
24 | Distribution Panel(s) |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
25 | GTG MCC(s) LM 6000 |  |  |  |  | 0 | 48000 | 0 | 1500 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
| LM 2500 Plus MCCs |  |  |  |  | 0 | 20000 | 0 | 1000 |  | 10 | 2 | 5 | 0 | 58.2116 | 0
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
28 | BOP MCC(s) |  |  |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
29 | Water Treatment MCC(s) |  |  |  |  | 1 | 8000 | 8000 | 240 | 240 | 10 | 2 | 2 | 40 | 58.2116 | 2328.4638 |  | E
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0
32 | Aux Transformer(s) | [13 empty] | 58.2116
33 | 15/5KV ___________ MVA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
34 | 15/600V _750_ KVA |  |  |  |  | 0 | 55000 | 0 | 2500 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
35 | 600/120/208V ________ KVA |  |  |  |  | 0 | 5000 | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
38 | Area Lighting | [13 empty] | 58.2116
39 | Poles _______ High |  |  |  |  | 0 | 1500 | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
40 | Floodlights _______ Watts |  |  |  |  | 0 | 500 | 0 | 50 | 0 | 10 | 1 | 0.5 | 0 | 58.2116 | 0 |  | E
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 58.2116 | 0
43 | Other Systems | [13 empty] | 58.2116
44 | UPS |  |  |  |  | 0 | 10000 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
45 | DC |  |  |  |  | 0 | 35000 | 0 | 1500 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
46 | Cathodic Protection |  |  |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
47 | Lightning Protection |  |  |  |  | 0 | 15000 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
48 | [11 empty] | 0 | 0 | 0 | 58.2116 | 0
49 | [14 empty] | 58.2116
50 | Temporary Electric |  |  |  |  | 0 | 35000 | 0 | 0 | 0 | 10 | 2 | 35 | 0 | 58.2116 | 0 |  | E
51 | Electrical Control Module LM 2500+ |  |  |  |  | 0 | 40000 | 0 | 5000 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
52 | Electrical Control Module LM 6000 |  |  |  |  | 0 | 90000 | 0 | 5000 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 33 |  | 0.99 |  |  |  | 340 |  | 19.7919
[12 empty] | Productivity | 2 | 680 | 58.2116 | 39.5839
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 75000 | 75000 | 2250 | 2250 | 10 | 4 | 25 | 1000 | 58.2116 | 58211.595 |  | E
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 75 |  | 2.25 |  |  |  | 1000 |  | 58.2116
58 | [10 empty] | Total Manhours |  |  | 1000
59 | [10 empty] | Times Prod Factor |  | 2 | 2000 | 58.2116 | 116.4232
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 27
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 9.45
40.45
[13 empty] | Contr G&A 8% |  | 3.236
[13 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[12 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N88: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q80: Insert Rate Here:

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [8 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [8 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [8 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
[13 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 |  |  |  | Hours: 10
2 | Instrumentation for GTG |  |  | 0 | 25000 | 0 | 10 | 2 | 10 | 0 | 58.2116 | 0 |  | E
3 |  |  |  | Hours: 10; Rate: 58.2116; Total: 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
5 |  |  |  | Hours: 10; Rate: 58.2116
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
7 |  |  |  | Hours: 10; Rate: 58.2116
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 15000 | 15000 | 10 | 2 | 8 | 160 | 58.2116 | 9313.8552 |  | E
9 |  |  |  | Hours: 10; Rate: 58.2116
10 | Instrumentation for DFO Centrifuges |  |  | 0 | 20000 | 0 | 10 | 2 | 10 | 0 | 58.2116 | 0 |  | E
11 |  |  |  | Hours: 10; Rate: 58.2116
12 | Instrumentation for gas compressors |  |  | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
13 |  |  |  | Hours: 10; Rate: 58.2116
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
15 |  |  |  | Hours: 10; Rate: 58.2116
16 |  |  |  | Hours: 10; Rate: 58.2116
17 |  |  |  | Hours: 10; Rate: 58.2116
18 |  |  |  | Hours: 10; Rate: 58.2116
19 |  |  |  | Hours: 10; Rate: 58.2116
20 |  |  |  | Hours: 10; Rate: 58.2116
21 |  |  |  | Hours: 10; Rate: 58.2116
22 |  |  |  | Hours: 10; Rate: 58.2116
23 |  |  | Total Cost of Plant Instrumentation | Total: 15; Qty: 160; Total: 9.3139
[8 empty] | Total Hours |  | 160
[8 empty] | Prod Factor | 2 | 320 | 58.2116 | 18.6277
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 27
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 9.45
40.45
[9 empty] | Contr G&A 8% |  | 3.236
[9 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[8 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [6 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est
1 |  |  |  |  | 10
2 | GTG Erection |  |  | 0 | 10 | 12 | 30 | 0 | 58.2116 | 0 | E
3 |  |  |  |  | 10 |  |  |  | 58.2116
4 | HRSG Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
5 |  |  |  |  | 10 |  |  |  | 58.2116
6 | SCR Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
7 |  |  |  |  | 10 |  |  |  | 58.2116
8 | Water Treatment and FW Systems |  |  | 1 | 10 | 4 | 8 | 320 | 58.2116 | 18627.7104 | E
9 |  |  |  |  | 10 |  |  |  | 58.2116
10 | DFO Treatment System |  |  | 0 | 10 | 4 | 10 | 0 | 58.2116 | 0 | E
11 |  |  |  |  | 10 |  |  |  | 58.2116
12 | BOP Equip Erection |  |  | 0 | 10 | 6 | 10 | 0 | 58.2116 | 0 | E
13 |  |  |  |  | 10 |  |  |  | 58.2116
14 | Gas Compressor Erection |  |  | 0 | 10 | 6 | 5 | 0 | 58.2116 | 0 | E
15 |  |  |  |  | 10 |  |  |  | 58.2116
16 | Evap Cooling Erection |  |  | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 | E
17 |  |  |  |  | 10 |  |  |  | 58.2116
18 | Fire Water Pump Skid |  |  | 0 | 10 | 4 | 3 | 0 | 58.2116 | 0 | E
19 |  |  |  |  | 10 |  |  |  | 58.2116
20 | STG Erection |  |  | 0 | 10 | 12 | 36 | 0 | 58.2116 | 0 | E
21 |  |  |  |  | 10 |  |  |  | 58.2116
22 | STG Cooling Tower |  |  | 0 | 10 | 8 | 8 | 0 | 58.2116 | 0 | E
23 |  |  |  |  | 10 |  |  |  | 58.2116
24 |  |  |  |  | 10 |  |  |  | 58.2116
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 320 |  | 18.6277
[6 empty] | Total Hours |  | 320
[6 empty] | Prod Factor | 2 | 640 | 58.2116 | 37.2554
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 27
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 9.45
40.45
[7 empty] | Contr G&A 8% |  | 3.236
[7 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[6 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Guarenas Add'l H2O for LM 6000 | [6 empty] | Date: | 2010-05-08
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total | Q=Quote
No. | [5 empty] | Units | Unit | Days | Per Day | Cost | E=Est
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator | [5 empty] | 6 | 0 | 10000 | 0
3 | 1 ea 150 Ton Crane w/ operator | [5 empty] | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator | [5 empty] | 0 | 0 | 2000 | 0
5 | 1 ea 20 Ton Crane w/ operator | [5 empty] | 50 | 0 | 3800 | 0
6 | 2 ea Sky Tracs | [5 empty] | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts | [5 empty] | 50 | 0 | 100 | 0
8 | 1 ea Man Lift | [5 empty] | 0 | 0 | 80 | 0
9 | 2 ea Welders | [5 empty] | 50 | 0 | 60 | 0
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 10 | 10 | 3500 | 35000
51 | 2 ea Fork Lifts |  |  |  |  | 0 | 100 | 0 | 70 | 0
52 | Welders |  |  |  |  | 0 | 60 | 0 | 70 | 0
53 | 2 ea Pick ups |  |  |  |  | 0 | 100 | 0 | 30 | 0
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 0 | 0 | 0 | 70 | 0
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 6 | 0 | 4000 | 0
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 40 | 0 | 1500 | 0
60 | 2 ea Man Lifts |  |  |  |  | 0 | 40 | 0 | 80 | 0
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 10 |  | 35

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Paint for GTG |  |  |  |  | 0 | 45000 | 0 | E
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0 | E
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0 | E
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 0 | 40000 | 0 | E
9
10 | Paint for BOP Equipment |  |  |  |  | 0 | 50000 | 0 | E
11
12 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0 | E
13
14 | Paint for Water Treatment |  |  |  |  | 1 | 15000 | 15000 | E
15
16 | Paint for DFO Treatment |  |  |  |  | 0 | 15000 | 0 | E
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0 | E
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 15

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 44.95 | 44.95 | E
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 0.99 | 0.99 | E
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 0 | 0 | E
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 1.5 | 1.5 | E
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 2.25 | 2.25 | E
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 49.69

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Conceptual Engineering WGPS |  |  |  |  | 0 | 15000 | 0 | E
3
4 | Detailed Engineering per GTG |  |  |  |  | 0 | 180000 | 0
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 0 | 0 | 0
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 1 | 15000 | 15000
13
14 | Detailed Engineering for civil/structural/bldg |  |  |  |  | 0 | 80000 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 15

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | No. | Cost | Total | Q=Quote
No. | [5 empty] | Mos | Per Mo | Cost | E=Est
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 1 | 16000 | 16000 | E
2 | Admin Mgr Months on Project | [5 empty] | 8000 | 0 | E
3 | Scheduler | [5 empty] | 8000 | 0 | E
4 | Purchasing Agent | [5 empty] | 8000 | 0 | E
5 | Expediter | [5 empty] | 5000 | 0 | E
6 | Home Office Logistic Coordinator |  |  |  |  | 0 | 9000 | 0 | E
7
8
9 | [6 empty] | 16000 |  | E
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 0 | 4000 | 0 | E
18 | Construction Mngr |  |  |  |  | 1 | 16000 | 16000 | E
19 | Contract Cost Admin | [5 empty] | 12000 | 0 | E
20 | Scheduler | [5 empty] | 10000 | 0 | E
21 | Mechanical Supervisor | [5 empty] | 20000 | 0 | E
22 | Electrical Supervisor | [5 empty] | 20000 | 0 | E
23 | Civil Supervisor | [5 empty] | 20000 | 0 | E
24 | Clerks | [5 empty] | 5000 | 0 | E
25 | Warehousemen | [5 empty] | 5000 | 0 | E
26 | Draftsman | [5 empty] | 7000 | 0 | E
27 | Security | [5 empty] | 15000 | 0 | E
28 | Safety | [5 empty] | 20000 | 0 | E
29 | QA/QC Mngr | [5 empty] | 20000 | 0 | E
30
31
32 | [6 empty] | 16000 |  | E
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 0 | 12000 | 0 | E
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0 | E
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 32
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
47 | Mechanical __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
48 | Electrical __ ea ___ mos |  |  |  |  | 0 | 11500 | 0
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 0 | 11500 | 0
50
51 |  |  |  |  | Total Inspectors |  |  | 0
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | Guarenas Add'l H2O for LM 6000 |  |  |  |  | Date: | 2010-05-08
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009B - 1
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS/JC
Bid Due Date: |  | 2010-05-11
Item |  | Description |  |  |  | No. | Cost | Total |  | Q=Quote
No. | [5 empty] | Units | Per Unit | Cost |  | E=Est
1
2 | Project & Construciton Management
3 | R T Air Fares (6 traveling regularly) |  |  |  |  | 4 | 3000 | 12000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 4 | 5000 | 20000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 0 | 5000 | 0
6 | Misc expenditures |  |  |  |  | 0 | 50000 | 0
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 0 | 65 | 0
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 0 | 3000 | 0 |  | E
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 0 | 300 | 0 |  | E
16 | Auto Rental for Eng Days at Site |  |  |  |  | 0 | 250 | 0 |  | E
17 | Misc Travel Expentitures |  |  |  |  | 0 | 40000 | 0 |  | E
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 32
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36