| CODE TYPE OF MEETING |  |  | IT MAKES A DRAFT Nº |  |  | DATE MEETING EMISSION |  |  |  | PREPARED BY |  |  | MEETING PLACE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| External |  |  | 2 |  |  | 11/DIC//2009 |  | 19/DIC/2009 |  | lv010 |  |  | San Bernardino - P17 |  |
| SUBJECT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ASSISTANTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ABBREVIATIONS | COMPANY |  | COMPANY/SIGNATURE |  | TELEPHONES |  |  | Email |  |  |
| 1 | Jose Rosemary |  |  | JR | EDC |  |  |  |  |  |  |  |  |  |
| 2 | Julio Sansonetti |  |  | JS | EDC |  | N/D |  |  |  |  |  |  |  |
| 3 | Calabrese frame |  |  | MC011 | EDC |  | N/D |  |  |  |  |  |  |  |
| 4 | Jose Ortiz |  |  | JO | EDC |  |  |  |  |  |  |  |  |  |
| 5 | Wolfang Silva |  |  | WS | EDC |  | N/D |  |  |  |  |  |  |  |
| 6 | Leonardo Venegas |  |  | LVP | EDC |  |  |  |  |  |  |  |  |  |
| 7 | Marianela Colmenares |  |  | MC029 | EDC |  | N/D |  |  |  |  |  |  |  |
| 8 | Ricardo Leon |  |  | RL | Asincro |  |  |  |  |  |  |  |  |  |
| 9 | Antonio Escalona |  |  | AE | Asincro |  |  |  |  |  |  |  |  |  |
| 10 | Adalberto Redondo |  |  | AR | Inelmeca |  |  |  |  |  |  |  |  |  |
| 11 | Ricardo Nuñez |  |  | RN | ICA |  |  |  |  |  |  |  |  |  |
| 12 | Raul Pirela |  |  | RP | GTME |  |  |  |  |  |  |  |  |  |
| 13 | Elbano Provenzali |  |  | EP | GTME |  |  |  |  |  |  |  |  |  |
| 14 | Blas Herrera |  |  | VH | Cielemca |  |  |  |  |  |  |  |  |  |
| 15 |  |  |  |  | Elecnor |  | N/D |  |  |  |  |  |  |  |
| 16 |  |  |  |  | Derwick |  | N/D |  |  |  |  |  |  |  |
| 17 |  |  |  |  | Clover |  | N/D |  |  |  |  |  |  |  |
|  |  | JR, Summarizes on estatus present and excellent facts of the projects, doing special mention to the first Turbine of Luisa Cáceres Arismendi; and the important participation of the equipment of the GO of Generation and Transmission. It indicates that the Projects follow operative during the decembrina season, but to smaller load. ICA: One is working for the access road to the area where the pipe will be stored, will be 4 days additional. 5 kilometers of pipe were freed, lack samples of quality for the rest. The other 5 kilometers will be for Monday 21DIC09. They were loaded in Documentum, diverse specifications of valves. The accessories of greater diameter and length of time of delivery are locating. Points of Attention: Route Gas pipeline Soapire sector and progressive of route; work beginning is contemplated in January. Asincro raises the necessity of the more expeditious joint revision of documents. ICA sets out of general form the handling of the pipe as much for which it dispatches of the USA, like that comes in Containers of Asia. In summary, for the first fortnight of January, first 5 km of pipe will be had in the country. Second fortnight of January with two fronts of work, two side boom, a dobladora. Coordinating SHAH and Resident Engineer are in site. Each front of work will have one group of punteo, soon two pairs of soldering irons and another one with you pass end, final + another one with coating, X-rays, etc. Today must be loaded the procedures for located damages, and another one for areas majors. Meeting 06ENE10. Inelmeca: they expose that they are present in Daisy, for LCA, JBA and Lines - S/E´s. Beginning occurred to the Topographical survey in JBA. They must finalize this week the limit of batteries between Plant and S/E. Slope the Authorization of the Affectation of Territory, Ortiz informs that already the administrative proceeding is ready. In January the parcel of the S/E must be given. They are in process of revision of products of lines of communication, are coordinated with Red Gaona, for the cadastre impacts. This week must be defined the Plot Plan and presented/displayed to the EDC 21DIC09. Engineering is developing the people to it of Vepica. GTME has 3 groups of Topography. JR raises that GTME and Cielemca, could have a transport mechanism (type barge) to material transport towards the Island. Inelmeca informs that they are going to toil until 23DIC and retake 04ENE10. 29 and 30 are not going to toil. Asincro: it summarizes on the works: Derwick was mobilized towards the Raisa and initiated the desmalezamiento of the terrace, construction of provisional works and construction of the monitoring house. GTME took the trailers of provisional works, topographers and initiated ground studies. Elecnor is about to finish the preparation of provisional works. ICA already has a trailer in site and gave beginning to the preparation of the access road to the terrace where they will temporarily store the first lot of pipe. The personnel of Asincro already has permanent presence in the work, in January he will be continued reinforcing the field and engineering group. LVP: the unit of the GF of PCP (EDC) asks for a representing interlocutor of each Contractor, to deal with the subject Physical Security. The diverse contractors considered to the companies that come using the EDC, with the effect to facilitate the coordinations. JO: tests of the transforming in China were testified that are destined to Planta the Raisa, these equipment passed the tests successful. Esteem that the boat gathers the transforming in India 24DIC09, gets at Shanghai to gather transforming the 30 DIC09 both and about 46 days later arrive at Venezuelan Port. GTME: It asks for the Packing List of the turbines, tracks of the machines. Environmental study, already commented. JR indicates that certainty of specific planes of each machine does not exist. A formal request of the engineering of the Turbines exists. JR, is going to him to make arrive at more taking before 30ENE10 footprint of 7EA via two actions: with General Electric - August Medina, request of documents, planes. We have a representative of Inelmeca and of Asincro in New Jersey, one goes away to assign the responsibility to him to look for the Manuals in the USA. It is indicated that we continued working with the Packing existing List until has more detailed other. JBA, is giving to this week a document listing of Engineering with dates of delivery. The continuity of activities in the Island of preliminary Earthwork in JBA is conditioned, if they leave the permissions. Engineering: they continue activities with the normal labor calendar. Cielemca: it indicates that they already have all the machinery in the Island and additionally they have contacts to have access to the elements of the Ferry. With respect to the handling of the Documentum tool, today they received a reinforcing and they loaded the information, but they briefed additionally it in physicist. It is thankful for to the EDC the considered be them like part of the solution in the problematic one that appeared with respect to the dielectric oil. Lines, all the topographic profiles are given like definitive. Asuncio'n the Oaks, near Bush Seven (Forest of Gallery), recommend the drawn up one original avoiding this. Inelmeca has all the information, as well as the lawyers. Points of Attention: Permisología AOT - AAR, are not ready. They take 04ENE10, but they need the permissions. It depends on the EDC - Inelmeca, that can begin a month before. The facilities of constructions are finishing before 18DIC09, day that stop works. S/E´s all the Ground Studies are ready. They have agreement with GTME with respect to They are conscious that they contracted a IPC with defined reach. As added value briefed layout for final stage, Victor Mendible made the observation that in the configuration of Switch and Means, 10 switches exist. They presented/displayed the restlessness to advance some tries now, to avoid expenses future majors for the EDC. They gave to board architecture and other documents. They briefed the First Estimate since they completed the first landmark, and was given to the EDC today. JR: The EDC is had brings back to consciousness of the form in which it is executing the projects and the level of commitment that require of loas fundamental actors, as well as of the levels of uncertainty that are handled, but the group of projects must render accounts and especially any impact of cost and time. JR explains the budgetary restrictions for the additional ones, that are not required specifically for the reaches at the moment established. Next 3 meeting MIE20ENE10 to p.m. in San Bernardino. |  |  |  |  |  |  |  |  |  |  |  |  |